## Slide 1: FS_eNA_ph2 Status Report
Xiaobo Wu(Huawei), Aihua Li(China Mobile)

## Slide 2: 2.4) Rel-17 Study
Progress since SA#86:
  Only one SA2 WG meeting in Q1
  Total TUs requested for Study Phase in 2020 is 5.5. 1.5 TU is used and 4 TUs are remaining.
  Key Issue #3/5/6 are not to be progressed in R17 as a result of downscoping exercise.
RAN impacts or dependencies:
  Regarding KI#8: UE data as an input for analytics generation, the method of collection of RAN impacting parameters from the UE will be investigated after the MDT work of TSG RAN is completed
Next steps:
  Complete solution, evaluation and conclusion(s) for each Key Issue.
  Find a way to resolve RAN dependencies
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_Ph2 | Study on Enablers for Network Automation for 5G - phase 2 | 15 > 32% | June, 20 | SP-190557

## Slide 3: FS_eNA_ph2 status after SA2#136AH (1/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_ph2 | Study on Enablers for Network Automation for 5G - phase 2 | 15 > 32% | June, 20 | SP-190557
General
  FS_eNA_ph2 TR 23.700-91 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 5.5. 1.5 TU is used and 4 TUs are remaining.
Use cases
  Use Case #1: NWDAF-assisted RAT/frequency selection
    Mapped to Key issue #12: NWDAF-assisted RFSP policy
  Use Case #2: NWDAF supporting detection of anomaly events and helping in analysing its cause
    Mapped to Key Issue #20: NWDAF assisting in detecting anomaly events for the user plane
  Use Case #3: NWDAF support for dispersion analytics
    Mapped to Key Issue #9: Dispersion analytic output provided by NWDAF
  Use Case #4: Analytics Assisted Smart City Applications
    No key issue and is not to be progressed

## Slide 4: FS_eNA_ph2 status after SA2#136AH (2/4)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_ph2 | Study on Enablers for Network Automation for 5G - phase 2 | 15 > 32% | June, 20 | SP-190557
Use cases
  Use Case #5: NWDAF supporting the detection of cyber-attacks
    No key issue and is not to be progressed
  Use Case #6: Supporting edge computing
    Mapped to Key Issue #16: UP optimization for edge computing
  Use Case #7: Real-time data collection and analytics delivery by NWDAF
    Mapped to Key Issue #18: Enhancement for real-time communication with NWDAF

## Slide 5: FS_eNA_ph2 status after SA2#136AH (3/4)
  Key Issues for Objective 1 (Remaining from R16):
  Key Issue #4: Remaining aspects on how to ensure that slice SLA is guaranteed
    One new Soution#2 was added at SA2#136AH to propose that the NSSF subscribes to slice service experience and load level analytics to enhance its slice selection functionality for new UE registrations in coordination with OAM.
  Key Issue #8: UE data as an input for analytics generation
  Key Issue #7: Adding Application attributes and KPIs as the Input data in some services described in TS 23.288 [5]
  Key Issue #15: User consent for UE data collection/analysis
    One New Solution#3 was added at SA2#136AH to propose that AF provision the user data consent to UDM/UDR and then NWDAF retrieves the information from UDM/UDR to help determine to trigger UE data collection.
  Key Issues for Objective 2&4 (Architecture Enhancement&New Use Case/Key Issue)
  Key Issue #1: Logical decomposition of NWDAF and possible interactions between logical functions
  Key Issue #2: Multiple NWDAF instances
  Key Issue #13: Triggering conditions for analytics
  Key Issue #17: Definition of accuracy levels
  Key Issue #19: Trained data model sharing between multiple NWDAF instances

## Slide 6: FS_eNA_ph2 status after SA2#136AH (4/4)
  Key Issues for Objective 3 (Rel-16 NWDAF features enhancement)
  Key Issue #9: Dispersion analytic output provided by NWDAF
  Key Issue #10: NWDAF Assisted UP Optimization
  Key Issue #11: Increasing efficiency of data collection
    One new Solution#1 was added at SA2#136AH to propose a solution inspired from Publish-Subscribe mechanism (including 3GPP Producer Adaptor, 3GPP Consumer Adaptor, Messaging Infrastructure, etc.) to increase efficiency of data collection.
  Key issue #12: NWDAF-assisted RFSP policy
    One New Solution#4 was added at SA2#136AH to propose that NWDAF could derive the Service Behaviour analytics (including application ID, Occurrence probability, Duration Time, Spatial validity, etc.) to help the consumer NF derive a suitable RFSP index.
  Key Issue #14: NWDAF-assisted application detection
  Key Issue #16: UP optimization for edge computing
  Key Issue #18: Enhancement for real-time communication with NWDAF
  Key Issue #20: NWDAF assisting in detecting anomaly events for the user plane
  Key Issue #21: NWDAF assisting in user plane performance
Key issues NOT to be progressed in R17 :
  Key Issue #3: Mapping of NWDAF use cases to NFs and identify actions that could be taken based on NWDAF analytics and predictions
  Key Issue #5: New types of outputs provided by NWDAF
  Key Issue #6: Study possible mechanisms for improved correctness of NWDAF analytics

## Slide 7: FS_eNA_ph2 status after SA2#136AH (4/4)
  RAN impacts and dependencies:
  Find a way to resolve RAN dependencies for UE data Reporting by e.g. sending LS to RAN group once the solution(s) are available and stable enough.
Contentious Issue:
  Whether or not the architecture/protocol solution for UPF data reporting will be out of scope of this study.
Focus for the Next Meeting (SA2#138):
  Any new Key Issue will be low priority unless supported by large number of companies.
Overall Plan:
  SA2#138 (Apr): Complete description of existing solutions. Capture New solutions.
  SA2#139 (May): Start initial evaluation and conclusions. Submit TR 23.700-91 to SA#88 plenary for one-stop approval. Agree a WID.
Risks:
  Completion of the study may not be possible in Q2 for all key issues and scheduling conf calls to make progress and dive a solution merge .

## Slide 8: FS_eNA_ph2 status after SA2#139E (1/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_Ph2 | Study on Enablers for Network Automation for 5G - phase 2 | 32% -> 55% | June, 20 -> Sep, 20 | SP-190557
  General
  FS_eNA_ph2 TR 23.700-91 v0.4.0 is available here.
  SID has 18 KI and 56 solutions in the TR and no solutions captured for KI#7/20/21 so far.
  Key Issue #1: Logical decomposition of NWDAF and possible interactions between logical functions
  8 solutions are agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s);Start evaluation.
  Key Issue #2: Multiple NWDAF instances
  22 solutions are agreed for this key issue.
  Next steps:
    Resolve ENs in solutions and complete/merge/classify the existing solutions;
    New solutions is allowed.
  Risk: The solutions are diverging and try to find a criteria for evaluation.
  Key Issue #3: Mapping of NWDAF use cases to NFs and identify actions that could be taken based on NWDAF analytics and predictions (NOT to be progressed in R17)

## Slide 9: FS_eNA_ph2 status after SA2#139E (2/5)
  Key Issue #4: Remaining aspects on how to ensure that slice SLA is guaranteed
  1 existing solution is revised.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); ); Start evaluation.
  Key Issue #5: New types of outputs provided by NWDAF (NOT to be progressed in R17)
  Key Issue #6: Study possible mechanisms for improved correctness of NWDAF analytics (NOT to be progressed in R17)
  Key Issue #7: Adding Application attributes and KPIs as the Input data in some services described in TS 23.288 [5]
  No solutions are captured for this key issue.
  Next steps: Capture new solution(s).
  Key Issue #8: UE data as an input for analytics generation
  3 solutions are agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.
  Key Issue #9: Dispersion analytic output provided by NWDAF
  1 solution is agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.
  Key Issue #10: NWDAF Assisted UP Optimization
  1 solution is agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.

## Slide 10: FS_eNA_ph2 status after SA2#139E (3/5)
  Key Issue #11: Increasing efficiency of data collection
  14 solutions are agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete/merge/classify the existing solutions and capture new solution(s); Start evaluation.
  Key issue #12: NWDAF-assisted RFSP policy
  5 solutions are agreed for this key issue, 1 existing solution is revised.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.
  Key Issue #13: Triggering conditions for analytics
  2 solutions are agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.
  Key Issue #14: NWDAF-assisted application detection
  1 solution is agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.
  Key Issue #15: User consent for UE data collection/analysis
  1 existing solution is revised and LS sent to SA3 to confirm the requirement
  Next steps: Resolve ENs in solutions and capture new solution(s); Start evaluation.
  Key Issue #16: UP optimization for edge computing
  6 solutions are agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.
  Key Issue #17: Definition of accuracy levels
  1 solution is agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.

## Slide 11: FS_eNA_ph2 status after SA2#139E (4/5)
  Key Issue #18: Enhancement for real-time communication with NWDAF
  3 solutions are agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.
  Key Issue #19: Trained data model sharing between multiple NWDAF instances
  3 solutions are agreed for this key issue.
  Next steps: Resolve ENs in solutions and complete the existing solutions and capture new solution(s); Start evaluation.
  Key Issue #20: NWDAF assisting in detecting anomaly events for the user plane
  No solutions are captured for this key issue.
  Next steps: Capture new solution(s).
  Key Issue #21: NWDAF assisting in user plane performance
  No solutions are captured for this key issue.
  Next steps: Capture new solution(s).

## Slide 12: FS_eNA_ph2 status after SA2#139E (5/5)
  RAN impacts and dependencies:
  None identified so far.
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#140E):
  Complete the existing solutions and dive a solution merge/classification and start evaluation;
  Capture New solutions and SA2#140E August e-meeting would be the last meeting for new solutions, which should be reasonably complete.
Overall Plan:
  2020 Q3: Complete the existing solutions and capture new solutions and merge/classify solutions and start evaluation. Submit TR 23.700-91 to SA#89e plenary for information.
  2020 Q4: Overall evaluation and make conclusions for each Key Issue. Submit TR 23.700-91 to SA#90e plenary for one-stop approval. Agree a WID.
Risks:
  SID has 18 KI and 56 solutions in the TR and no solutions captured for KI#7/20/21 so far. There is risk that Key Issues will not be concluded by Sep, 20. Original TU estimates were severely under-estimated.

## Slide 13: backup