## Slide 1: FS_MUSIM Status Report
Sašo Stojanovski
Intel Corporation

## Slide 2: FS_MUSIM Status at SA#89-e
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 60% > 80% | Jun, 20 -> Dec, 20 | SP-200091
Progress since SA#88-e:
  The TR includes initial evaluations on all three key issues and some interim conclusions for KI#3.
  RAN impacts and dependencies:
  LS OUT sent to RAN2, RAN3 and SA3 with request for feedback on the principles of some solutions
Next steps:
  Final evaluation and conclusion of what to progress towards a normative phase in Q4
  Target Completion: The target completion date for the study is proposed to be moved to Dec 2020.

## Slide 3: FS_MUSIM status after SA2#140E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 60% > 80% | Jun, 20 -> Dec, 20 | SP-200091
General
  FS_MUSIM TR 23.761 v0.5.0 is available here.
Key Issue 1 (Handling of MT Service):
  Four new solutions agreed (two of which for the case where the two USIMs are served by the same network).
  Interim evaluations agreed.
  Next Steps: Draw final evaluations and conclusions in Q4. No new solutions are accepted.
Key Issue 2 (Enable Paging reception):
  Interim evaluations agreed.
  Next Steps: Draw final evaluations and conclusions in Q4. No new solutions are accepted.
Key Issue 3 (Co-ordinated leaving):
  One new solution agreed.
  Interim evaluations and conclusions agreed.
  Next Steps: Draw final evaluations and conclusions in Q4. No new solutions are accepted.

## Slide 4: FS_MUSIM status after SA2#140E (2/2)
  RAN impacts and dependencies:
  All three key issues may potentially lead to solutions with RAN impact and may require RAN coordination.
  Feedback requested from RAN WGs (LS OUT in S2-2006037)
  SA3 dependencies:
  Feedback requested from SA3 on security aspects of some solutions (LS OUT in S2-2006011)
Contentious Issue:
  None
Focus for the Next Meeting (SA2#141E):
  Ahead of SA2#141E: Organize a conference call to discuss Way Forward proposals to finalize the conclusions.
  During SA2#141E:
    Focus on finalizing the conclusions (where possible).
Overall Plan:
  SA2#141E (Oct) and SA2#142E (Nov) : Final evaluations and conclusions. Submit TR 23.761 to SA#90 plenary for approval. Agree a WID on concluded aspects.
Risks:
  The target completion date for the study is proposed to be moved to Dec 2020. Normative phase is unlikely to complete in Q4.