## Slide 1: FS_eNPN Status Report
Peter Hedman
Ericsson

## Slide 2: FS_eNPN status after SA2#140E (1/3)
General
  FS_eNPN is captured in TR 23.700-07 and v0.5.0 will be available here.
  Total TUs requested for Study Phase in 2020 is 5. 2 TUs and two e-meetings have been used.
  TR 23.700-07 was agreed to be sent for information, while cover sheet was noted and will be submitted as company contribution
Key Issue 1 (Enhancements to Support SNPN along with credentials owned by an entity separate from the SNPN):
  9 P-CRs agreed updating existing solutions, and 4 new added solutions were agreed for inclusion in the TR. Total number of solutions for KI#1 is 12.
  LS sent to SA1 on possibility of extending PLMN selection to include SNPN selection for UEs with a PLMN subscription
  Interim conclusions proposed but were not agreed due to different opinion on AAA-type of functionality.
  Next Steps: Next meeting (SA2#141E) will focus on evaluation and attempts to conclusions.
Key Issue 2 (NPN support for Video, Imaging and Audio for Professional Applications (VIAPA))
  3 P-CRs agreed updating existing solutions, and 7 new added solutions were agreed for inclusion in the TR. Total number of solutions for KI#2 is 15.
  Interim conclusions agreed with EN related to QoS and N3IWF architecture
  Next Steps: Next meeting (SA2#141E) will focus on evaluation and attempts to conclusions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 55% > 75% | Sep, 20-> Dec, 20 | SP-200094

## Slide 3: FS_eNPN status after SA2#140E (2/3)
Key Issue 3 (Support of IMS voice and emergency services for SNPN)
  Key issue updated such that KI includes to study any SNPN selection impacts due to support of IMS voice
  6 P-CRs agreed updating existing solutions, and 2 new added solutions were agreed for inclusion in the TR. Total number of solutions for KI#1 is 10.
  LS sent to SA1, requesting feedback on Use Cases for providing IMS services to SNPN (S2-2006029)
  Interim conclusions agreed
  Next Steps: Next meeting (SA2#141E) will focus on evaluation and attempts to conclusions.
Key Issue 4 (UE Onboarding and remote provisioning)
  17 P-CRs agreed updating existing solutions, and no new added solutions were agreed for inclusion in the TR. Total number of solutions for KI#1 is 17.
  Interim conclusions agreed
  LS sent to SA3, requesting feedback on interim conclusions and related ENs
  Next Steps: Next meeting (SA2#141E) will focus on evaluation and attempts to conclusions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 55% > 75% | Sep, 20-> Dec, 20 | SP-200094

## Slide 4: FS_eNPN status after SA2#140E (3/3)
  RAN impacts and dependencies:
  Key issues 1, 2, 3 and 4 may potentially lead to solutions with RAN impact and may require RAN coordination.
  Impacts are SIB related for solutions related to Key issues 1, 3 and 4, new RRC indications for solutions related to Key issues 4 and additional NGAP impacts for solutions related to Key issues 2 and 4
SA3 dependencies
  SA3 dependencies identified for solutions related to key issue 1 and LS sent to SA3 in S2-2004385, but also other SA3 dependencies identified by ENs for solutions related to key issue 1, 3 and 4. LS sent to SA3 to get feedback on interim conclusions for KI#4 and related ENs.
  One solution (#17) for key issue 2 has security related ENs, but FFS whether to be resolved by SA2.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#141E):
  Organize a conference call before SA2#141E to discuss Way Forward proposals.
  Resolve major open issues for the solutions and find way forward for concluding the key issues (i.e. evaluations and conclusions).
  If show-stoppers found e.g. related to other WG dependencies that cannot be resolved by SA2, send LS with explicit question
  Find a way to resolve RAN as well as SA3 dependencies as given the delayed start of eNPN related work in RAN and SA3.
Overall Plan:
  SA2#141E (Oct): Evaluation and conclusions. Based on input from RAN2/3, SA1 and SA3, new solutions/options may be proposed.
  SA2#142E (Nov): Final evaluation and conclusions. Submit TR 23.700-07 to SA#90 plenary for approval. Agree a WID.
Risks:
  Completion of the study may not be possible in Q4 for all key issues, due to RAN and SA3 dependencies

## Slide 5: FS_eNPN Status at SA#89
Progress since SA#88-e:
  35 P-CRs agreed updating solutions and 13 new solutions added.
  LS, related to KI#1, sent to SA1 asking for possibility of extending PLMN selection to include SNPN selection for UEs with a PLMN subscription
  LS, related to KI#3, sent to SA1, requesting feedback on Use Cases for providing IMS services to SNPN
  LS, related to KI#4, sent to SA3, requesting feedback on interim conclusions and related ENs
  Interim conclusions agreed for KI#2, KI#3 and KI#4.
  RAN impacts and dependencies:
  RAN impact depends on the conclusions of the KIs (e.g. KI#1, KI#2, KI#3 and KI#4).
Next steps:
  Potentially add any new solutions based on feedback from SA3 or RAN WGs
  Evaluation and agree on final conclusions
  Target Completion: December TSG SA#90.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 55% > 75% | Sep, 20-> Dec, 20 | SP-200094