## Slide 1: FS_enh_EC Status Report
Hui Ni
Huawei

## Slide 2
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 60% -> 70% | Sep, 2020 -> Dec, 2020 | SP-190185
Progress since SA#88-e:
  6 new Solutions have been agreed to address various KIs.
  37 existing solutions have been updated to address Editor’s Notes.
  KI#1 (Discovery of EAS) has been partially concluded.
  2 LSs were sent to SA3 and SA6 respectively for coordination.
  The TR 23.748 is sent to SA plenary for information.
RAN impacts and dependencies:
  None identified
Next steps:
  Complete evaluation and conclusion of all KIs.
  Submit a WID to SA plenary for normative work.
2.4) Rel-17 Study/Work (2/10)

## Slide 3: FS_enh_EC status after SA2#140e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 60% -> 70% | Sep, 2020 -> Dec, 2020 | SP-190185
General
  FS_enh_EC TR 23.748 v0.5.0 is available at link. The TR is sent to SA plenary for information.
  Two LSs were sent to SA3 and SA6 respectively for coordination.
Key issue 1 (Discovery of Edge Application Server)
  17 existing solutions were revised.
  The key issue was partially concluded (on URSP/ECS provisioning/ Distributed Anchor connectivity models).
  Next steps: Resolve ENs in solutions and conclusion parts; Complete Key issue conclusion (on Session Breakout connectivity model).
Key issue 2 (Edge relocation)
  5 new solutions were approved, 11 existing solutions were revised. Totally 25 solutions for KI#2.
  Next steps: Classify the solutions based on different aspects; evaluate solutions and conclude the Key issue.
Key issue 3 (Network Information Provisioning to Local Applications with low latency)
  1 new solution was approved, 7 existing solutions were revised. Totally 10 solutions for KI#3.
  Next steps: Evaluate solutions and conclude the Key issue.
Key issue 5 (Activating the traffic routing towards Local Data Network per AF request)
  2 existing solutions were revised. Totally 2 solutions for KI#5.
  Overall evaluation was approved.
  Next steps: Conclude the Key issue.

## Slide 4: FS_enh_EC status after SA2#140e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  LDNSR placement issue needs to be resolved.
Focus for the Next Meeting (SA2#141e):
  Conclusions for KI#2, KI#3, KI#5 and session breakout case of KI#1.
  Proposals for new solution, new/updated key issue will NOT be discussed.
  Any update to existing solution should focus on resolving ENs and keep the solution stable.
Overall Plan:
  SA2#141e: Concluding all KIs.
  SA2#142e: All remaining works for completing SI. Agreeing to a WID.

## Slide 5: backup

## Slide 6: FS_enh_EC status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 20 > 40% | June, 20 | SP-190185
General
  FS_enh_EC TR 23.748 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 4. 1 TU is used and 3 TUs are remaining.
Key issue 1 (Discovery of Edge Application Server)
  7 new solutions are agreed for this key issue.
  Next steps: Resolve ENs in the solutions; Solution evaluations; Way forwards towards conclusion.
Key issue 2 (Edge relocation)
  No solution discussed yet.
Key issue 3 (Network Information Provisioning to Local Applications with low latency)
  No solution discussed yet.
Key issue 4 (Consecutive traffic steering in different N6-LAN)
  Downscoped. Will not be studied in Rel-17.
Key issue 5 (Activating the traffic routing towards Local Data Network per AF request)
  No solution discussed yet.

## Slide 7: FS_enh_EC status after SA2#136AH (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  None identified.
Focus for the Next Meeting (SA2#138):
  Solution collection for all Key issues. No new key issue will be discussed.
  Initial evaluation on key issue #1.
Overall Plan:
  SA2#138 (Apr): Finish solution collection for all key issues. Start initial evaluation. New solutions should be proposed with all details, including impacts on existing NFs and services.
  SA2#139 (May): Aim to conclude most Key issues. Submit TR 23.748 to SA#88 plenary for approval. Agree a WID.

## Slide 8: FS_enh_EC status after SA2#139e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 40 > 60% | Sep, 20 | SP-190185
General
  FS_enh_EC TR 23.748 v0.4.0 is available at link.
Key issue 1 (Discovery of Edge Application Server)
  17 new solutions are agreed for this key issue, 7 existing solutions are revised. Totally 24 solutions for KI#1 in the TR.
  Next steps: Resolve ENs in solutions; Overall evaluation; Conclusion.
Key issue 2 (Edge relocation)
  19 solutions are agreed for this key issue.
  Next steps: Potentially new/merged/simplified solutions, resolve ENs in the solutions; Classify the solutions based on different aspects; Overall evaluation.
  Risk: The solutions are diverging, based on different assumptions (e.g. stateful/stateless application..) and focusing on different aspects (e.g. server rediscovery, packet lossless..). Classifying solutions based on problem spaces are needed for further conclusion.
Key issue 3 (Network Information Provisioning to Local Applications with low latency)
  9 solutions are agreed for this key issue.
  Next steps: Potentially new/merged/simplified solutions, resolve ENs in the solutions; Overall evaluation.
Key issue 5 (Activating the traffic routing towards Local Data Network per AF request)
  1 solution is agreed for this key issue.
  Next steps: Resolve ENs in the solution; Overall evaluation; Conclusion.

## Slide 9: FS_enh_EC status after SA2#139e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  None identified.
Focus for the Next Meeting (SA2#140e):
  No new solution will be discussed for KI#1 and KI#5.
  Last meeting to bring any new solutions for KI#2 and KI#3. New solution proposals should be reasonably complete.
  Resolving ENs of existing solutions.
  Overall evaluation and conclusion for KI#1 and KI#5.
Overall Plan:
  SA2#140e: Concluding KI#1 and KI#5. Sending TR to SA plenary for information.
  SA2#141e: All remaining works for completing SI. Agreeing to a WID.