## Slide 1: FS_eNPN and eNPN Status Report
Peter Hedman
Ericsson

## Slide 2: FS_eNPN status after SA2#143E (1/3)
General
  FS_eNPN is captured in TR 23.700-07 and v1.3.0 will be available here.
  Total TUs requested for Study Phase in 2020 is 5. 2 TUs and five e-meetings have been used.
  P-CR noted proposing general conclusion of SNPN support for other features e.g. 5MBS, i.e. assumed not part of eNPN work
Key Issue 1 (Enhancements to Support SNPN along with credentials owned by an entity separate from the SNPN):
  1 P-CR agreed updating a solution.
  4 P-CR agreed updating conclusions.
  P-CRs noted with proposed conclusion updates related to Credentials Holder with AAA
  P-CRs noted with proposed conclusion updates related to simultaneous connections for UEs with one subscription and mobility (related to a not handled SA1 LS reply in S1-210356)
  Next Steps: normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 90% > 100% | March, 21 | SP-200094

## Slide 3: FS_eNPN status after SA2#142E (2/3)
Key Issue 2 (NPN support for Video, Imaging and Audio for Professional Applications (VIAPA))
  4 P-CRs agreed updating conclusions.
  1 P-CR updating evaluation
  Next Steps: normative work
Key Issue 3 (Support of IMS voice and emergency services for SNPN)
  2 P-CRs agreed updating conclusions.
  Next Steps: normative work
Key Issue 4 (UE Onboarding and remote provisioning)
  LS sent to CT1 and SA3 on UE capabilities indication in UPU
  More discussions required for how to enable selection of UP provisioning vs CP provisioning (P-CRs noted), discussions related to above LS sent to CT1 and SA3
  P-CR agreed clarifying Onboarding SUCI used to determine DCS
  P-CR agreed clarifying CP provisioning is network-triggered, PDU session establishment for UP provisioning is UE-triggered
  P-CR agreed clarifying that Group ID (defined by KI#1) can be used for ON-SNPN network selection
  P-CRs agreed updating conclusions e.g. removing resolved ENs.
  P-CR noted related to ongoing SA3 discussions on one-way primary authentication
  P-CR noted proposing options on how AF can configure ON with Provisioning Server address
  Next Steps: normative work
  Progress of unresolved aspects with SA3 dependencies are dependent on SA3 feedback
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 90% > 100% | March, 21 | SP-200094

## Slide 4: FS_eNPN status after SA2#143E (3/3)
  RAN impacts and dependencies:
  As per agreed conclusions, key issues 1, 3 and 4 impacts RAN, key issue 2 may impact RAN4 (LS feedback outstanding)
  Impacts are SIB related for solutions related to Key issues 1, 3 and 4, new RRC indications for solutions related to Key issues 4 and additional NGAP impacts for solutions related to Key issue 4. For Key issue 2 impact may be related to UE performance requirements when UE 2Rx/2Tx capable.
SA3 dependencies
  SA3 dependencies identified for solutions and conclusions related to key issue 1, 3 and 4.
  LS sent to SA3 indicating that key issues in TR 33.857 are not complete with regards to Provisioning (S2-2009132)
Contentious Issue:
  KI#1: Whether AUSF or separate NF is to interact with AAA-S using non-SBI protocol
  KI#4: Selection of CP vs UP provisioning
Focus for the Next Meeting (SA2#144E):
  Progress normative work based on TR conclusions and feedback from other WGs
Overall Plan:
  Submit TR 23.700-07 to SA#90 plenary for approval.
  Agree an update of the WID based on the updated TR conclusions
Risks:
  Completion of the work dependent on progress in SA3 (KI#4)

## Slide 5: FS_eNPN Status at SA#91e
Progress since SA#90-e:
  Updated conclusions agreed for KI#1, KI#2, KI#3 and KI#4.
  LS exchanges with SA1, SA3, CT1 WGs
  RAN impacts and dependencies:
  RAN impacts identified by TR conclusions as follows:
    Impacts are SIB related for solutions related to Key issues 1, 3 and 4,
    New RRC indications during RRC establishment for solutions related to Key issues 4
    Additional NGAP impacts for solutions related to Key issue 4.
    Key issue 2 impact may be related to (RAN4) UE performance requirements when UE 2Rx/2Tx capable
Next steps:
  TR proposed to be sent for approval with cover sheet explaining aspects to be considered during normative phase
  An updated WID has been agreed based on the agreed updates to the TR conclusions for KI#3
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 90% > 100% | March, 21 | SP-200094

## Slide 6: eNPN Status at SA#91e
Progress since SA#90-e:
  WID update agreed as per agreed updates to the TR 23.700-07 conclusions for KI#3
  LS reply to RAN2 agreed answering some of the questions asked by RAN2 for the eNPN feature
  LS sent to CT1 and SA3 whether to use UPU or SoR for updating the Separate Entity controlled lists for SNPN selection
  4 CRs agreed to TS 23.501 related to KI#1
  2 CRs agreed to TS 23.501 related to KI#2
  1 CR agreed to TS 23.501, 2 CRs agreed to TS 23.503 related to KI#3
  RAN impacts and dependencies:
  RAN impacts as per agreed CRs:
    Impacts are SIB related for CRs addressing KI#1
  TBD whether eCall and PWS is to be enabled for SNPNs
Next steps:
  Progress CRs for the uncovered functionality
  Progress CRs as per the feedback from other WGs e.g. SA3 on UE Onboarding
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 0% > 20% | June, 21 | SP-200980