## Slide 1: SA WG2 Status report for ID_UAS
Stefano Faccin
Qualcomm

## Slide 2: ID_UAS status after SA2#144E (1/2)
General
  ID_UAS is captured in TS 23.256.
  18 CRs were approved
  It was concluded to proceed with an API-based solution for UUAA procedures specific for UAV UE (not generic to all UEs). The solution will be captured solely in TS 23.256 with no impacts on TS 23.501 and TS 23.502.
WI Code | Work Item Title | WP | Target Date | WID#
ID_UAS | Support of Unmanned Aerial Systems Connectivity, Identification, and Tracking | 15% > 45% | June 2021 | SP-200979

## Slide 3: ID_UAS status after SA2#144E (2/2)
  RAN impacts and dependencies:
  None
SA3 dependencies
  An EN has been added in S2-2103482 that the UUAA procedure will be revisited after security aspects are determined by SA3.
Contentious Issue:
  The exact UAS NF interfaces to other NFs is still being discussed.
  Some aspects concluded in the TR are still being challenged and require further discussion.
Focus for the Next Meeting (SA2#144E):
  Progress and complete normative work
Overall Plan:
  Complete the normative work at SA2#145e and submit T2 23.256 to SA#92-e plenary for approval.
Risks:
  If basic TR conclusions are being challenged, there is a risk of inability to complete the WID.

## Slide 4: ID_UAS status after SA2#143E (1/2)
General
  ID_UAS is captured in TS 23.256.
WI Code | Work Item Title | WP | Target Date | WID#
ID_UAS | Support of Unmanned Aerial Systems Connectivity, Identification, and Tracking | 0% > 15% | June 2021 | SP-200979

## Slide 5: ID_UAS status after SA2#143E (2/2)
  RAN impacts and dependencies:
  None
SA3 dependencies
  Discussion on expanding the applicability of EAP-based UAV authentication to be applicable beyond UAV, i.e. a generic API-based solution for authentication, may require SA3 feedback.
Contentious Issue:
  The conclusion from the TR whether to use a UUAA procedure based on API, instead of an EAP-based procedure, was challenged in SA2#143E and related papers could not be approved. Note that the conclusion was driven by an LS from the aviation community indicating no interest in EAP-based solutions.
Focus for the Next Meeting (SA2#144E):
  Progress normative work
Overall Plan:
  Submit T2 23.256 to SA#92-e plenary for approval.
Risks:
  If basic TR conclusions are being challenged, there is a risk of inability to complete the WID.