## Slide 1: eEdge_5GC Status Report
Hui Ni
Huawei

## Slide 2: eEdge_5GC status after SA2#144e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | 35%-> 60% | Jun, 2021 | SP-201107
General
  TS 23.548 v0.2.0 is available at link.
  26 pCRs for TS 23.548 and 14 CRs for TS 23.501/23.502/23.503 are approved.
  General aspects for EC in both 23.501 and 23.548 are updated/addressed.
Topic 1: (Re-)Discovery of Edge Application Server
  pCRs/CRs for the following solutions are approved:
    New: EASDF discovery and selection, EASDF functional description, EASDF services, EAS deployment information from AF; EAS Re-discovery Procedure at Edge Relocation, EAS Discovery with dynamic PSA Distribution(sol#12).
    Update: EAS discovery procedure for session breakout, EAS rediscovery for session breakout, UE Considerations for EAS (re)Discovery, AF guidance to PCF determination of proper URSP rules.
Topic 2: Edge Relocation
  pCRs/CRs for the following solutions are approved:
    New: General part for Edge relocation, Edge Relocation with Multiple AFs, EAS Relocation on Simultaneous connectivity over source and target PSA .
    Update: Target PSA buffering, Edge Relocation considering User Plane latency, EAS IP replacement.
    Topic 3: Network Exposure to Edge Application Server
  pCRs/CRs for the following solutions are approved:
    Update: Network exposure via local NEF, local NEF selection.
Topic 4: Support of 3GPP Application Layer Architecture
  pCR/CRs for updating ECS Address Provisioning are approved.

## Slide 3: eEdge_5GC status after SA2#144e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  Issues related to “whether/how to guarantee that the UE uses the EASDF's IP address”.
  Issue related to “whether specify Local UPF-Local NEF interface”.
Focus for the Next Meeting (SA2#145e):
  Continue to discuss the postponed solutions.
  Resolve the open issues.
Overall Plan:
  Achieve 80% completion after SA2 #145e.
  Send TS 23.548 to SA#92-e for information/approval after SA2 #145e.
Risk:
  Depending on the progress on contentious issues, there may be a risk that the TS cannot be ready for approval before SA #92-e.

## Slide 4: backup

## Slide 5
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 70% -> 100% | Dec, 20 | SP-200093
Progress since SA#89E:
  40 approved P-CRs on solution update, evaluation/conclusion of key issues.
  All Key issues prioritized in Rel-17 have been concluded, including:
    Key Issue #1: Discovery of Edge Application Server
    Key Issue #2: Edge relocation
    Key Issue #3: Network Information Provisioning to Local Applications with low latency
    Key Issue #5: Activating the traffic routing towards Local Data Network per AF request
  2 LS replies from SA3 and SA6 were handled.
  The TR 23.748 and corresponding WID are sent to SA plenary for approval.
RAN impacts and dependencies:
  None identified
Next steps:
  Start normative work in 2021 Q1 according to WID.
FS_enh_EC status for SA #90E

## Slide 6: FS_enh_EC status after SA2#142e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 85%(#141E) -> 100% | Dec, 2020 | SP-190185
General
  FS_enh_EC TR 23.748 is available at link.
  26 pCRs are approved on SA2#142e meeting.
Key issue 1 (Discovery of Edge Application Server)
  3 existing solutions are revised. Existing conclusions are refined.
  The key issue is concluded.
  Detailed interaction between LDNSR and SMF is left to normative phase.
Key issue 2 (Edge relocation)
  6 existing solutions are revised. New conclusions on specific solutions are approved.
  The key issue is concluded.
Key issue 3 (Network Information Provisioning to Local Applications with low latency)
  1 conclusion proposal is approved.
  The key issue is concluded.
Key issue 5 (Activating the traffic routing towards Local Data Network per AF request)
  The KI has been concluded in SA2 #141E. No new progress.

## Slide 7: FS_enh_EC status after SA2#142e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#143e):
  Starting normative phase after WID is approved.
Overall Plan:
  SA2#143e: Starting normative phase after WID is approved.