## Slide 1: FS_5MBS_Ph2 Status Report
Li, Meng
Huawei

## Slide 2: FS_5MBS status after SA2#150E (1/2)
General
  TR 23.700-47 v0.2.0 is available.
  Total TUs requested for Study Phase is 7.5, 2 TUs used after 150E and 5.5 TUs remaining.
  Added new Key Issue #6 (Improvement for potential performance issues related to high numbers of public safety UEs)
Architectural requirement
  The architectural requirement was updated and included public safety requirement.
Key Issue 1 (RRC Inactive for Multicast)
  Four new solutions were included in the TR and one solution was updated.
  Next step: in SA2#151E finalize description for solutions with strong support. Potential proceeding with solution evaluation and interim conclusion.
Key Issue 2 (MOCN for broadcast)
  Three solutions were captured and two updates were agreed.
  Next step: in SA2#151E finalize description for solutions with strong support. Potential proceeding with solution evaluation and interim conclusion.
Key Issues 3 (AF triggered MBS session management)
  Two solutions were captured.
  Next step: in SA2#151E discuss and capture solutions.
Key Issue 4 (Group message delivery)
  Two solutions captured.
  Next step: in SA2#151E discuss and capture solutions.
Key Issues 5 (Power Saving mechanisms)
  Two solutions captured.
  Next step: in SA2#151E discuss and capture solutions
Key Issues 6 (Public safety)
  Two solutions captured.
  Next step: in SA2#151E discuss and capture solutions
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 15%  35% | Sept., 2022 | SP-211645
To be updated

## Slide 3: FS_5MBS status after SA2#150E (2/2)
  RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#150):
  Finalize description for already captured solutions with strong support.
  Capture new solutions with strong support.
  List identified RAN dependencies and send liaisons to relevant RAN WGs if needed.
To be updated

## Slide 4: FS_5MBS_Ph2 Status after SA#95-e
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 15%  35% | Sept., 2022 | SP-211645
  Progress since SA#95-e:
  1 KI is agreed, and architectural requirement is updated.
  1 LS is sent to RAN WGs.
  15 new solutions and 3 solution updates are agreed.
  RAN impacts and dependencies:
  3 KIs have RAN WGs coordination requirement as per agreed pCR.
Other WG dependencies
  KIs have potential SA6/SA4/SA3 coordination requirements accordingly as per agreed pCR.
Contentious Issue:
  None.
Next steps in SA2#151E:
  Finalize description for already captured solutions with strong support.
  Capture new solutions with strong support.
  List identified RAN dependencies and send liaisons to relevant RAN WGs if needed.
To be updated

## Slide 5: Annex

## Slide 6: Work Plan
Overall Plan: (study phase)
  SA2#149e, Feb (1TU): Focus on KIs, solutions are allowed. Agree the skeleton/scope/architectural assumption.
  SA2#150e, Apr (1TU): Focus on Solutions and complete all KIs. Potential updates/new KIs. Last meeting for KI proposal/modification.
  SA2#151e, May (2TUs): Solutions
  SA2#152, Aug (2TUs): Solutions, evaluations, conclusions
  SA2#153, Oct (1TU): evaluations, conclusions
    Approval of MBS_Ph2 WID
  SA2#154, Nov (0.5 TU): final conclusions
    Adjustment/issues depends on RAN progress
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 12