## Slide 1: FS_5TRS_URLLC Status Report
Devaki Chandramouli (Rapporteur)
Nokia

## Slide 2: FS_5TRS_URLLC status at SA#96E
General
  17 P-CRs agreed.
  5 solutions agreed for KI#1
  2 solutions agreed for KI#2
  1 solution agreed for KI#4
  3 solutions agreed for KI#5
  5 solutions agreed for KI#6
RAN dependencies:
  S2-2201767 - LS out sent to RAN2 (with RAN1, RAN3 in CC) to obtain feedback related to problem statements for one of the KI “LS on RAN feedback for low latency”.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5TRS_URLLC | Study on 5G Timing Resiliency and TSC & URLLC enhancements | 25%-50% | Sep’ 22 | SP-211634
DRAFT
Notes: S2-2201767

## Slide 3: FS_5TRS_URLLC status after SA2#150E
  RAN and SA3 impacts and dependencies:
  LS response pending for KI#6
Contentious Issue:
  Varying interpretation of KI#3 exists
Focus for the Next Meeting (SA2#151E):
  Reach consensus for KI#3 scope and prioritize solutions for KI#3.
  Update solutions and resolve open issues.
Overall Plan:
  No new key issues or KI update expected after SA2#151E.
  Recommended: no new solutions after SA2#151E.
  Strive to reach conclusion for KI#4, KI#2 during SA2#151E.
  Strive to reach conclusion for KI#1, KI#3, KI#5 during SA2#152E
  Strive to reach KI#6 conclusion immediately after receiving RAN2 response.
Risks:
  KI#6 conclusion could be delayed to Q4 due to RAN dependency.
  KI#3 is at a mild risk due to lack of consensus with the scope at this time.
DRAFT