## Slide 1: WI Status Report: Study on Vehicle Mounted Relays (FS_VMR)
Qualcomm Incorporated
S2-2206986

## Slide 2: FS_VMR status after SA2#152E (1/2)
General
  TR 23.700-05 v.0.4.0 was created based on approved contributions.
  7 key issues, 20 solutions documented in the TR.
  0.5 TU used for SA2#152E (2 TU used in total) and 0.75 TU left for the Study Phase.
7 Key Issues agreed for the study:
20 candidate solutions documented in TR 23.700-05:
  5 new solution added in SA2#152e
  Evaluation and conclusions
    Initial evaluation of the solutions and dependencies on other WGs were documented
    Interim conclusions for KI#1, KI#4, KI#5, and KI#6 were documented.
  RAN impacts and dependencies:
  RAN impacts were documented in evaluations.
  LS (S2-2207070) was sent to RAN2 and RAN3 for feedbacks on solutions and assumptions.
Other WG dependencies
  Charging support is expected to be handled by SA5, and alignment work in SA2 may be required
  Potential security impacts is expected to be handled by SA3
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 55% > 80% | Nov, 22 | SP-211636

## Slide 3: FS_VMR status after SA2#152E (2/2)
Contentious Issue:
  None.
Focus of the Next Meeting (SA2#153E):
  Solution updates and evaluations.
  Conclusions update.
  WID approval.
Overall work Plan:
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (New KIs; solutions)
  SA2#151 May’22: 0.5 (Last chance for KIs; last chance for new solutions; solution updates)
  SA2#152 Aug’22: 0.5 (Solution updates; evaluations; Interim conclusions, send TR to RAN for comments)
  SA2#153 Oct’22: 0.5 (Finalize conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (Resolve RAN dependent open issues for selected solutions); start normative work.
  SA2#154AH Jan’23: 0.5 (Normative work)
  SA2#155 Feb’23: 1 (Normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 (0.25+0.75) | 0.5 | 1 | 5

## Slide 4: FS_VMR status at SA#97
Progress since SA#96:
  5 new solutions agreed
  Solution evaluation and interim conclusions for KI#1, KI#4, KI#5, and KI#6 agreed.
  TR 23.700-05 v0.4.0 generated based on the agreed contributions
RAN impacts and dependencies:
  1 LS (S2-2207070) was sent to RAN2 and RAN3 for feedbacks on solutions and assumptions.
Next steps:
  Continue the study on solution evaluation and conclusions
  WID approval
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 55% > 80% | Nov, 22 | SP-211636