## Slide 1: WI Status Report: Study on Vehicle Mounted Relays (FS_VMR)
Qualcomm Incorporated
S2-2209231

## Slide 2: FS_VMR status after SA2#153E (1/2)
General
  TR 23.700-05 v.1.1.0 was created based on approved contributions.
  0.5 TU used for SA2#153E (2.5 TU used in total) and 0.25 TU left for the Study Phase.
  13 contributes agreed with updates to solutions, evaluations and conclusions.
7 Key Issues agreed for the study:
20 candidate solutions documented in TR 23.700-05:
  Evaluation and conclusions
    All 7 key issues have initial conclusions
    Some normative phase work have been identified for the key issues
  RAN impacts and dependencies:
  RAN impacts were documented in evaluations, and final conclusions depends on RAN WG response to LS (S2-2207070).
Other WG dependencies
  Charging support is expected to be handled by SA5, and alignment work in SA2 may be required
  Potential security impacts is expected to be handled by SA3
WID approval postponed to SA2#154 (S2-2209070)
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 80% > 90% | Nov, 22 | SP-211636

## Slide 3: FS_VMR status after SA2#153E (2/2)
Contentious Issue:
  None.
Focus of the Next Meeting (SA2#154):
  Conclusions update.
  TR sent to SA for Approval.
  WID approval.
  Normative work based on the objectives of the WID.
Overall work Plan:
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (New KIs; solutions)
  SA2#151 May’22: 0.5 (Last chance for KIs; last chance for new solutions; solution updates)
  SA2#152 Aug’22: 0.5 (Solution updates; evaluations; Interim conclusions, send TR to RAN for comments)
  SA2#153 Oct’22: 0.5 (Finalize conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (Resolve RAN dependent open issues for selected solutions); start normative work 0.75.
  SA2#154AH Jan’23: 0.5 (Normative work)
  SA2#155 Feb’23: 1 (Normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 (0.25+0.75) | 0.5 | 1 | 5

## Slide 4: FS_VMR status at SA#98
Progress since SA#97:
  TR 23.700-05 v1.1.0 generated based on the agreed contributions
  Initial occlusions for all key issues.
  WID draft based on conclusions in S2-2209070
RAN impacts and dependencies:
  1 LS (S2-2207070) was sent to RAN2 and RAN3 for feedbacks on solutions and assumptions.
Next steps:
  WID approval
  Normative work for WID: VMR_ARCH
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 80% > 90% | Nov, 22 | SP-211636