## Slide 1: FS_EDGE_Ph2 status report
Patrice Hédé
Huawei Technologies

## Slide 2: EDGE Ph2 status after SA2#153E
  Progress since SA2#152-e:
  Total TUs requested for Study phase in 2022 is 7,25, 7 TUs used until SA2#153E and 0,25 TUs remaining.
  17 contributions approved:
    1 LS and 1 editorial clean-up contribution
    6 solution updates
    9 evaluation and conclusions (new or update)
  6 KIs (out of 7) have received conclusions:
    5 KIs have received a complete conclusion
    1 KI has a minor EN to resolve (KI#1/HR)
    1 KI has not yet concluded (KI#6)
  RAN impacts and dependencies:
  None
Next steps in SA2#154e:
  Remove the remaining ENs in conclusions
  Resolve KI#6 conclusion
  Start normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 83% → 97% | Dec 2022 | SP-220352

## Slide 3: EDGE Ph2 status after SA2#153E — work plan
Study phase
  SA2#149e, Feb (1TU): Agreement on scenarios/use cases and assumptions for all KIs
  SA2#150e, Apr (1TU): Updates to KI definition. Solutions
  SA2#151e, May (2TU): Solutions
  SA2#152e, Aug (2TU): Solutions, evaluations, conclusions
    Approval of first version of Edge ph2 WID based on first conclusions, TR sent for information
  SA2#153e, Oct (1TU): evaluations, conclusions
    Completion of conclusions, Edge ph2 WID based on remaining conclusions
  SA2#154e, Nov (0,25 TU): final conclusions
    TR sent for approval, Edge ph2 WID based on final conclusions if needed
 |  |  |  | Feb. 22 | Apr. 22 | May 22 | Aug. 22 | Oct. 22 | Nov. 22 | Jan. 23 | Feb. 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_EDGE_Ph2 | 7,25 | 4,25 | 11,5 | 1 | 1 | 2 | 2 | 1 | 0,25/0,75 | 1,5 | 2 | 11,5