## Slide 1: Status Report: Study on generic group management, exposure and communication enhancements
<Qianghua Zhu>
<Primary Rapporteur, Huawei>
<Sang-Jun Moon>
<Secondary Rapporteur, Samsung>

## Slide 2: FS_GMEC Status after SA2#153E
General
  FS_GMEC TR 23.700-74 v1.1.0 will be available after SA2#153E meeting, this includes TR skeleton, TR scope, Architecture Assumptions and Requirements, definitions of terms and abbreviations, 5 key issues, 22 solutions, evaluations and conclusion for KI#1, KI#2, KI#3 and KI #5.
Updates at SA2#152E, 6 PCRs are agreed in total
  2 PCR for conclusions update for Key Issue #1: Enhance group attribute management
  0 PCR for conclusions update for Key Issue #2: Enhance group status event reporting
  3 PCR for conclusions update for Key Issue #3: NEF exposure framework for provisioning of traffic characteristics and monitoring of performance characteristics
  0 PCRs for Key Issue #4: Multiple SMFs for VN group communication
  1 PCR for conclusions update for Key Issue #5: Allowing UE to simultaneously send data to different groups with different QoS policy
WI Code | Work Item Title | WP | Target Date | WID#
FS_GMEC | Study on generic group management, exposure and communication enhancements | 95% | Sept. 2022 | SP-211603

## Slide 3: FS_GMEC Status at SA#98
Progress since SA#97:
  Agree: 6 PCR agreed for KI#1/#2/#3/#5 conclusions
RAN impacts and dependencies
  no
Contentious Issue
  Evaluations and conclusion for KI#4: Multiple SMFs for VN group communication, in particular for dynamic control of the connectivity between UPFs controlled by different SMF Sets
Outstanding Issue
  no
Next Steps:
  Complete conclusion/evaluations for KI#4
WI Code | Work Item Title | WP | Target Date | WID#
FS_GMEC | Study on generic group management, exposure and communication enhancements | 95% | Sept. 2022 | SP-211603

## Slide 4: GMEC Status after SA2#153E
General
  2 CRs are agreed in total, those CRs target for “Enhance group status event reporting”, one for TS23.501, one for TS23.502
WI Code | Work Item Title | WP | Target Date | WID#
GMEC | Generic group management, exposure and communication enhancements | 15% | Mar 2023 | SP-220959

## Slide 5: GMEC Status at SA#98
Progress since SA#97:
  2 CRs are agreed in total, those CRs target for “Enhance group status event reporting”, one for TS23.501, one for TS23.502
RAN impacts and dependencies
  no
Contentious Issue
  no
Outstanding Issue
  no
Next Steps:
  WID revision, Continue normative work for other WID objectives
WI Code | Work Item Title | WP | Target Date | WID#
GMEC | Generic group management, exposure and communication enhancements | 15% | Mar 2023 | SP-220959

## Slide 6: Work Planning for FS_GMEC/GMEC
SA2#149-E, 1 TU assigned: (TR skeleton, TR scope, assumptions, terms, key issues, some solutions)
SA2#150-E, 1 TU assigned: (key issue updates, solutions, last meeting for new KIs)
SA2#151-E, 1 TU assigned: (solution updates, initial evaluations and conclusions, last meeting for new solution)
SA2#152-E, 1 TU assigned: (solution updates, finial evaluations and conclusions, send TR for approval, WID approval)
SA2#153-E, 0.5 TU assigned: (normative work for KI#2, #5; WID revision; continue conclusion/evaluations for KI#1, #3, #4, #5)
SA2#154-E, 0 TU assigned: (WID revision)
SA2#154-E AH, 0.75 TU assigned: (normative work, WID revision, continue conclusion/evaluations for KI#4)
SA2#155-E, 0.5 TU assigned: (normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.75 | 0.5