## Slide 1: FS_eNA_Ph3 Status Report
Aihua Li (China Mobile), Xiaobo Wu (vivo)

## Slide 2: FS_eNA_Ph3 status after SA2#153E (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_Ph3 | Study on Enablers for Network Automation for 5G - phase 3 | 75% -> 88% | September 2022 | SP-211650
General
  44 contributions are agreed (including 19 solution updates, 2 LS out and 23 Evaluation and Conclusion updates).
  16 contributions are merged and 2 contributions are noted.
  5 contributions not handled due to exceeding the quota.
  Total TUs requested for Study Phase is 9 TUs, and 1 TUs are remaining.
KI#1: How to improve correctness of NWDAF analytics:
    4 solution updates are approved, 4 Evaluation updates and 3 Conclusion updates are merged, 1 Evaluation updates and 1 Conclusion updates is approved.
    Next steps: updates based on feedback from LS to SA3 and start normative work.
    KI#2: NWDAF-assisted application detection:
    2 solution updates and 1 LS OUT to SA3 is approved, 1 Conclusion updates is merged, 1 Evaluation updates and 1 Conclusion updates is approved.
    Next steps: finalize the conclusion and start normative work.
    KI#3: Data and analytics exchange in roaming case:
    4 solution updates are approved, 3 Conclusion updates are merged, 1 Evaluation updates and 1 Conclusion updates is approved.
    Next steps: finalize the conclusion and start normative work.

## Slide 3: FS_eNA_Ph3 status after SA2#153E (2/3)
    KI#4: How to Enhance Data collection and Storage:
    1 solution updates is approved, 1 Evaluation updates and 2 Conclusion updates are approved, 1 Conclusion updates is noted.
    Next steps: finalize the conclusion and start normative work.
    KI#5: Enhance trained ML Model sharing:
    1 solution updates is approved, 1 Conclusion updates is approved.
    Next steps: finalize the conclusion and start normative work.
    KI#6: NWDAF-assisted URSP:
    1 solution updates is approved, 3 Conclusion and Evaluation updates are approved.
    Next steps: address one Editor´s Note and start normative work.
    KI#7: Enhancements on QoS Sustainability analytics:
    1 solution updates is approved, 1 Evaluation updates and 1 Conclusion updates is approved.
    Next steps: finalize the conclusion and start normative work.
    KI#8: Supporting Federated Learning in 5GC:
    2 solution updates are approved, 2 Conclusion updates are merged, 1 Evaluation updates and 2 Conclusion updates are approved.
    Next steps: finalize the conclusion and start normative work.
    KI#9: Enhancement of NWDAF with finer granularity of location information:
    3 solution updates and 1 LS OUT to SA5 is approved, 2 Evaluation updates and 1 Conclusion updates is merged, 1 Evaluation updates and 2 Conclusion updates are approved.
    Next steps: finalize the conclusion and start normative work.
    KI#10: Interactions with MDAS/MDAF:
    1 solution updates is noted, 1 Evaluation updates and 1 Conclusion updates is approved.
    Next steps: start normative work.

## Slide 4: FS_eNA_Ph3 status after SA2#153E (3/3)
  RAN impacts and dependencies:
  No RAN impact.
Contentious Issue:
  A LS is sent to SA3, requesting SA3 to provide feedback about the user consent checking for the NWDAF-assisted application detection by 5GC NWDAF (e.g. whether and which type of user consent is needed).
  A LS is sent to SA5, requesting SA5 to confirm if OAM can provide per UE level speed and orientation to NWDAF as defined in Table 6.27.1-1 (Information collected from OAM) TR 23.700-81 proposed as input data for proximity analytics.
Focus for the Next Meeting (SA2#154E):
  Finalize the conclusion and start normative work.
  Approve the WID.
    Risk:
  None.

## Slide 5
Backup Slide for FS_eNA_Ph3 Study Phase Work Plan
#149 meeting: focus on TR skeleton, scope, assumptions and KIs, no solution will be discussed;
#150 meeting: solutions discussions, and KIs. Finalize the KIs (Last chance for new KI proposal);
#151 meeting: continue the solution discussions and capture new solutions;
#152 meeting: solution updates/merging and last chance for new solution(s) (1 supporting companies required) and start to evaluate/conclude solution(s) and send TR for information;
#153 meeting: continue the evalutaion&conclusion, disusss the WID proposal.
#154 meeting: finalize the conclusion and approve the WID for 1 TU, and start normative work;
#154AH and #155 meeting: finalize normative work.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_eNA_Ph3 | 9 | 5 | 14 | 1 | 1 | 2 | 2 | 2 | 1+1 | 2 | 2 | 14