## Slide 1: FS_eNPN_Ph2 + eNPN_Ph2 Status Report
Peter Hedman
Ericsson (Rapporteur)

## Slide 2: FS_eNPN_Ph2 status after SA2#153E (1/3)
General
  14 P-CRs to TR 23.700-08 agreed
  1 LS out sent to SA1, SA3, CT1 on “Progress and open issues for NPN enhancements in Rel-18” related to KI#2 and KI#4
  KI#2 conclusions updated, one open issue that is dependent on SA3 remaining in conclusion.
  KI#3 evaluations updated, and conclusions agreed
  KI#4 evaluations updated, and conclusions agreed, but multiple open issues remains
  KI#5 evaluations updated, and conclusions agreed
  KI#6 evaluations updated, and conclusions agreed
  2 solutions updated; the TR includes still 47 solutions
  Latest TR 23.700-08 is available here.
  Total TUs requested for Study Phase is 5.5 TUs, and 0 TU is remaining from the original plan
Related to Key Issue 1: Enabling support for idle and connected mode mobility between SNPNs without new network selection
  No tdocs, normative work
Related to Key Issue 2: Support of Non-3GPP access for SNPN
  2 P-CR updating conclusions agreed.
  One open issue that is dependent on SA3 remaining in conclusion
  Next Steps:
    Finalize normative work, wait for SA3 on the open issue
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN_Ph2 | Enhanced support of Non-Public Networks | 75% > 90% | Sept, 22 | SP-211656

## Slide 3: FS_eNPN_Ph2 status after SA2#153E (2/3)
Related to Key Issue 3: Enabling NPN as hosting network for providing access to localized services
  1 P-CR updating evaluation agreed
  2 P-CRs updating conclusions agreed
  No open issue remains in conclusion
  Next Steps:
    Study assumed done for the key issue
Related to Key Issue 4: Enabling UE to discover, select and access NPN as hosting network and receive localized services
  2 P-CRs updating solutions agreed
  1 P-CR updating evaluation agreed
  1 P-CR updating conclusions agreed
  Multiple open issues remains in conclusion
  Next Steps:
    Finalize the work i.e. focus on resolving open issues in conclusion
Related to Key Issue 5: Enabling access to localized services via a specific hosting network
  1 P-CR updating evaluation agreed
  2 P-CRs updating conclusions agreed
  No open issue remains in conclusion
  Next Steps:
    Study assumed done for the key issue
Related to Key Issue 6: Support for returning to home network
  1 P-CR updating evaluation agreed
  2 P-CRs updating conclusions agreed
  No open issue remains in conclusion
  Next Steps:
    Study assumed done for the key issue

## Slide 4: FS_eNPN_Ph2 status after SA2#153E (3/3)
  RAN impacts and dependencies:
  Potential RAN impacts or dependencies identified for Key Issue 1, 2 and 4.
WG dependencies
  SA3 dependencies related to key issue 2, 3, 4, 5
  SA5 dependencies related to key issue 3 and 5
Contentious Issue:
  none
Focus for the Next Meeting (SA2#154E):
  Finalize the study, focus on open issues for KI#4
  Update of normative WID based on conclusions
Overall Plan:
  SA2#149-E, 1 TU assigned, TR Skeleton, TR Scope, Architectural Assumption, Key Issues, allow solutions for KIs related to WT#1 and WT#2.
  SA2#150-E, 1 TU assigned, last e-meeting for any new Key Issue, solutions for all Key Issues/WTs
  SA2#151-E, 1,5 TU assigned, The last e-meeting for any new solution related to KI#1 and KI#2.
  SA2#152-E, 1 TU assigned, last e-meeting for any new solution related to KI#3-6, solution evaluation and conclusion, normative WID creation.
  SA2#153-E, 1 TU assigned, solution evaluation and conclusion, update of normative WID if needed, TR for approval
  SA2#154, use TU planned for normative work to finalize the study, update normative WID, TR for approval, No normative work scheduled.
  SA2#154AH, SA2#155, normative work
Risks:
  Some aspects dependent on SA3 progress

## Slide 5: FS_eNPN_Ph2 and eNPN_Ph2 Status at SA#98e
Progress since SA#97-e of FS_eNPN_Ph2:
  14 P-CRs agreed
  1 LS out sent to SA1, SA3, CT1 on “Progress and open issues for NPN enhancements in Rel-18” related to KI#2 and KI#4
  2 solutions updated; the TR includes still 47 solutions
  KI#2 conclusions updated, one open issue that is dependent on SA3 remaining in conclusion
  KI#3-6 evaluations updated, and conclusions agreed, multiple open issues remains for KI#4
  TR sent for approval, normative WID updated as per TR conclusions
  RAN impacts and dependencies:
  No new RAN impact identified (key issues 1, 2 and 4 have potential RAN impact)
Next steps:
  Finalize the study and continue normative work
Progress of eNPN_Ph2:
  2 CRs approved related to KI#1
  4 CRs approved related to KI#2
  1 question related to SNPN access mode for non-3GPP access (KI#2) sent to CT1 in LS “Progress and open issues for NPN enhancements in Rel-18” that may impact approved CRs related to KI#2
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN_Ph2 | Enhanced support of Non-Public Networks | 75% > 90% | Sept, 22 | SP-211656
eNPN_Ph2 | Enhanced support of Non-Public Networks | 0% > 25% | Mar, 23 | SP-220805
DRAFT, content to be updated after SA2#154e