## Slide 1: FS_eUEPO Status Report
Intel (Rapporteur)

## Slide 2: FS_eUEPO status at SA2#153E
WI Code | Work Item Title | WP | Target Date | WID#
FS_eUEPO | Study on enhancement of 5G UE Policy | 80% -> 95% | Dec. 2022 | SP-220416
General
  The latest TR 23.700-85 v1.1.0 is generated by incorporating approved contributions at SA2 #153E. TR approval was postponed to SA2#154.
  Total TUs requested for Study Phase is 4.25 TUs, and 0 TUs are left.
  KI#1, KI#3 and #4 are completely concluded, KI#2 is partially concluded.
  28 papers were submitted including 4 LS OUT, 12 papers were approved, 0 papers were not handled.
KI#1(URSP in VPLMN):
  1 existing solution is updated, 4 evaluation and conclusion papers are approved.
KI#2(5GC awareness of URSP enforcement):
  1 existing solution is updated, 1 conclusion paper was approved, 1 LS to SA3 is approved.
KI#3(Provision consistent URSP to UE across 5GS and EPS):
  1 evaluation and conclusion paper resolving the EN is approved.
KI#4(Support standardized and operator-specific traffic categories in URSP):
  1 evaluation and conclusion update paper is approved, 1 LS to GSMA and 1 LS to CT1 are approved.

## Slide 3: FS_eUEPO status at SA2#153E (2/2)
Contentious Issue:
  KI #2 conclusion on solution based on UE reporting assistance information during PDU Session Establishment/Modification to 5GC.
Focus for the Next Meeting (SA2#154):
  Approve updated WID based on outcome of SA2#153E.
  TR sent to TSG SA for approval.

## Slide 4: Rel-18 FS_eUEPO Overall Work Plan
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
  Overall Work Plan
  SA2#149e, 0.5 TU assigned, 15 documents in maximum:
    TR Skeleton, TR Scope, Architectural Assumption, Key Issues.
  SA2#150e, 1 TU assigned, 30 documents in maximum:
    Key issue update and new solutions. Last e-meeting for new Key Issue.
  SA2#151e, 1 TU assigned, 30 documents in maximum:
    Stabilize solution. Last e-meeting for new solution. Potential TR for information.
  SA2#152(e), 1 TU assigned, 30 documents in maximum:
    Stabilize solution and conclusion, TR for information and potential TR for approval, potential WID discussion and approval.
  SA2#153(e), 0.75 TU assigned, 23 documents in maximum:
    Potential update on solution and conclusions, WID approval and update.
*The Work Plan will be updated and reflected in status report after each meeting.
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0 | 0.75 | 0.75 | 5.75