## Slide 1: FS_REDCAP_Ph2, NR_REDCAP_Ph2 Status Report
Qian Chen
Ericsson

## Slide 2: FS_REDCAP_Ph2, NR_REDCAP_Ph2 status after SA2#153E (1/2)
  General:
  Total 4 papers are agreed, including:
    2 normative CRs (S2-2209583/S2-2209675)
    1 CR for the completion of TR 23.700-68 conclusion (S2-2208654)
    1 LS to RAN2/RAN3 for further coordination on the normative work (S2-2209958)
  Study/TR 23.700-68 is complete.
  Total TUs planed for normative work is 1 TU. 0.5 TU is used and 0.5 TU is remaining
  RAN impacts and dependencies:
  Further response from RAN WGs on the questions listed in the LS
  Contentious Issue:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_REDCAP_Ph2 | Study on RedCap phase 2 | 98% -> 100 % | September, 22 | SP-220074
NR_REDCAP_Ph2 | 5GS support of NR RedCap UE with long eDRX for RRC_INACTIVE State | 0%->60% | March, 23 | SP-220803

## Slide 3: FS_REDCAP_Ph2, NR_REDCAP_Ph2 status after SA2#153E (2/2)
Focus for the Next Meeting (SA2#155E):
  Continue to work on remaining issues (e.g. as indicated in the ENs), considering the responses from RAN WGs
Overall Plan:
  100% progress on the study.
    SA2#149E Feb(0.5 TU): TR skeleton; Agreement on scope, architecture assumptions and requirements, key issues; solution proposals
    SA2#150E Apr(0.5 TU): Solution proposals/updates; initial evaluation
    SA2#151E May(0.5 TU): Evaluations; solution update; initial conclusion; TR for information
    SA2#152E Aug(0.5 TU): Evaluations; conclusions; WID approval; TR for approval
  60% progress on the normative work. Continue the study based on following overall time plan
    SA2#153E Oct(0.5 TU): Start of the normative work
    SA2#155 Feb (0.5 TU): Solving remaining issues

## Slide 4
Progress since SA#97
  Total 4 papers are agreed, including:
    2 normative CRs (S2-2209583/S2-2209675)
    1 CR for the completion of TR 23.700-68 conclusion (S2-2208654)
    1 LS to RAN2/RAN3 for further coordination on the normative work (S2-2209958)
  Study/TR 23.700-68 is complete.
  Total TUs planed for normative work is 1 TU. 0.5 TU is used and 0.5 TU is remaining.
  RAN impacts and dependencies:
  Normative work needs further coordination with RAN WGs.
  Next steps:
  Continue to work on remaining issues (e.g. as indicated in the ENs), considering the responses from RAN WGs
FS_REDCAP_Ph2, NR_REDCAP_Ph2 status at SA#98
WI Code | Work Item Title | WP | Target Date | WID#
FS_REDCAP_Ph2 | Study on RedCap phase 2 | 98% -> 100 % | September, 22 | SP-220074
NR_REDCAP_Ph2 | 5GS support of NR RedCap UE with long eDRX for RRC_INACTIVE State | 0%->60% | March, 23 | SP-220803