## Slide 1: SA2 Work Planning
Puneet Jain
SA2 Chair
SA WG2 Meeting #153E (e-meeting) S2-220xxxx
Oct 10 – 14, 2022

## Slide 2: Rel-18 timelines
SA#92-e
Jun/2021
SA#93e
Sep/2021
SA#94-e
Dec/2021
SA#95
Mar/2022
SA#96
Jun/2022
SA#97
Sep/2022
SA#98
Dec/2022
SA#99
Mar/2023
R17
stage 2
freeze
R17
stage 3
freeze
R17 code
freeze
stage 1
100%;
SA2 SIDs prioritization
R18 stage 2
Functional freeze
R18 stage 3
freeze
stage 1
>= 80%; SA2 SIDs Discussion
SA#100
Jun/2023
SA
Rel-18
Workshop
RAN
Rel-18
Workshop
Rel-18
timeline
Rel-18
content agreed
Rel-17
Schedule
Rel-18
Planning
exceptions
S1 normative ongoing;
SA2 SID Discussion
SA#101
Sep/2023
SA#102
Dec/2023
Exceptions
(if any)
R18 stage 2
SID Completion
/WIDs Approval
SA#103
Mar/2024
R18 code
freeze
R18 Stage 2 Study Phase
R18 Stage 2 Normative Phase
TEI18 propsoal submission/approval
TEI18 handling
R18 Stage 2 Study Agreed/ Endorsed

## Slide 3: SA2 Meeting Planning
TSG
153
(5)
152
(5)
TSG
Planned as E-meetings
June
2022
30-3
6-10
20-24
13-17
T
S
G
#
9
6
July
2022
27-1
4-8
18-29
11-15
Aug
2022
1-5
8-12
22-26
15-19
Sep
2022
29-2
5-9
19-23
12-16
T
S
G
#
9
7
Oct
2022
26-30
3-7
17-21
10-14
Nov
2022
24-28
31-4
7-11
SA2
152-E
(3+5)
SA2
153-E
(5)
14-18
Planned as F2F
154
(5)
January
2023
February
2023
16-20
23-27
30-03
06-10
13-17
20-24
March
2023
27-03
06-10
13-17
T
S
G
#
9
9
WG
TSG
S
P
R
I
N
G
F
E
S
T
I
V
A
L
20-24
E-meetings
F2F -meetings
December
2022
21-25
28-02
05-08
12-16
19-30
02-06
09-13
T
S
G
#
9
8
T
H
A
N
K
S
G
I
V
I
N
G
X
M
A
S
&
N
E
W
Y
E
A
R
SA2
154-AH
(5)
Planned as E-Meetings
Planned as F2F

## Slide 4: SA2 meeting dates for 2022 & 2023
SA2 F2F meeting calendar
  SA2 #153-E (10 – 14 Oct, 2022) – Electronic ordinary meeting
  SA2 #154 (14 – 18 Nov, 2022) – F2F ordinary meeting in Toulouse, FR
  SA2 #154-AH-E (16 – 20 Jan, 2023) – Electronic Adhoc meeting
  SA2 #155 (20 – 24 Feb, 2023) – F2F ordinary meeting in EU

## Slide 5: Guidance to Rel-18 Rapporteurs
Previous Guidance:
  Rel-18 Rapporteurs should put together a work plan for their SID and how they plan to utilize the assigned TU for each meeting. Update the Work Plan after each meeting. Can be part of the status report. For e.g. - SA2#152-E, 1 TU assigned, solution evaluation and conclusion, normative WID creation, etc.
  Rel-18 Rapporteurs shall provide the status report after each (e-)meeting on the progress, any controversial issue, RAN dependency, etc. Single status report covering both study and normative phase. Please use template defined for Rel-17 SIDs/WIDs.
Additional Guidance:
  Rel-18 Rapporteurs should prepare for conclusion the SIDs on time.
    Prioritize conclusions papers for offline CCs. Where consensus could not be achieved bring meaningful proposals for SoH (or utilize offline moderated email discussion).
  Rel-18 WID should be based on the conclusions agreed in the TR. WID can be further updated if new conclusions can be agreed. No blanket WIDs for plenary, please.
  Avoid pushing issues requiring further Study (SID) to the Normative phase (WID).

## Slide 6: Guidance on Rel-18 SIDs/WIDs
Rel-18 study phase should finish by SA2#154 (Nov F2F)
  SA2#154 should be the last meeting to handle Rel-18 study items conclusions. Conclusions papers will be top priority and other papers (e.g., solution update, etc.) may not get handled.
  WID update and CRs can submitted based on agreed WID from SA#153-E
  KIs not concluded by SA2#153E can be discussed at SA2#154 as long as overall TU budget remains unchanged. Such SIDs needs to borrow from corresponding normative TU budget at SA2#154.
  Rel-18 CRs can be submitted to SA#154 based on agreed new/revised Rel-18 WID from SA#153-E (even if it’s not TSG approved).
    It was previously agreed that Rel-18 WID and CRs can be submitted together to TSG SA#98-e for approval.
SA2 meetings in Q1, 2023 will focus on normative work
  Any TR not 100% complete will need valid justification to continue the work.
  Any RAN/other WG dependency will be tracked at KI granularity.
  Pushing study phase issues to normative phase is strongly discouraged. Rel-18 normative WIDs should be based on agreed TR conclusions.

## Slide 7
SA2#154 Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X (CRs only if there any incoming LS)
  AI 8.X: Rel-17 (CRs only if there any incoming LS)
  AI 9.X: Rel-18 (TU allocation as per NEW work plan)
Proposal
  Meeting closing time to be 6:00PM local time, may close early.
Open
  Email Approval – TBD.
Docs request | 04 Nov 2022 (Friday) | 2359 UTC
Docs submission | 04 Nov 2022 (Friday) | 2359 UTC
Registration | 07 Nov 2022 (Monday) | 0000 UTC
Start of meeting | 14 Nov 2022 (Monday) | 0900 Local Time
Close of meeting | 18 Nov 2022 (Friday) | 1800 Local Time
Upload Approved docs | 18 Nov 2022 (Friday) | 1800 Local Time
Upload Rapporteur Status Reports | 22 Nov 2022 (Tuesday) | 1700 UTC

## Slide 8
SA2#154-Ad-Hoc (Jan) Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Urgent LS and associated CRs
  AI 9.X: Rel-18 (TU allocation as per NEW work plan)
Proposal
  Agree to have SA2#154 Ad-hoc meeting as electronic ad-hoc meeting.
  5 days
  Only Rel-18 topics will be on agenda + Urgent LS
  TEI18 will be on agenda.
Docs request | 09 Jan 2023 (Monday) | 2359 UTC
Docs submission | 09 Jan 2023 (Monday) | 2359 UTC
Registration | 09 Jan 2023 (Monday) | 0000 UTC
Start of e-meeting | 16 Jan 2023 (Monday) | 0000 UTC
CC#1 | 16 Jan 2023 (Monday) | TBD
Revisions | 18 Jan 2023 (Wednesday) | 1600 UTC
Final Comments | 19 Jan 2023 (Thursday) | 1600 UTC
CC#2 | 19 Jan 2023 (Thursday) | TBD
CC#3 | 20 Jan 2023 (Friday) | TBD
Close of e-meeting | 20 Jan 2023 (Friday) | 1700 UTC
Upload Approved docs | 23 Jan 2023 (Monday) | 1700 UTC
Upload Rapporteur Status Reports | 24 Jan 2023 (Tuesday) | 1700 UTC

## Slide 9: TEI18 Handling
TEI18 proposals (shown in Red) will be on agenda for SA2#153E & SA2#154.
Remaining TEI18 proposal will be on agenda for SA2#154-AH-E and SA2#155.
TEI18 proposals needs to finish within 1 plenary cycle.
TD# | Type | Title | Acronym | TU Budget
SP-220793 | WID new | New WID: MBS support for V2X services (TEI18_MBS4V2X) | TEI18_MBS4V2X | 1 TU
SP-220794 | WID new | WID: TEI18_SLAMUP Spending Limits for AM and UE Policies in the 5GC (TEI18_SLAMUP) | TEI18_SLAMUP | 1 TU
SP-220795 | WID new | Multiple location report for MT-LR Immediate Location Request for the regulatory service (TEI18_MLR) | TEI18_MLR | 0.5TU
SP-220796 | WID new | TEI18 on enhancement of application detection event exposure (TEI18_ADEE) | TEI18_ADEE | 0.5TU
SP-220797 | WID new | New WID on General Support of IPv6 Prefix Delegation (TEI18_IPv6PD) | TEI18_IPv6PD | 0.5 TU
SP-220798 | WID new | Secondary DN Authentication and authorization in EPC IWK cases (TEI18_SDNAEPC) | TEI18_SDNAEPC | 0.5 TU
SP-220799 | WID new | New WID on Dynamically Changing AM Policies in the 5GC Phase 2 (TEI18_DCAMP_Ph2). | TEI18_DCAMP_Ph2 | 0.5TU
SP-220988 | WID new | New Rel-18 WID: Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection | eNSAC | 0.5TU

## Slide 10: Rel-18 TU Update for SA2#154
SA2#155 is planned as F2F meeting.
It needs to schedule 25 Rel-18 WIDs + 6 TEI18 WID + Exception sheet handling.
We need to extend to email/e-meeting to cover all topics.
  See initial thoughts in next slide
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0.25 | 0 | 0.25 | 0
FS_5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0.25 | 0.25
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 1
FS_TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0 | 1.5 | 1
FS_5G_ProSe_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.25
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0
FS_AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 1 | 2 | 2
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0.5 | 0.5
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0.5
FS_eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 1 | 1
FS_DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 0.5
FS_eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 1.75
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0.5
FS_REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0.5
FS_eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 1 | 1.5 | 1.5
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25
FS_ATSSS_ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0 | 1.25 | 1.25
FS_EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 1 | 1.5 | 2
FS_eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.25
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0 | 0.75 | 0.75
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0.5
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.75 | 0.5
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 0.5
Total | 119.5 | 71.75 | 191.25 | 19.25 | 21.5 | 27.5 | 29.75 | 26.25 | 13 | 26.75 | 27.25

## Slide 11
SA2#155 Dates/Agenda
SA2#155 will be F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X (CRs only if there any incoming LS)
  AI 8.X: Rel-17 (CRs only if there any incoming LS)
  AI 9.X: 25 Rel-18 WIDs + 6 TEI18
  AI 10.X: Rel-18 exception sheets
Proposal: To cover extensive agenda, we need extra days of meeting (within PCG guidelines).
  5 Days of ordinary F2F (20 - 24 Feb)
  3.5 Days of e-meeting (Ad-Hoc) (27 Feb – 02 Mar), Participation not counted towards voting rights.
  Agenda split/details - TBD
Docs request | 10 Feb 2023 (Friday) | 2359 UTC
Docs submission | 10 Feb 2023 (Friday) | 2359 UTC
Registration | 13 Feb 2022 (Friday) | 0000 UTC
Start of meeting | 20 Feb 2023 (Monday) | 0000 UTC
Close of meeting | 24 Feb 2023 (Friday) | 1700 UTC
Upload Approved docs/revisions | 27 Feb 2023 (Monday) | 1700 UTC
E-meeting Start | 27 Feb 2023 (Monday) | 2359 UTC
E-meeting Ends | 02 Mar 2023 (Thursday) | 1700 UTC
Upload Approved docs | 03 Feb 2023 (Friday) | 1700 UTC

## Slide 12: Proposals (to be Endorsed)
.