## Slide 1: FS_AMP Status Report AMP Status Report
Zhuoyi Chen
China Telecom (Rapporteur)

## Slide 2: FS_AMP status after SA2#154
General
  TR 23.700-89 v18.0.0 is available.
  Study phase was completed in SA2#152E.
NO TU is allocated for FS_AMP at SA2#154.
Next Steps:
  Remove the EN, and complete AMP SA2 normative work.
  RAN impacts and dependencies:
  No RAN impacts or dependencies are identified
WI Code | Work Item Title | WP | Target Date | WID#
FS_AMP | Study on 5G AM Policy | 100% | Sept, 22 | SP-211642
AMP | 5G AM Policy | 80 -> 80% | Mar, 23 | SP-220807

## Slide 3: FS_AMP status after SA2#154 (2/2)
Contentious Issue:
  None
Focus for the Next Meeting (SA2#154AH):
  No plan for SA2#154AH.
Overall Plan:
  SA2#149-E, 0.5 TU assigned, TR Skeleton, TR Scope, Architectural Assumption, Key Issues, allow solutions.
  SA2#150-E, 0.5 TU assigned, no new Key Issue could be allowed and the last e-meeting for new solution(s).
  SA2#151-E, no TU assigned.
  SA2#152-E, 0.5 TU assigned, for solution clean-up, evaluation and conclusion. Normative WID creation. Submit TR23.700-89 to SA#97E.
  SA2#153-E: 0.25 TU assigned, for normative
  SA2#154AH: 0.25 TU assigned, for normative
Risks:
  None.

## Slide 4: FS_AMP status at SA#98E
General
  TR 23.700-89 v18.0.0 is available.
  Study phase is completed.
  Normative phase begins and 5 CRs are approved at SA2#153E.
  WID update is submitted.
  RAN impacts and dependencies
  No RAN impacts or dependencies are identified
Next steps
  Remove the EN, and complete AMP normative work by SA#99.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AMP | Study on 5G AM Policy | 100% | Sept, 22 | SP-211642
AMP | 5G AM Policy | 0 -> 80% | Mar, 23 | SP-220807