## Slide 1: FS_5MBS_Ph2 status report
Li, Meng
Huawei

## Slide 2: FS_5MBS_Ph2 status after SA2#154 (1/2)
General
  TR 23.700-47 v1.2.0 is available.
  Total TUs requested for Study phase in 2022 is 7.5, all TUs for study phase has been used up after SA2#154 meeting.
  Now the percentage of TR completion is 100%.
  SA2 did not reach consensus on whether it is possible to add support of MOCN for multicast in Rel-18.
  RAN impacts and dependencies:
  The response LS has been sent to RAN2 and RAN3 in (S2-2211256) and highlighted the conclusions that requires coordination in the normative phase.
  Other WG dependencies
  KIs have potential SA6/SA4/SA3 coordination requirements accordingly as per agreed pCR.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 85% → 100% | Dec 2022 | SP-220072

## Slide 3: FS_5MBS_Ph2 status after SA2#154 (2/2)
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#154 AH):
  None.
Overall Plan: (study phase)
  SA2#149e, Feb (1TU): Focus on KIs, solutions are allowed. Agree the skeleton/scope/architectural assumption.
  SA2#150e, Apr (1TU): Focus on Solutions and complete all KIs. Potential updates/new KIs. Last meeting for KI proposal/modification.
  SA2#151e, May (2TUs): Solutions
  SA2#152, Aug (2TUs): Solutions, evaluations, conclusions
  SA2#153, Oct (1TU): Solution updates (No new Solutions), evaluations, conclusions: Approval of MBS_Ph2 WID.
  SA2#154, Nov (0.5 TU): final conclusions: Adjustment/issues depends on RAN progress, update of the WID.
    NOTE: In SA2#154 meeting, we have to re-arrange the TU allocated for study/normative phase, so 0.5 TU is not the exact number.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 12

## Slide 4: FS_5MBS_Ph2 Status at SA#98e
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 75% → 100% | Dec 2022 | SP-220072
  Progress since SA#97-e:
  TR 23.700-47 v1.2.0 is available.
  Total TUs requested for Study phase in 2022 is 7.5, all TUs for study phase has been used up after SA2#154 meeting.
  Now the percentage of TR completion is 100%.
  SA2 did not reach consensus on whether it is possible to add support of MOCN for multicast in Rel-18.
  RAN impacts and dependencies:
  The response LS has been sent to RAN2 and RAN3 in (S2-2211256) and highlighted the conclusions that requires coordination in the normative phase.
Other WG dependencies
  KIs have potential SA6/SA4/SA3 coordination requirements accordingly as per agreed pCR.
Contentious Issue:
  None.
Next steps:
  None.

## Slide 5: 5MBS_Ph2 status after SA2#154
General
  1 CR agreed to TS 23.247 based on the TR conclusion.
  RAN impacts and dependencies:
  RAN impacts as per agreed CRs.
  Other WG dependencies
  KIs have potential SA6/SA4 coordination requirements accordingly as per agreed CR.
Next steps
  Continue the normative work based on TR conclusions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 0% → 20% | Dec 2022 | SP-22xxxx

## Slide 6: 5MBS_Ph2 Status at SA#98e
Progress since SA#97e:
  1 CR agreed to TS 23.247 based on the TR conclusion.
  RAN impacts and dependencies:
  RAN impacts as per agreed CRs.
Next steps
  Continue the normative work based on TR conclusions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 0% → 20% | Dec 2022 | SP-22xxxx