## Slide 1: FS_5TRS_URLLC and TRS_URLLC Status Report
Devaki Chandramouli (Rapporteur)
Nokia

## Slide 2: FS_5TRS_URLLC status at SA#98E
General
  17 P-CRs agreed.
  Conclusions agreed and updated for all key issues
  3 LS out sent to SA3, RAN2, RAN3, SA1 to obtain feedback regarding open items related to KI#1, KI#6.
  Total TU(s) = 9 for study + normative phase; 8 TUs used, 1 TU remaining for normative phase (including resolution of open items for study phase).
RAN dependencies:
  S2-2209876 – LS on Time Synchronization Status notification towards UE(s).
  S2-2209964 – LS on low latency communication applications to use RAN feedback on periodicity for scheduling
  S2-2209879 - LS OUT on UL scenario of reactive RAN feedback for burst sending time adjustment.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5TRS_URLLC | Study on 5G Timing Resiliency and TSC & URLLC enhancements | 90%->98% | Dec’ 22 | SP-211634
Notes: S2-2201767

## Slide 3: FS_5TRS_URLLC status after SA2#153E
WI Code | Work Item Title | WP | Target Date | WID#
FS_5TRS_URLLC | Study on 5G Timing Resiliency and TSC & URLLC enhancements | 83%->90% | Dec’ 22 | SP-211634
General
  10 P-CRs agreed.
  New conclusions agreed for KI#1, KI#3. KI#2, 5, 6 conclusion updated.
  3 LS out sent to SA3, RAN2, RAN3, SA1 to obtain feedback regarding open items related to KI#1, KI#6.
  Total TU(s) = 9 for study + normative phase; 6 TUs used, 3 TUs remaining for normative phase (including resolution of open items for study phase).
RAN dependencies:
  S2-2209876 – LS on Time Synchronization Status notification towards UE(s).
  S2-2209964 – LS on low latency communication applications to use RAN feedback on periodicity for scheduling
  S2-2209879 - LS OUT on UL scenario of reactive RAN feedback for burst sending time adjustment.
Notes: S2-2201767

## Slide 4: FS_5TRS_URLLC status after SA2#154
WI Code | Work Item Title | WP | Target Date | WID#
FS_5TRS_URLLC | Study on 5G Timing Resiliency and TSC & URLLC enhancements | 90%->98% | Dec’ 22 | SP-211634
General
  7 P-CRs agreed.
  Conclusions updated for KI#1, KI#3, KI#6.
  Total TU(s) = 9 for study + normative phase; 8 TUs used, 1 TU remaining for normative phase (including resolution of open items for study phase).
RAN dependencies:
  S2-2209876 – LS on Time Synchronization Status notification towards UE(s).
  S2-2209964 – LS on low latency communication applications to use RAN feedback on periodicity for scheduling
  S2-2209879 - LS OUT on UL scenario of reactive RAN feedback for burst sending time adjustment.
Notes: S2-2201767

## Slide 5: TRS_URLLC status after SA2#154
WI Code | Work Item Title | WP | Target Date | WID#
TRS_URLLC | 5G Timing Resiliency and TSC & URLLC enhancements | 5%->50% | Dec’ 22 | SP-211634
General
  9 CRs agreed based on KI#2, KI#3, KI#5, KI#6 conclusion.
  KI#1 CRs not handled as the conclusion was still being updated and not stable yet.
RAN dependencies:
  Progress CRs based on resolution of the dependencies.
Notes: S2-2201767

## Slide 6: FS_5TRS_URLLC, TRS_URLLC status after SA2#154
  RAN and SA3 impacts and dependencies:
  LS response needed from respective WGs.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#154AH):
  Resolve open items in the TR conclusion for KI#1, KI#6 based on LS response.
  CRs related to KI#1 for approval. CRs related to KI#5, 6 open items for approval.
Overall Plan:
  No more new solutions or solution updates allowed.
  Resolve open items related for Key issues #1 conclusion (e.g. idle, inactive).
  Resolve open items related for Key issues #6 conclusion (e.g. periodicity, UL).
  CRs related to KI#1 for approval (SA2#154AH, SA2#155).
  CRs related to KI#5, 6 open items for approval (SA2#154AH). CRs related to KI#2, 3 open items for approval (SA2#155).
Risks:
  Risk of not getting more time for SI would also be KI#1 not fully addressed in Rel-18 Some ENs in the TS remain open after SA2#155.