## Slide 1: FS_NG_RTC Status Report
Yi Jiang (Rapporteur)
China Mobile

## Slide 2: FS_NG_RTC work plan updates
  The usage of TUs has been adjusted according to the delay of TR conclusion
    The total TU is still kept unchanged
    0.5 TU has been used for study at #153E, which decreases TU for normative work to 1.5
    More TUs are foreseen for TR conclusion
  The work plan is updated according to the progress at #153E:
  #154 has no agenda item for FS_NG_RTC and NG_RTC
  #154AH meeting: continue to conclude TR; start normative work if possible
  #155 meeting: continue normative work
  #156 meeting: exception for NG_RTC may be needed
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
 |  |  |  | #149E | #150E | #151E | #152E | #153E | #154 | #154AH | #155
SID/WID | Study Phase TU | Normative TU | Total TU |  |  |  |  |  |  |  | 
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 0.5

## Slide 3: FS_NG_RTC status after SA2#154
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC | Study on system architecture for next generation real time communication services | 79%->87% | Sep. 2022 | 940066
General
  17 contributions from 7 companies were submitted and were all handled in SA2#153
  Solution updates
    KI#1 (IMS Data Channel): solution 5, 6, 17, 20 and 22 were updated
  New solutions
    KI#1 (IMS Data Channel): 1 new solution postponed from SA#152E was agreed
  Evaluation and conclusions
    Conclusions to KI#1 was updated
    KI#3 was partially concluded
    KI#4 was concluded
  A LS on usage of DC application identifier in SDP is sent to SA4
  No agenda for FS_NG_RTC in SA2#154
  RAN impacts and dependencies:
  None
Next steps:
  Send the TR to plenary for approval
  Continue offline discussions and try to finalize conclusions on KI#1 and KI#3 at SA2 Jan Ad Hoc meeting
  Start normative work for concluded KIs if possible