## Slide 1: FS_XRM Status Report
Dan Wang, Hui Ni
China Mobile, Huawei

## Slide 2: FS_XRM status after SA2#154
General
  Total 11 papers are agreed including:
    10 p-CRs with concluding all the open issues.
    1 LS out to BBF and CableLabs.
  TR 23.700-60 is completed.
  RAN impacts and dependencies:
  Further cooperation with RAN WGs in normative phase.
  Contentious Issue:
  None
Focus for the Next Meeting (SA2#155E):
  Normative work
  Overall Plan: (study phase)
WI Code | Work Item Title | WP | Target Date | WID#
FS_XRM | Study on XR (Extended Reality) and media services | 90% 100% | Dec, 2022 | SP-220705
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_XRM | 10 | 4 | 14 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2

## Slide 3: FS_XRM status after SA2#153E (1/2)
General
  9 p-CRs agreed, including
  1 TR clean up
  8 Conclusion papers
  2 LSs out: 1 to RAN and 1 to SA4
Key Issue1&2(Coordinated transmission for single UE& multiple UEs)
  2 p-CRs for KI#1 and KI#2 conclusion separately
  Next step: Finalize conclusion and resolving ENs.
Key Issue 3 (Information Exposure)
  2 p-CR updating the existing conclusion
  Next step: Finalize conclusion and resolving ENs.
Key Issues 4&5(PDU Set )
  1p-CRs for KI#4&5 conclusion
  Next step: Finalize conclusion and resolving ENs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_XRM | Study on XR (Extended Reality) and media services | 75%  90% | Dec, 2022 | SP-220705
Key Issue 6(Round-Trip latency requirements)
  1 p-CR for conclusion update and conclusion for this KI has completed.
Key Issues 7(jitter minimization)
  Conclusion for this KI has completed.
Key Issues 8 (power savings)
  1 p-CR for evaluation and conclusion
  Next step: Finalize conclusion and resolving ENs.
Key Issues 9(Trade-off of QoE and Power Saving)
  1 p-CR for conclusion
  Next step: Finalize conclusion and resolving ENs.

## Slide 4: FS_XRM status after SA2#153E (2/2)
  RAN impacts and dependencies:
  1 LS to RAN with questions and current FS_XRM discussion status.
Other WG dependencies
  1 LS to SA4 for N6 PDU Set identification.
Contentious Issue:
  No
Focus for the Next Meeting (SA2#154):
  Finalizing conclusion and resolving ENs.
  WID submission for approval
Overall Plan: (study phase)
  SA2#149 Feb’22: TR skeleton, arch assumptions, KIs
  SA2#150 Apr’22: solutions discussions, and KIs. Finalize the KIs (no new KI proposal afterwards)
  SA2#151 May’22: potential KI update, solution discussions; solution evaluation with low priority
  SA2#152 Aug’22: solution updates (last chance for new solution)and start the evaluation and conclusion ; send TR for information;
  SA2#153 Oct’22: evaluation and conclusion for TR KIs; WID Approval;
  SA2#154 Nov: finalizing conclusion and resolving ENs.; WID Approval;Start to submit the R18 Draft CRs/CRs for concluded aspects.
  SA2#154AH and SA2#155 meeting: normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_XRM | 10 | 4 | 14 | 1 | 2 | 2 | 2 | 2 | 1 (change for Study phase) | 2 | 2

## Slide 5
Progress since SA#97
  Total 22 papers are agreed, including:
    19 p-CRs
    3 LSs out: 1 LS to RAN WGs, 1 LS to SA4, and 1 LS to BBF& CableLabs
  TR 23.700-60 is complete.
  Total TUs planed for normative work is 4 TU.
  RAN impacts and dependencies:
  Further cooperation with RAN WGs in normative phase.
Other WG dependencies
  Further cooperation with SA4 in normative phase.
Contentious Issue:
  No
  Next steps:
  Start the normative work.
FS_XRM status at SA#98
WI Code | Work Item Title | WP | Target Date | WID#
FS_XRM | Study on XR (Extended Reality) and media services | 75% 100% | Dec, 2022 | SP-220705