## Slide 1: SA2 Work Planning
Puneet Jain
SA2 Chair
SA WG2 Meeting #153E (e-meeting) S2-220xxxx
Oct 10 – 14, 2022

## Slide 2: Rel-18 timelines
SA#92-e
Jun/2021
SA#93e
Sep/2021
SA#94-e
Dec/2021
SA#95
Mar/2022
SA#96
Jun/2022
SA#97
Sep/2022
SA#98
Dec/2022
SA#99
Mar/2023
R17
stage 2
freeze
R17
stage 3
freeze
R17 code
freeze
stage 1
100%;
SA2 SIDs prioritization
R18 stage 2
Functional freeze
R18 stage 3
freeze
stage 1
>= 80%; SA2 SIDs Discussion
SA#100
Jun/2023
SA
Rel-18
Workshop
RAN
Rel-18
Workshop
Rel-18
timeline
Rel-18
content agreed
Rel-17
Schedule
Rel-18
Planning
exceptions
S1 normative ongoing;
SA2 SID Discussion
SA#101
Sep/2023
SA#102
Dec/2023
Exceptions
(if any)
R18 stage 2
SID Completion
/WIDs Approval
SA#103
Mar/2024
R18 code
freeze
R18 Stage 2 Study Phase
R18 Stage 2 Normative Phase
TEI18 propsoal submission/approval
TEI18 handling
R18 Stage 2 Study Agreed/ Endorsed

## Slide 3: SA2 Meeting Planning
TSG
153
(5)
152
(5)
TSG
Planned as E-meetings
June
2022
30-3
6-10
20-24
13-17
T
S
G
#
9
6
July
2022
27-1
4-8
18-29
11-15
Aug
2022
1-5
8-12
22-26
15-19
Sep
2022
29-2
5-9
19-23
12-16
T
S
G
#
9
7
Oct
2022
26-30
3-7
17-21
10-14
Nov
2022
24-28
31-4
7-11
SA2
152-E
(3+5)
SA2
153-E
(5)
14-18
Planned as F2F
154
(5)
January
2023
February
2023
16-20
23-27
30-03
06-10
13-17
20-24
March
2023
27-03
06-10
13-17
T
S
G
#
9
9
WG
TSG
S
P
R
I
N
G
F
E
S
T
I
V
A
L
20-24
E-meetings
F2F -meetings
December
2022
21-25
28-02
05-08
12-16
19-30
02-06
09-13
T
S
G
#
9
8
T
H
A
N
K
S
G
I
V
I
N
G
X
M
A
S
&
N
E
W
Y
E
A
R
SA2
154-AH
(5)
Planned as E-Meetings
Planned as F2F

## Slide 4: SA2 meeting dates for 2022 & 2023
SA2 F2F meeting calendar
  SA2 #153-E (10 – 14 Oct, 2022) – Electronic ordinary meeting
  SA2 #154 (14 – 18 Nov, 2022) – F2F ordinary meeting in Toulouse, FR
  SA2 #154-AH-E (16 – 20 Jan, 2023) – Electronic Adhoc meeting
  SA2 #155 (20 – 24 Feb, 2023) – F2F ordinary meeting in Athens, GR

## Slide 5: Guidance to Rel-18 Rapporteurs
Previous Guidance:
  Rel-18 Rapporteurs should put together a work plan for their SID and how they plan to utilize the assigned TU for each meeting. Update the Work Plan after each meeting. Can be part of the status report. For e.g. - SA2#152-E, 1 TU assigned, solution evaluation and conclusion, normative WID creation, etc.
  Rel-18 Rapporteurs shall provide the status report after each (e-)meeting on the progress, any controversial issue, RAN dependency, etc. Single status report covering both study and normative phase. Please use template defined for Rel-17 SIDs/WIDs.
Additional Guidance:
  Rel-18 Rapporteurs should prepare for conclusion the SIDs on time.
    Prioritize conclusions papers for offline CCs. Where consensus could not be achieved bring meaningful proposals for SoH (or utilize offline moderated email discussion).
  Rel-18 WID should be based on the conclusions agreed in the TR. WID can be further updated if new conclusions can be agreed. No blanket WIDs for plenary, please.
  Avoid pushing issues requiring further Study (SID) to the Normative phase (WID).

## Slide 6: Guidance on Rel-18 SIDs/WIDs
Rel-18 study phase should finish by SA2#154 (Nov F2F)
  SA2#154 should be the last meeting to handle Rel-18 study items conclusions for study items on the agenda. Conclusions papers will be top priority and other papers (e.g., solution update, etc.) may not get handled.
  WID update and CRs can submitted based on agreed WID from SA#153-E
  KIs not concluded by SA2#153E can be discussed at SA2#154 as long as overall TU budget remains unchanged. Such SIDs needs to borrow from corresponding normative TU budget at SA2#154.
  Rel-18 CRs can be submitted to SA#154 based on agreed new/revised Rel-18 WID from SA#153-E (even if it’s not TSG approved).
    It was previously agreed that Rel-18 WID and CRs can be submitted together to TSG SA#98-e for approval.
SA2 meetings in Q1, 2023 will focus on normative work
  Any TR not 100% complete will need valid justification to continue the work.
  Any RAN/other WG dependency will be tracked at KI granularity.
  Pushing study phase issues to normative phase is strongly discouraged. Rel-18 normative WIDs should be based on agreed TR conclusions.

## Slide 7
SA2#154 Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X (CRs only if there any incoming LS)
  AI 8.X: Rel-17 (CRs only if there any incoming LS)
  AI 9.X: Rel-18 (TU allocation as per NEW work plan)
Proposal
  Meeting closing time to be 6:00PM local time, may close early.
Open
  Email Approval – TBD.
Docs request | 04 Nov 2022 (Friday) | 2359 UTC
Docs submission | 04 Nov 2022 (Friday) | 2359 UTC
Registration | 07 Nov 2022 (Monday) | 0000 UTC
Start of meeting | 14 Nov 2022 (Monday) | 0900 Local Time
Close of meeting | 18 Nov 2022 (Friday) | 1800 Local Time
Upload Approved docs | 18 Nov 2022 (Friday) | 1800 Local Time
Upload Rapporteur Status Reports | 22 Nov 2022 (Tuesday) | 1700 UTC

## Slide 8
SA2#154-Ad-Hoc (Jan) Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Urgent LS and associated CRs
  AI 9.X: Rel-18 (TU allocation as per NEW work plan)
Proposal
  Agree to have SA2#154 Ad-hoc meeting as electronic ad-hoc meeting.
  5 days
  Only Rel-18 topics will be on agenda + Urgent LS
  TEI18 will be on agenda.
Docs request | 09 Jan 2023 (Monday) | 2359 UTC
Docs submission | 09 Jan 2023 (Monday) | 2359 UTC
Registration | 09 Jan 2023 (Monday) | 0000 UTC
Start of e-meeting | 16 Jan 2023 (Monday) | 0000 UTC
CC#1 | 16 Jan 2023 (Monday) | TBD
Revisions | 18 Jan 2023 (Wednesday) | 1600 UTC
Final Comments | 19 Jan 2023 (Thursday) | 1600 UTC
CC#2 | 19 Jan 2023 (Thursday) | TBD
CC#3 | 20 Jan 2023 (Friday) | TBD
Close of e-meeting | 20 Jan 2023 (Friday) | 1700 UTC
Upload Approved docs | 23 Jan 2023 (Monday) | 1700 UTC
Upload Rapporteur Status Reports | 24 Jan 2023 (Tuesday) | 1700 UTC

## Slide 9: TEI18 Handling
TEI18 proposals (shown in Red) will be on agenda for SA2#153E & SA2#154.
Remaining TEI18 proposal will be on agenda for SA2#154-AH-E and SA2#155.
TEI18 proposals needs to finish within 1 plenary cycle.
TD# | Type | Title | Acronym | TU Budget
SP-220793 | WID new | New WID: MBS support for V2X services (TEI18_MBS4V2X) | TEI18_MBS4V2X | 1 TU
SP-220794 | WID new | WID: TEI18_SLAMUP Spending Limits for AM and UE Policies in the 5GC (TEI18_SLAMUP) | TEI18_SLAMUP | 1 TU
SP-220795 | WID new | Multiple location report for MT-LR Immediate Location Request for the regulatory service (TEI18_MLR) | TEI18_MLR | 0.5TU
SP-220796 | WID new | TEI18 on enhancement of application detection event exposure (TEI18_ADEE) | TEI18_ADEE | 0.5TU
SP-220797 | WID new | New WID on General Support of IPv6 Prefix Delegation (TEI18_IPv6PD) | TEI18_IPv6PD | 0.5 TU
SP-220798 | WID new | Secondary DN Authentication and authorization in EPC IWK cases (TEI18_SDNAEPC) | TEI18_SDNAEPC | 0.5 TU
SP-220799 | WID new | New WID on Dynamically Changing AM Policies in the 5GC Phase 2 (TEI18_DCAMP_Ph2). | TEI18_DCAMP_Ph2 | 0.5TU
SP-220988 | WID new | New Rel-18 WID: Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection | eNSAC | 0.5TU

## Slide 10: Rel-18 Study/Work Items: Summary
UID | Name | Acronym | SID | Target | AT SA#96 | AT SA#97-e | After SA2#153-e | Comments/At risk
940060 | Study on Support of Satellite Backhauling in 5GS | FS_5GSATB | SP-211639 | 3/10/2023 | 60% | 80% | 98% | All KIs concluded. Study phase completed. On Track
940074 | Study on 5GC enhancement for satellite access Phase 2 | FS_5GSAT_Ph2 | SP-211651 | 9/12/2022 | 50% | 75% | 100% | All KIs concluded. Study phase completed. On Track
940065 | Study on Personal IoT Networks | FS_PIN | SP-211643 | 9/12/2022 | 60% | 75% | 95% (?) | All KIs concluded. Study phase completed (?). On Track (?)
940051 | Study on Phase 2 of UAS, UAV and UAM | FS_UAS_Ph2 | SP-211632 | 9/12/2022 | 50% | 80% | 98% | All KIs concluded. Study phase completed. On Track
940069 | Study on Ranging based services and sidelink positioning | FS_Ranging_SL | SP-211647 | 12/12/2022 | 60% | 70% | 85% | Many KIs remains to be concluded. Study TUs used. At Risk.
940058 | Study on Enhancement to the 5GC LoCation Services-Phase 3 | FS_eLCS_Ph3 | SP-220069 | 12/12/2022 | 55% | 80% | 100% | All KIs concluded. Study phase completed. On Track
940077 | Study on Stage 2 for Proximity based Services Phase 2 | FS_5G_ProSe_Ph2 | SP-211653 | 12/12/2022 | 55% | 75% | 95% | KI#7 remains to be concluded. Study TUs used. At Risk
940061 | Study on generic group management, exposure and communication enhancements | FS_GMEC | SP-211603 | 9/12/2022 | 70% | 90% | 95% | KI#4 remains to be concluded. Study TUs used. At Risk.
940071 | Study on 5G System Support for AI/ML-based Services | FS_AIMLsys | SP-220071 | 9/12/2022 | 60% | 70% | 90% | KI#5, KI#7 remains to be concluded. Study TUs used. At Risk.
940067 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | FS_5MBS_Ph2 | SP-220072 | 9/12/2022 | 55% | 75% | 85% | KI#1, #2, #3, #5 remains to be concluded. Study TUs used. At Risk. RAN dependency.
940063 | Study on Enhancement of Network Slicing Phase 3 | FS_eNS_Ph3 | SP-220073 | 9/12/2022 | 50% | 70% | 85% | Large number of EN remains for KI#1, #3, #5, #6. Study TUs used. At Risk.
940068 | Study on architecture enhancement for XR and media services | FS_XRM | SP-220705 | 12/12/2022 | 40% | 75% | 90% | KI#1 - 5, KI#8, KI#9 remains to be concluded. Study TUs used. At Risk.
940056 | Study on RedCap Phase 2 | FS_REDCAP_Ph2 | SP-220074 | 9/12/2022 | 70% | 98% | 100% | Study 100% complete. Normative work 60% complete. On Track.
940066 | Study on system architecture for next generation real time communication services | FS_NG_RTC | SP-220288 | 9/12/2022 | 55% | 79% | 80% | KIs not concluded. Study TUs used. At Risk.
940070 | Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 | FS_ATSSS_Ph3 | SP-211612 | 9/12/2022 | 70% | 80% | 100% | All KIs concluded. Study phase completed – On Track
940076 | Study on UPF enhancement for Exposure And SBA | FS_UPEAS | SP-220417 | 12/12/2022 | 60% | 80% | 98% | Some EN in KI#1, KI#2 remains. Study TUs used. On Track
940059 | Study on Stage 2 of Edge Computing phase 2 | FS_EDGE_Ph2 | SP-220352 | 12/12/2022 | 55% | 83% | 97% (?) | KI#1 (HR), KI#6 remains to be concluded. Study TUs used. At Risk (?)
940055 | Study on 5G Timing Resiliency and TSC&URLLC enhancements | FS_5TRS_URLLC | SP-211634 | 9/12/2022 | 65% | 83% | 90% | KI#1, KI#3, KI#6 remains to be concluded. Study TUs used. At Risk.
940057 | Study on Architecture Enhancements for Vehicle Mounted Relays | FS_VMR | SP-211636 | 9/12/2022 | 55% | 80% | 90% | RAN dependent open issues remains. Study TUs used. At Risk.
840085 | Study on enhancement of support for 5WWC | FS_5WWC_Ph2 | SP-220419 | 9/12/2022 | 60% | 80% | 90% | KI#1 remains to be concluded. Study TUs used. At Risk.
940053 | Stage 2 of MPS_WLAN | MPS_WLAN | SP-211595 | 9/12/2022 | 0% | 0% | 0% | Work Item. On Track
940064 | Study on 5G AM Policy | FS_AMP | SP-220647 | 9/12/2022 | 80% | 100% | 100% | Study 100% complete. Normative work 80% complete. On Track.
940073 | Study on Enablers for Network Automation for 5G - phase 3 | FS_eNA_Ph3 | SP-220678 | 9/12/2022 | 50% | 75% | 88% (?) | Most KI#1 to KI#9 remains to be concluded. Study TUs used. At Risk.
940075 | Study on enhanced support of Non-Public Networks phase 2 | FS_eNPN_Ph2 | SP-220418 | 12/12/2022 | 50% | 75% | 90% | KI#2, KI#4 remains to be concluded. Study TUs used. At Risk.
840020 | Study on enhancement of 5G UE Policy | FS_eUEPO | SP-211649 | 12/12/2022 | 70% | 80% | 95% | KI#1, KI#2, KI#3 remains to be concluded. Study TUs used. At Risk.
940052 | Study on System Enabler for Service Function Chaining | FS_SFC | SP-220415 | 9/12/2022 | 60% | 80% | 100% | All KIs concluded. Study phase completed. On Track
940054 | Study on Extensions to the TSC Framework to support DetNet | FS_DetNet | SP-211633 | 9/12/2022 | 70% | 90% | 90% | One open issue remains in TR. Study TUs used. At Risk.
940079 | Study on Seamless UE context recovery | FS_SUECR | SP-211654 | 9/12/2022 | 100% | 100% | 100% | Study 100% complete. Normative work 100% complete. Finished.

## Slide 11: Work overload and SA2#155 F2F planning
SA2#155 is planned as F2F meeting. It needs to schedule 25 Rel-18 WIDs + 6 TEI18 WID + Exception sheet handling.
Issue #1: Study items not finishing by Nov may delay completion of normative work by Mar 2023.
  Option 1a: Drop the KI that are not concluded by Nov (for SID on agenda for SA2#154) / Jan (for SID not on agenda for SA2#154).
  Option 1b: Ask TSG#98e to move Stage-2 freeze from Mar 2023 -> June 2023. All study items should finish by Jan (no extension).
Issue #2: It is not possible to schedule 25 Rel-18 WIDs + 6 TEI18 WID + Rel-18 exception sheet handling in parallel at SA2#155.
  Option 2a: Add additional 3.5 days of e-meeting and split the agenda to cover all topics. See proposal in slide#12.
  Option 2b: Ask TSG#98e to move Stage-2 freeze from Mar 2023 -> June 2023. All study items should finish by Jan (no extension). All Normative work should finish by May 2023 (no extension).
NOTE: SoH will be taken on the above options.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0.25 | 0 | 0.25 | 0
FS_5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0.25 | 0.25
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 1
FS_TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0 | 1.5 | 1
FS_5G_ProSe_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.25
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0
FS_AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 1 | 2 | 2
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0.5 | 0.5
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0.5
FS_eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 1 | 1
FS_DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 0.5
FS_eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 1.75
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0.5
FS_REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0.5
FS_eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 1 | 1.5 | 1.5
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25
FS_ATSSS_ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0 | 1.25 | 1.25
FS_EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 1 | 1.5 | 2
FS_eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.25
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0 | 0.75 | 0.75
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0.5
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.75 | 0.5
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 0.5
Total | 119.5 | 71.75 | 191.25 | 19.25 | 21.5 | 27.5 | 29.75 | 26.25 | 13 | 26.75 | 27.25

## Slide 12
SA2#155 Dates/Agenda
SA2#155 will be F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X (CRs only if there any incoming LS)
  AI 8.X: Rel-17 (CRs only if there any incoming LS)
  AI 9.X: Rel-18 WIDs + TEI18 (details TBD)
  AI 10.X: Rel-18 exception sheets
Assumption: Rel-18 stage-2 freeze is Mar 2023, and Rel-18 timelines as agreed before.
Option 2a from slide#11:
  4 Days of e-meeting (Ad-Hoc) (27 Feb – 02 Mar), Participation not counted towards voting rights.
  AI 9.X: Rel-18 WIDs + TEI18 (details TBD)
  AI 10.X: Rel-18 exception sheets
Docs request | 10 Feb 2023 (Friday) | 2359 UTC
Docs submission | 10 Feb 2023 (Friday) | 2359 UTC
Registration | 13 Feb 2022 (Friday) | 0000 UTC
Start of meeting | 20 Feb 2023 (Monday) | 0000 UTC
Close of meeting | 24 Feb 2023 (Friday) | 1700 UTC
Upload Approved docs/revisions | 27 Feb 2023 (Monday) | 1700 UTC
E-meeting Start | 27 Feb 2023 (Monday) | 1600 UTC
Revision deadline | 27 Feb 2023 (Tuesday) | 1600 UTC
Final deadline | 27 Feb 2023 (Wednesday) | 1600 UTC
E-meeting Ends | 02 Mar 2023 (Thursday) | 1700 UTC
Upload Approved docs | 03 Feb 2023 (Friday) | 1700 UTC

## Slide 13: Proposals (to be Endorsed)
.