## Slide 1: WI and SID Status Report on 5GC enhancement for satellite access Phase 2
Jean-Yves Fine
Thales (Rapporteur)

## Slide 2: FS_5GSAT_Ph2, 5GSAT_Ph2 status after SA2#155 (1/2)
General
  TR 23.700-28 v18.0.0 is available.
  Study phase was completed in SA2#153E, normative phase started at SA2#154AHE.
  4 CRs are approved at SA2#154AHE for TS23.501, 1CR is approved to update EN in TR23.700-28
  4 CRs are approved at SA2#155 for TS23.501.
  RAN impacts and dependencies:
  No RAN impacts or dependencies are identified
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSAT_Ph2 | Study on satellite access, Phase2 | 100% | Oct, 22 | SP-211651
5GSAT_Ph2 | 5GC/EPC enhancement for satellite access Phase 2 | 70% | Jun, 23 | SP-221344

## Slide 3: FS_5GSAT_Ph2, 5GSAT_Ph2 status after SA2#155 (2/2)
Contentious Issue:
  None
Overall Plan:
  1.5 additional TUs are endorsed (S2-2301447).
  Total TU for normative: 3.5 (1 additional TU allocated in Athens)
  All conclusions for the 2KeyIssues were agreed during SA2#153
    SA2#154: FS_5GSAT_Ph2 not at the agenda (chairman request) only new WID for normative phase was presented
    SA2#154AH: Normative work, focus on 501 CR
    SA2#155 meeting: Focus on 501 CRs
    SA2#156 meeting: Focus on solving reminding 23.501 Editor’s notes and AMF satellite info provisioning, 502&503, 401CRs
    SA2#157 meeting: finalize open points
Risks:
  None.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23
Rel-18 SID/WID | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0,5 | 0,5 | 1 | 1 | 1 | 0 | 0,5 | 1+1 | 0,5 | 0,5

## Slide 4
FS_5GSAT_Ph2, 5GSAT_Ph2 status after SA#99
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSAT_Ph2 | Study on satellite access, Phase2 | 100% | Oct, 22 | SP-211651
5GSAT_Ph2 | 5GC/EPC enhancement for satellite access Phase 2 | 0 -> 70% | Jun, 23 | SP-221344
General
  Total of 8 normative CRs were agreed.
  Total of 1+1.5(additionally requested) + 1 (allocated in Athens) TUs were temporally requested for normative phase in 2023. 2.5 TUs have been used.
  RAN impacts and dependencies:
  None
Contentious Issues:
  None.
Next steps:
  Complete the work:
    Solve Editor’s notes in 23.501
    Finalize AMF/MME satellite information provisioning item.
    Finalize normative work for 23.502 and EPS according 23.501
  It is expected to complete the remaining work in time by SA#100 (stage 2 freeze).