## Slide 1: FS_eUEPO/eUEPO Status Report
Intel (Rapporteur)

## Slide 2: FS_eUEPO status report to SA#99
WI Code | Work Item Title | WP | Target Date | WID#
FS_eUEPO | Study on enhancement of 5G UE Policy | 95% -> 100% | June 2023 | SP-220416
General
  The latest TR 23.700-85 v1.3.0 is generated by incorporating approved contributions at SA2 #154AHE. TR coversheet and revised WID were approved at SA2#155.
  Total TUs requested for Study Phase is 4.25 TUs, and 0 TUs are left.
  All key issues are completely concluded.
  At SA2#154AHE, 15 papers were submitted, 5 papers were approved, 3 papers were not handled.
KI#1(URSP in VPLMN):
  1 conclusion paper was approved.
KI#2(5GC awareness of URSP enforcement):
  2 conclusion papers were approved.
KI#3(Provision consistent URSP to UE across 5GS and EPS):
  2 conclusion papers resolving were approved.
KI#4(Support standardized and operator-specific traffic categories in URSP):
  This key issue has been completely concluded at SA2#153e, no paper was submitted.
Contentious issue:
  None.

## Slide 3: eUEPO status report to SA#99
WI Code | Work Item Title | WP | Target Date | WID#
eUEPO | enhancement of 5G UE Policy | 0% -> 65% | June 2023 | SP-221127
General
  At SA2#154AHE, 11 papers were submitted for normative work, 7 CRs were approved, all papers were handled.
  At SA2#155, 31 papers were submitted for normative work, 9 CRs were approved, 8 CRs were not handled. 2 LS OUTs (CT1 and GSMA respectively) on Traffic Categories were approved.
KI#1(URSP in VPLMN):
  6 CRs were approved.
KI#2(5GC awareness of URSP enforcement):
  4 CRs were approved.
KI#3(Provision consistent URSP to UE across 5GS and EPS):
  4 CRs were approved.
KI#4(Support standardized and operator-specific traffic categories in URSP):
  2 CRs were approved.
Contentious issue:
  None.

## Slide 4: eUEPO status at SA2#155
WI Code | Work Item Title | WP | Target Date | WID#
eUEPO | enhancement of 5G UE Policy | 40% -> 65% | June 2023 | SP-221127
General
  31 papers were submitted, 9 CRs were approved, 8 CRs were not handled.
  2 LS OUTs (CT1 and GSMA) on Traffic Categories were approved.
KI#1(URSP in VPLMN):
  5 CRs were approved.
KI#2(5GC awareness of URSP enforcement):
  4 CRs were approved.
KI#3(Provision consistent URSP to UE across 5GS and EPS):
  No CR was handled.
KI#4(Support standardized and operator-specific traffic categories in URSP):
  Two LS OUTs were approved. No CR was approved.
Contentious issue:
  None.

## Slide 5: Rel-18 eUEPO Overall Work Plan
 |  |  |  | Jan, 23 | Feb, 23 | Apr, 23 | May, 23 |  |  |  |  | 
SID/WID | Study TU | Normative TU | Total TU | #154AHE | #155 | #156E | #157 |  |  |  |  | Total TU
  Overall Work Plan
  SA2#155AH(e), 0.75 TU was assigned for both study and normative phases:
    Resolve the ENs in the TR conclusion, update conclusions, progress the normative work.
  SA2#155, 1 TU assigned for normative phase, 30 CRs for normative phase in maximum:
    Progress the normative work. WID update, TR for approval.
  SA2#156E, 1 TU assigned for normative phase, 30 CRs for normative phase in maximum:
    Progress the normative work.
  SA2#157, 0.5 TU assigned for normative phase, 15 CRs for normative phase in maximum:
    Complete the normative work.
eUEPO | 4.25 | 2.75 | 7 | 0.75 | 1 | 1 | 0.5 |  |  |  |  | 7