## Slide 1: WI and SID Status Report on Ranging based services and sidelink positioning
Sherry (Yang) Shen
Xiaomi (Rapporteur)
S2-2303455

## Slide 2: FS_Ranging_SL status after SA2#155
General
  The latest TR 23.700-86 is available here: http://www.3gpp.org/ftp/Specs/archive/23_series.
  Conclusions for the 8 KIs are updated and completed
  7 Solutions are updated (#3, #7, #9, #20, #25, #26 and #30)
  2 LSs sent to RAN WGs for RAN dependent issues, i.e. broadcast/groupcast, RSPP/SLPP transport, QoS parameters for Service Authorization, assistant UE, etc.
34 solutions and their mapping to Key Issues (see the table)
  RAN and SA3 impacts and dependencies:
  RAN impacts or dependencies identified for Key Issue #1, #2, #3, #4, #5 and #8, and their corresponding solutions
  Privacy protection and other SA3 security aspects identified for Key Issue #2, #3, #4, #5, #6 and #7, and their corresponding solutions
Contentious Issue:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_Ranging_SL | Study on Ranging based services and sidelink positioning | 85% > 100% | Mar, 23 | SP-211647
 | Key Issues |  |  |  |  |  |  | 
Solutions | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | X |  |  |  |  |  |  | X
2 | X |  |  |  |  |  |  | 
3 |  |  |  | X |  |  |  | 
4 |  |  | X | X |  |  |  | 
5 |  |  | X | X |  |  |  | 
6 |  |  |  |  | X |  |  | 
7 |  |  |  |  | X |  |  | 
8 |  |  |  |  | X |  |  | 
9 |  |  |  |  |  | X |  | 
10 |  |  |  |  |  | X |  | 
11 |  |  |  |  |  | X |  | 
12 |  |  |  |  | X |  | X | 
13 |  |  |  |  |  |  | X | 
14 | X | X | X | X | X | X | X | X
15 |  |  |  |  |  |  |  | X
16 |  | X |  |  |  |  |  | 
17 |  | X |  |  |  |  |  | 
18 |  |  | X |  |  |  |  | 
19 |  |  |  | X | X |  |  | 
20 |  |  |  |  | X |  |  | 
21 |  |  |  |  | X |  |  | 
22 |  |  |  |  |  | X | X | 
23 |  |  |  |  |  |  | X | 
24 |  |  |  |  |  |  | X | 
25 |  |  |  |  |  | X |  | 
26 |  | X | X | X | X | X | X | 
27 |  | X | X | X | X | X | X | 
28 |  | X | X | X | X | X | X | 
29 |  | X |  |  |  |  |  | 
30 |  | X |  |  |  |  |  | 
31 |  |  |  |  | X |  |  | 
32 |  |  |  | X | X |  |  | 
33 |  |  |  |  |  | X | X | 
34 |  | X |  |  |  | X |  | 

## Slide 3: Ranging_SL status after SA2#155
General
  The latest TS 23.586 is available here: http://www.3gpp.org/ftp/Specs/archive/23_series.
  SA2#154AHe:
    Skeleton and scope of of TS 23.586 agreed.
    4 pCRs related to introduction, architectural reference model, functional entities and 2 high level functionalities agreed and documented in TS 23.586.
  SA2#155:
    TS 23.586: 15 pCR related to introduction, architectural reference model, functional entities, and high level functionalities agreed.
    TS 23.273: 1 CR to update architecture reference model + 1 CR for the general introduction of the new Ranging/SL Positioning procedures agreed
    1 LS out sent to SA5 on charging solution + 1 LS out sent to RAN2 on support of multiple Target UEs
  RAN, SA3 and SA5 impacts and dependencies:
  Since corresponding RAN work and SA3 work are progressing, some alignments are expected, e.g. RSPP related for RAN, privacy protection and service access authorization for SA3, etc.
  SA5 is asked to develop the charging solution.
Contentious Issue:
  None
WI Code | Work Item Title | WP | Target Date | WID#
Ranging_SL | Stage 2 of Ranging-based services and Sidelink Positioning | 10% > 50% | Jun, 23 | S2-2303106

## Slide 4: Work Plan after SA2#155
Focus for the Next Meeting:
  SA2#156e: Contribute to TS 23.586, TS 23.273, TS 23.501, TS 23.502 and TS 23.503 with high priority for features/descriptions of no/less RAN, SA3, and SA5 dependency or features/descriptions based on clear feedback from RAN GWs, SA3, and SA5
Overall Plan:
Feb, 22 #149 0.5 | Apr, 22 #150 0.5 | May, 22 #151 1 | Aug, 22 #152 0.5 | Oct, 22 #153 0.5 | Nov, 22 #154 0 | Jan, 23 #154AHe 0.5+1 | Feb, 23 #155 1 | Apr, 23 #156e 2 | May 23 #157 1
 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | 
TR for information @ SA#97e
WID approval @ SA#98e
TR completion @ SA#99
 Contributions are conditionally handled & approved
 Contributions are handled and approved
 Last chance for new proposal to be handled and approved
TS completion @ SA#100
TR Skeleton, Scope
Reference & Definition
Architecture requirement & assumptions
Key Issue
Solution
Evaluation & Conclusion
WID Approval
TS Development

## Slide 5: Ranging_SL SID/WID status at SA#99
Progress since SA#98e:
  TR 23.700-86: TR conclusions for the 8 KIs are updated and completed, and 7 TR solutions are updated (#3, #7, #9, #20, #25, #26 and #30)
  TS 23.586: Skeleton and scope of of TS 23.586 agreed. 21 pCRs related to introduction, architectural reference model, functional entities and high level functionalities agreed and documented in TS 23.586.
  TS 23.273: 1 CR to update architecture reference model + 1 CR for the general introduction of the new Ranging/SL Positioning procedures agreed
  3 LSs sent to RAN WGs + 1 LS sent to SA5
RAN, SA3 and SA5 impacts and dependencies:
  Since corresponding RAN work and SA3 work are progressing, some alignments are expected, e.g. RSPP related for RAN, privacy protection and service access authorization for SA3, etc.
  SA5 is asked to develop the charging solution.
Next steps:
  SA2#156e&SA2#157: Contribute to TS 23.586, TS 23.273, TS 23.501, TS 23.502 and TS 23.503 with high priority for features/descriptions of no/less RAN, SA3, and SA5 dependency or features/descriptions based on clear feedback from RAN GWs, SA3, and SA5
WI Code | Work Item Title | WP | Target Date | WID#
FS_Ranging_SL | Study on Ranging based services and sidelink positioning | 85% > 100% | Mar, 23 | SP-211647
Ranging_SL | Stage 2 of Ranging-based services and Sidelink Positioning | 10% > 50% | Jun, 23 | S2-2303106