## Slide 1: WI Status Report: Vehicle Mounted Relays (VMR)
Qualcomm Incorporated
S2-2303460

## Slide 2: FS_VMR status after SA2#155 (1/2)
General
  Normative Phase work progress to 40%.
  0.5 TU used for the E-meeting (processed 13 contributions).
  1 TU planned for Apr meeting.
  0.5 TU planned for May meeting.
  RAN impacts and dependencies:
  Pending response from RAN2/3 on LS (S2-2211437) regarding the support of certain features based on SA2 conclusions.
Other WG dependencies
  One LS (S2-2301465) sent to SA3/SA5 (and cc RAN3) regarding the secure and trusted access to the serving PLMN OAM server by a MBSR.
WID was approved in SA#98 (SP-221328) and updated to S2-2303033
  Completion date updated to Jun 2023 aligned with stage 2 freeze dates.
Normative work progress:
  9 CR approved.
  1 CR (S2-2301451) technically endorsed.
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 100% | Nov, 22 | SP-211636
VMR | Architecture Enhancements for Vehicle Mounted Relays | 20% > 40% | Jun, 23 | SP-221328

## Slide 3: FS_VMR status after SA2#154AH-E (2/2)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157 | Total TU
FS_VMR | 3.75 | 2.75 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 (1.25+0.75) | 0.5 | 0 | 1.0 | 0.5 | 6.5
Contentious Issue:
  MBSR node authorization handling; OAM interactions for LCS support.
Focus of the Apr Meeting (SA2#156):
  Normative work based on the objectives of the WID & response from RAN WGs and SA3/SA5.
Overall work Plan:
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (New KIs; solutions)
  SA2#151 May’22: 0.5 (Last chance for KIs; last chance for new solutions; solution updates)
  SA2#152 Aug’22: 0.5 (Solution updates; evaluations; Interim conclusions, send TR to RAN for comments)
  SA2#153 Oct’22: 0.5 (Finalize conclusions; WID approval)
  SA2#154 Nov’22: 1.25 (Resolve RAN dependent open issues for selected solutions); start normative work 0.75.
  SA2#154AH Jan’23: 0.5 (Normative work)
  SA2#155 Feb’23: 0
  SA2#156 Apr’23: 1.0 (Normative work) – additional TU requested
  SA2#157 May’23: 0.5 (Normative work) – additional TU requested.

## Slide 4: FS_VMR status at SA#99
Progress since SA#98:
  Normative Phase work progress to 40%.
  WID (SP-221328) updated to S2-2303033 to reflect the target completion date (Jun’23)
  1.5 TU remaining for the WID.
RAN impacts and dependencies:
  Pending response from RAN2/3 on LS (S2-2211437) regarding the support of certain features based on SA2 conclusions.
Next steps:
  Normative work based on approved WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 100% | Nov, 22 | SP-211636
VMR_ARCH | Architecture Enhancements for Vehicle Mounted Relays | 20% > 40% | Jun, 23 | SP-221328