## Slide 1: XRM Status Report
Dan Wang, China Mobile
Yixue Lei, Tencent

## Slide 2: XRM status after SA2#157
WI Code | Work Item Title | WP | Target Date | WID#
FS_XRM | Study on XR (Extended Reality) and media services | 100% | Dec, 2022 | SP-220705
XRM | Architecture Enhancements for XR and media services (XRM) | 85%->98% | June, 2023 | SP-230092
  Progress since SA2#157
  Paper status:
    13 CRs are approved.
  RAN impacts and dependencies:
  3 LSs are sent to inform RAN WGs
    1 LS reply for TSCAI
    1 LS reply for measurement data rate exposure by NG-RAN and UP based QNC.
    1 LS to RAN WGs for Non-homogeneous deployment of PDU Set based QoS handling.
  Other WG dependencies
  2 LS are sent to SA4
    1 LS reply for design of RTP header.
    1 LS reply for N6 PDU Set Identification.
  Contentious Issue:
  UL PDU set handling and Non-Homogeneous deployment depends on RAN WG’s progress

## Slide 3
Focus for the Next Meeting (SA2#158):
  CRs for functionality introduction (Cat B/C) for TS23.501 should be frozen(Except when based on incoming LS trigger). Some CRs(Cat B/C) for TS 23.502/23.503 needed in order to keep alignment with TS23.501 and complete stage 2 functionality need to be handled.
Overall Plan:
  SA2#149 Feb’22: TR skeleton, arch assumptions, Key Issues;
  SA2#150 Apr’22: solutions discussions, and KIs. Finalize the KIs (no new KI proposal afterwards)
  SA2#151 May’22: potential KI update, solution discussions; solution evaluation with low priority
  SA2#152 Aug’22: solution updates (last chance for new solution)and start the evaluation and conclusion ; send TR for information;
  SA2#153 Oct’22: evaluation and conclusion for TR Kis;
  SA2#154 Nov’22: finalizing conclusion and resolving ENs.; WID Approval;
  SA2#154AH Jan’23: Start the normative work;
  SA2#155 Feb’23: WID update for timeline, continue the normative work;
  SA2#156 April’23: Continue the normative work; resolving the ENs in CRs;
  SA2#157 May’23: Complete the 501 CRs. Some Key Issues of 502/503 CRs are completed
  SA2#158 August: Complete the whole work.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | April,23 | May,23 | August 20
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156E | #157 | #158
FS_XRM | 10->11 | 4->8 | 14->19 | 1 | 2 | 2 | 2 | 2 | 1 ->2 | 2 | 2 | 2 | 2 | ?
XRM status after SA2#157

## Slide 4
General
  30 CRs are approved.
Contentious Issue:
  UL PDU set handling and Non-Homogeneous deployment depends on RAN WG’s progress
Other WG dependencies
  Two Editor Notes(UL PDU set handling and Non-homogeneous deployment) remained due to pending RAN progress
Focus of the Next Meeting (SA2#158):
  CRs for functionality introduction (Cat B/C) for TS23.501 should be frozen(Except when based on incoming LS trigger). Some CRs(Cat B/C) for TS 23.502/23.503 needed in order to keep alignment with 23.501 and complete stage 2 functionality need to be handled.
  LS triggered CRs
WI Code | Work Item Title | WP | Target Date | WID#
XRM | Architecture Enhancements for XR and media services (XRM) | 85%->98% | June, 2023 | SP-230092
XRM status after SA#99