## SA2 Work Plan post SA2#157
SA WG2 Meeting #157 |  | S2-2308257
May 22 – 26, 2023
|  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23
|  |  |  | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157
|  |  |  | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan
Rel-15/Rel-16 maintenance
| Combined (Multiple WIDs) |  |  | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Sum |  |  | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Rel-17 maintenance
| Combined (17 WIDs) |  |  | 12 | 12 | 10 | 8 | 8 | 6 | 4 | 4 | 4 | 4
| Sum |  |  | 12 | 12 | 10 | 8 | 8 | 6 | 4 | 4 | 4 | 4
Rel-17 Alignment (with RAN/CT)
| Combined (3 WIDs) |  |  | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0
Total (Maintenance) |  |  |  | 18 | 18 | 13 | 12 | 12 | 9 | 6 | 6 | 6 | 6
Buffer (TEI18, overflow, other)
| Buffer |  |  | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3
Total (Maintenance + Buffer) |  |  |  | 18 | 18 | 13 | 12 | 15 | 12 | 9 | 9 | 9 | 9
Available for Rel-18 SIDs/WIDs |  |  |  | 20 | 20 | 25 | 26 | 23 | 26 | 29 | 29 | 29 | 29
|  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23
Rel-18 SID/WID | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157 | Study TU (Used) | Normative TU (used) | Total TU (used) | Additonal TU (%) | Study % Compeltion after SA2#154AHE | Work % completion after SA2#154 | Work % completion after SA2#154AHE | Work % completion after SA2#155 | Work % completion after SA2#156E | Work % completion after SA2#157 | Normative TU (Used) after SA2#154AHE | Normative TU (Used) after SA2#155 | Normative TU (Used) after SA2#156E | Normative TU (Used) after SA2#157 | Total TU (Remaining) | Additonal Total TU requested (vs orig plan)
FS_SATB / SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 0.5 | 0 | 3.5 | 2 | 5.5 | 10% | 100% | 30% | 65% |  | 100% |  | 1.5 | 1.5 | 2 | 2 | 0 | 0.5
FS_5GSAT_Ph2 / 5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0.5 | 2 | 0.5 | 1 | 4 | 4 | 8 | 60% | 100% | 0% | 20% | 60% | 80% | 100% | 0.5 | 2.5 | 3 | 4 | 0 | 3
FS_PIN / PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 1 | 2 | 1 | 2 | 3.5 | 6 | 9.5 | 72.73% | 100% | 0% | 20% | 60% | 80% | 100% | 1 | 3 | 4 | 6 | 0 | 3
FS_UAS_Ph2 / UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1 | 1 | 1 | 3.25 | 4 | 7.25 | 31.82% | 100% | 0% | 25% | 85% | 95% | 100% | 1 | 2 | 3 | 4 | 0 | 1.5
FS_Ranging_SL / Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0 | 1.5 | 2 | 2 | 2 | 3 | 7.5 | 10.5 | 90.91% | 100% | 0% | 10% | 50% | 80% | 100% | 1.5 | 3.5 | 5.5 | 7.5 | 0 | 4
FS_eLCS_Ph3 /eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 2 | 1.5 | 2 | 1 | 2 | 7.25 | 7.5 | 14.75 | 43.9% | 100% | 30% | 45% | 65% | 85% | 100% | 2.5 | 4.5 | 5.5 | 7.5 | 0 | 3.5
FS_5G_ProSe_Ph2 / 5G_Prose_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 7 | 7 | 14 | 51.35% | 100% | 20% | 60% | 80% | 95% | 100% | 2 | 4 | 5 | 7 | 0 | 3.25
FS_GMEC / GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.75 | 0 | 1 | 0 | 4 | 2.25 | 6.25 | 8.696% | 100% | 15% | 70% |  | 100% |  | 1.25 | 1.25 | 2.25 | 2.25 | 0 | 0.5
FS_AIMLsys / AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 2 | 2 | 2 | 2 | 2 | 8.5 | 7.5 | 16 | 33.33% | 100% | 5% | 20% | 50% | 80% | 100% | 2.5 | 4.5 | 5.5 | 7.5 | 0 | 4
FS_5MBS_Ph2 / 5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 0 | 8.5 | 5.5 | 14 | 16.67% | 100% | 20% | 60% | 75% | 100% |  | 2.5 | 4.5 | 5.5 | 5.5 | 0 | 2
FS_eNS_Ph3 / eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1.25 | 2 | 7.75 | 6.5 | 14.25 | 54.05% | 100% | 1% | 20% | 50% | 80% | 100% | 1.25 | 3.25 | 4.5 | 6.5 | 0 | 4.5
FS_XRM / XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 11 | 10 | 21 | 50% | 100% | 0% | 30% | 50% | 85% | 98% | 2 | 5 | 7 | 10 | 0 | 5
FS_REDCAP_Ph2 / REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.25 | 1 | 2 | 2.25 | 4.25 | 41.67% | 100% | 60% | 95% |  | 98% | 100% | 1 | 1 | 1.25 | 2.25 | 0 | 0.5
FS_NG_RTC / NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 1 | 1 | 2 | 4.5 | 5 | 9.5 | 58.33% | 100% | 0% | 10% | 60% | 85% | 100% | 1 | 2 | 3 | 5 | 0 | 1.5
FS_ATSSS_Ph3 / ATSSS_Ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0 | 1.25 | 0 | 1.25 | 0 | 6 | 2.5 | 8.5 | 0% | 100% | 0% | 85% |  | 100% |  | 1.25 | 1.25 | 2.5 | 2.5 | 0 | 0
FS_UPEAS / UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0 | 0.5 | 0 | 3.25 | 2.25 | 5.5 | 0% | 100% | 20% | 75% |  | 100% |  | 1.75 | 1.75 | 2.25 | 2.25 | 0 | 0
FS_EDGE_Ph2 / EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 2 | 1.5 | 2 | 1.5 | 2 | 8 | 8 | 16 | 39.13% | 100% | 15% | 50% | 80% | 90% | 100% | 2.5 | 4.5 | 6 | 8 | 0 | 3.5
FS_5TRS_URLLC / TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 2 | 1 | 1 | 0.5 | 1 | 7 | 4.5 | 11.5 | 27.78% | 100% | 50% | 70% | 80% | 95% | 100% | 2 | 3 | 3.5 | 4.5 | 0 | 2
FS_VMR / VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 0 | 1 | 1 | 3.5 | 3.5 | 7 | 40% | 100% | 20% | 40% |  | 80% | 100% | 1.5 | 1.5 | 2.5 | 3.5 | 0 | 1
FS_5WWC_Ph2 / 5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0.75 | 2 | 1.5 | 3.5 | 5 | 100% | 100% | 20% | 45% |  | 80% | 100% | 0.75 | 0.75 | 1.5 | 3.5 | 0 | 1
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 2 | 2 | 0% | NA | 0% | 50% |  | 98% | 100% | 1.5 | 1.5 | 2 | 2 | 0 | 0.25
FS_AMP / AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 1.5 | 0.5 | 2 | 0% | 100% | 80% | 100% |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
FS_eNA_Ph3 / eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 9 | 11 | 20 | 42.86% | 100% | 25% | 45% | 65% | 85% | 100% | 3 | 6 | 8 | 11 | 0 | 5
FS_eNPN_Ph2 / eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 2 | 1 | 2 | 1 | 0 | 7 | 5 | 12 | 23.08% | 100% | 50% | 70% | 90% | 100% |  | 2 | 4 | 5 | 5 | 0 | 2.25
FS_eUEPO / eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0 | 0.75 | 1 | 1 | 2 | 4.25 | 4.75 | 9 | 56.52% | 100% | 0% | 40% | 65% | 90% | 100% | 0.75 | 1.75 | 2.75 | 4.75 | 0 | 2.25
FS_SFC / SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 3 | 1 | 4 | 0% | 100% | 0% | 60% |  | 100% |  | 0.5 | 0.5 | 1 | 1 | 0 | 0
FS_DetNet / DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 1 | 0.5 | 0 | 1 | 2 | 3 | 50% | 100% | 0% | 50% | 90% | 100% |  | 0.5 | 1.5 | 2 | 2 | 0 | 1
FS_SUECR / SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0.25 | 1.75 | 0% | 100% | 100% |  |  |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0
Total Rel-18 SID/WID | 119.5 | 71.75 | 191.25 | 19.25 | 21.5 | 27.5 | 29.75 | 26.25 | 23 | 27.25 | 31 | 26.5 | 31 | 134.25 | 127.75 | 262 | 36.99% | [6 empty] | 40.25 | 71.25 | 96.75 | 127.75 | 0 | 55
TEI-18 mini WIDs
TEI18_MLR |  | 0.5 | 0.5 | #153: 0.25; #154: 0.25; #157: 0 |  | 0.5 | 0.5 | 0% | NA | 100% |  |  |  |  | 0.5 |  |  |  | 0
TEI18_SDNAEPC |  | 0.5 | 0.5 | #153: 0.25; #154: 0.25; #157: 0 |  | 0.5 | 0.5 | 0% | NA | 100% |  |  |  |  | 0.5 |  |  |  | 0
TEI18_MBS4V2X |  | 1 | 1 | #154AH: 0.5; #155: 0.5; #157: 0 |  | 1 | 1 | 0% | NA | 0% | 100% |  |  |  | 0.5 | 1 |  |  | 0
TEI18_SLAMUP |  | 1 | 1 | #154AH: 0.5; #155: 0; #157: 0.5 |  | 1 | 1 | 0% | NA | 0% | 80% |  | 80% | 100% | 0.5 |  |  |  | 0.5
TEI18_ADEE |  | 0.5 | 0.5 | #154AH: 0.25; #155: 0.25; #157: 0 |  | 0.5 | 0.5 | 0% | NA | 0% | 100% |  |  |  | 0.25 | 0.25 |  |  | 0
TEI18_IPv6PD |  | 0.5 | 0.5 | #154AH: 0.25; #155: 0; #157: 0 |  | 0.5 | 0.5 | 0% | NA | 0% | 100% |  |  |  | 0.25 | 0 |  |  | 0.25
TEI18_DCAMP_Ph2 |  | 0.5 | 0.5 | #156: 0.25; #157: 0.25 |  | 0.5 | 0.5 | 0% | NA | 0% | 0% |  | 80% | 100% | 0 |  | 0.25 |  | 0.25
eNSAC |  | 0.5 | 0.5 | #156: 0.25; #157: 0.25 |  | 0.5 | 0.5 | 0% | NA | 0% | 0% |  | 60% | 100% | 0 |  | 0.25 |  | 0.25
Total TEI-18 mini WID |  | 5 | 5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1.5 | 0.75 | 0.5 | 1 | 0 | 5 | 5 | 0% | [6 empty] | 2.5 | 1.25 | 0.5 |  | 1.25 | 0
Total Rel-18 | 119.5 | 76.75 | 196.25 | 19.25 | 21.5 | 27.5 | 29.75 | 26.75 | 23.5 | 28.75 | 31.75 | 27 | 32 | 134.25 | 132.75 | 267 | 36.05% | [6 empty] | 42.75 | 72.5 | 97.25 | 127.75 | 1.25 | 55
Others
Generic Rel-18 LSs | bar: #156 to #157
Rel-18 alignment (not in SA2 scope) | bar: #157
NOTE1: Planning is based on max 38 TUs (including 3TU as buffer) per meeting
NOTE2: TU budget estimates assumes 8 meetings untill stage-2 freeze deadline
Note on K34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 (Normative) + 0.5 (Study)
Note on J39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 0.5
Note on I45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on J46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on I47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 1
Note on J48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on I53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 (Study) + 0.5 (normative)