## Slide 1: FS_5GSAT_Ph3 _ARCH Status Report Study on Integration of satellite components in the 5G architecture Phase 3
Jean-Yves Fine
Thales (Rapporteur)
Note: following guidance from work plan manager, acronym for SID is now FS_5GSAT_Ph3 _ARCH instead of FS_5GSAT _ARCH_Ph3

## Slide 2
General
  TU estimates for the study phase:7 (1TU used in Xiamen, 1TU used in Chicago, 1.5 used in Elbonia)
  Total TU estimates for the normative phase: 5.5
  TR skeleton , definition, scope, Architecture Assumptions are agreed
  3 Key Issues are agreed
  Several solutions provided for all Key Issues, good panel of several possible technical options
Progress since SA#101
  Start the study phase, TR 23.700-29 v0.1.0 available
  TR 23.700-29 v0.2.0 available
  TR 23.700-29 v0.3.0 available
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSAT_Ph3_ARCH | Study on Integration of satellite components in the 5G architecture Phase 3 | 20 -> 40% | June, 2024 | SP-231199
FS_5GSAT_Ph3 _ARCH status after SA2#161AH

## Slide 3
  RAN impacts and dependencies
  Yes, on WT#1, WT#2, WT#3
Contentious issues
  none
Overall Plan
Next steps
  Last meeting to provide/update solutions. Start solutions evaluation
FS_5GSAT_Ph3 _ARCH status after SA2#161AH
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, definition, assumption, scenario
SA2#160 | Nov 2023 | 1 | 1 | Key Issues, assumptions
SA2 E-AH | Jan 2024 | 1.5 | 1,5 | last meeting for Key Issues update (no new KI), start solution discussions
SA2#161 | Feb 2024 | 1 |  | Provide/update solutions. Start solutions evaluation
SA2#162 | Apr 2024 | 1.5 |  | Last meeting to update solutions. Continue solutions evaluation and start conclusion.
SA2#163 | May 2024 | 1 |  | Complete evaluations and conclusions
 | Total | 7 |  |