## Slide 1: FS_VMR_Ph2 Status Report
Qualcomm Incorporated
S2-2401670

## Slide 2: FS_VMR_Ph2 status after SA2#160 Ad Hoc-E (1/2)
General
  TR 23.700-06 v.0.1.0 was created based on approved contributions.
  11 contributions agreed (including TR skeleton, scope, architecture assumptions and requirements, and key issues).
  0.5 TU used and 2.5 TU left for the Study Phase.
6 Key Issues agreed for the study:
  Key Issue #1: Architectural enhancements for the support of a MWAB
  Key Issue #2: Authorization of a MWAB and configuration of MWAB
  Key Issue #3: Control of UE's access to 5GS via a wireless access backhaul
  Key Issue #4: Efficient mobility and service continuity when served by MWAB
  Key Issue #5: Support of location services for UEs when MWAB(s) is involved
  Key Issue #6: Support of Emergency services for UEs via a MWAB
  RAN impacts and dependencies:
  RAN impacts or dependencies identified for Key Issue #1, #2, #3, #4
Other WG dependencies
  Charging support is expected to be handled by SA5, and security to be handled by SA3.
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR_Ph2 | Study on Vehicle Mounted Relays Phase 2 | 0% > 15% | Jun, 24 | SP-231799 (updated by S2-2401625)

## Slide 3: FS_VMR_Ph2 status after SA2#160 Ad Hoc-E (2/2)
Contentious Issue:
  None.
Focus of the Next Meeting (SA2#161):
  Handle any new Key Issue or update existing key issues
  Handle solutions for all Key Issues
Overall Plan: (study phase)
  SA2#160-Ah-Hoc-e Jan’24: 0.5 TU (TR skeleton, Scope, Assumptions, Key Issues)
  SA2#161 (Athens) Feb’24: 0.5 TU (New KIs, KI updates; New solutions)
  SA2#162 (China) Apr’24: 1.0 TU (KI updates if needed; last chance for new solutions; solution updates, initial evaluations/Start coord with RAN)
  SA2#163 (Jeju) May’24: 1.0 TU (Solution updates; evaluations; conclusions, send TR for approval; WID approval – Send TR to RAN for review)
  SA2#164 (EU) Aug’24: 0.5 TU ( Normative work, coordination with RAN – If needed, finalize remaining TR conclusions)
  SA2#165 (India) Oct’24: 1.0 TU (Normative work, coordination with RAN)
  SA2#166 (Orlando) Nov’24: 1 TU (Normative work, coordination with RAN)
 |  |  |  | Jan, 24 | Feb.24 | Apr. 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | 
SID/WID | Study TU | Normative TU | Total TU | #160 | #161 | #162 | #163 | #164 | #165 | #166 | Total used TU
FS_VMR | 3 | 2.5 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 1 | 1 | 5.5

## Slide 4: FS_VMR_Ph2 status at SA#103
Progress since SA#102:
  TR 23.700-06 v.0.1.0 was created based on approved contributions.
  11 contributions agreed (including TR skeleton, scope, architecture assumptions and requirements, and 6 key issues).
  0.5 TU used and 2.5 TU left for the Study Phase.
Impacts and dependencies on other WGs:
  RAN impacts or dependencies identified for Key Issue #1, #2, #3, #4
Next steps:
  Handle any new Key Issue
  Handle solutions for all Key Issues
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 06/03/2024 | 0% | SP-231799 | 15% | SID to be updated by S2-2401625