## Slide 1: WI Status Report for eNA_Ph3
Aihua Li (China Mobile), Xiaobo Wu(Vivo)

## Slide 2: eNA_Ph3 status at SA#102
WI Code | Work Item Title | WP | Target Date | WID#
eNA_Ph3 | Enablers for Network Automation for 5G - phase 3 | 100%->100% | June 2023 | SP-220678
General
  180 proposals are sumbitted in SA2#159 and #160 totally.
  52 CRs are agreed, 8 CRs are merged, 7 CRs are noted and 6 CRs are postponed.
  1 LS IN is REPLY OPEN to CT3, 1 LS OUT is agreed and 3 LS OUTs are merged.
  1 LS IN and 1 LS OUT is not handled, 4 LS IN and 1 LS OUT is postponed.
  3 CRs are withdrawn, 1 DP is noted, 1 DP and 90 CRs are not handled.
  SA2 work on all key issues are completed.
  RAN impacts and dependencies:
  No RAN impact.
Contentious Issue:
  No contentious Issue.
Focus for the Next Meeting (SA2 #161):
  Correction and Maintenance .
    Risk:
  None.

## Slide 3: eNA_Ph3 status after SA2#160 (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
eNA_Ph3 | Enablers for Network Automation for 5G - phase 3 | 100%->100% | June 2023 | SP-220678
General
  99 proposals are sumbitted.
  30 CRs are agreed, 1 CR is merged, 1 CR is noted and 5 CRs are postponed.
  3 LS IN and 1 LS OUT is postponed.
  1 CR is withdrawn, 1 DP is noted and 56 CRs are not handled.
  SA2 work on all key issues are completed.
General issue
    2 CRs are agreed, 2 CRs are not handled and 1 DP is not noted.
KI#1: How to improve correctness of NWDAF analytics:
    11 CRs are agreed.
    KI#2: NWDAF-assisted application detection:
    3 CRs are agreed, 1 CR is merged, 1 CR is postponed and 1 CR is not handled.
    KI#3: Data and analytics exchange in roaming case:
    2 CRs are agreed and 2 CRs are not handled.
    KI#4: How to Enhance Data collection and Storage:
    5 CRs are agreed and 13 CRs are not handled.
    KI#5: Enhance trained ML Model sharing:
    2 CRs are agreed, 2 CRs are postponed and 1 CR is withdrawn.

## Slide 4: eNA_Ph3 status after SA2#160 (2/2)
    KI#6: NWDAF-assisted URSP:
    1 CR is agreed.
    KI#7: Enhancements on QoS Sustainability analytics:
    2 LS IN and 1 LS OUT is postponed.
    KI#8: Supporting Federated Learning in 5GC:
    1 CR is agreed and 23 CRs are not handled.
    KI#9: Enhancement of NWDAF with finer granularity of location information:
    3 CRs are agreed, 2 CRs are postponed and 1 CR is noted.
    KI#10: Interactions with MDAS/MDAF:
    1 LS IN is postponed and 2 CRs are not handled.
  Editorial clean-up
    13 CRs are not handled.
  RAN impacts and dependencies:
  No RAN impact.
Contentious Issue:
  No contentious Issue.
Focus for the Next Meeting (SA2 #161):
  Correction and Maintenance .
    Risk:
  None.

## Slide 5: eNA_Ph3 status after SA2#159 (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
eNA_Ph3 | Enablers for Network Automation for 5G - phase 3 | 100%->100% | June 2023 | SP-220678
General
  81 proposals are sumbitted.
  22 CRs are agreed, 7 CRs are merged, 6 CRs are noted and 1 CR is postponed.
  1 LS IN is REPLY OPEN to CT3, 1 LS OUT is agreed and 3 LS OUTs are merged.
  1 LS IN and 1 LS OUT is not handled, and 1 LS IN is postponed.
  2 CRs are withdrawn, 1 DP and 34 CRs are not handled.
  SA2 work on all key issues are completed.
eNetAE related
    1 LS IN is REPLY OPEN to CT3, 2 CRs are noted, 1 CR is merged, 3 LS OUTs are merged and 1 LS OUT is agreed.
KI#1: How to improve correctness of NWDAF analytics:
    7 CRs are not handled.
    KI#2: NWDAF-assisted application detection:
    4 CRs are not handled.
    KI#3: Data and analytics exchange in roaming case:
    2 CRs are not handled.
    KI#4: How to Enhance Data collection and Storage:
    5 CRs are not handled.
    KI#5: Enhance trained ML Model sharing:
    4 CRs are not handled.

## Slide 6: eNA_Ph3 status after SA2#159 (2/2)
    KI#6: NWDAF-assisted URSP:
    No contributions.
    KI#7: Enhancements on QoS Sustainability analytics:
    2 CRs are not handled, 1 LS IN and 1 LS OUT is not handled.
    KI#8: Supporting Federated Learning in 5GC:
    14 CRs are agreed, 2 CRs are noted, 3 CRs are merged and 2 CRs are withdrawn.
    KI#9: Enhancement of NWDAF with finer granularity of location information:
    7 CRs are agreed, 2 CRs are noted and 2 CRs are postponed.
    KI#10: Interactions with MDAS/MDAF:
    1 CR is agreed, 1 CR is merged, 1 CR is postponed and 1 LS IN is postponed.
  General
    1 DP is not handeld and 10 CRs are not handled.
  RAN impacts and dependencies:
  No RAN impact.
Contentious Issue:
  No contentious Issue.
Focus for the Next Meeting (SA2 #160):
  Correction and Maintenance .
    Risk:
  None.

## Slide 7
Backup Slide for eNA_Ph3 Study Phase Work Plan
#149 meeting: focus on TR skeleton, scope, assumptions and KIs, no solution will be discussed;
#150 meeting: solutions discussions, and KIs. Finalize the KIs (Last chance for new KI proposal);
#151 meeting: continue the solution discussions and capture new solutions;
#152 meeting: solution updates/merging and last chance for new solution(s) (1 supporting companies required) and start to evaluate/conclude solution(s) and send TR for information;
#153 meeting: continue the evalutaion&conclusion, disusss the WID proposal.
#154 meeting: finalize the conclusion and approve the WID for 1 TU, and start normative work;
#154AH, #155 and #156E meeting: continue normative work.
#157 meeting: finalize normative work, focusing on KI# 1/3/4/6/8/9/10.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23 | 
Rel-18 SID/WID | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157 | Total TU
FS_eNA_Ph3 | 9 | 8 | 14 | 1 | 1 | 2 | 2 | 2 | 1+1 | 2 | 3 | 2 | 3 | 18