## Slide 1: Release 19 FS_MPS4msg Status Report
Robert Streijl
Peraton Labs (Rapporteur)

## Slide 2: FS_MPS4msg Status at SA#102
Progress since SA#101:
  TR 23.700-75 v0.1.0 is available
  Study started with SA2#160 (not on agenda for SA2#159).
  13 TDocs were submitted to SA2#160.
  pCRs for TR skeleton, Scope, Architecture Assumptions and 3 Key Issues to cover the WTs in the SID have been agreed.
Impacts and dependencies on other WGs:
  None
  Contentious issues:
  None
Next steps:
  Start solution discussions for agreed Key Issues in next meeting
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 18/06/2024 | 0% | SP-231197 | 20% | Study in progress

## Slide 3: FS_MPS4msg Status after SA2#160
  General
  Started the Study in SA2#160
  Tdocs were submitted for Skeleton, Scope, Architecture assumptions, Key Issues, and a few Solutions.
  Solutions were noted and deferred to the next meeting.
  Progress since SA2#159
  6 pCRs were agreed: Skeleton, Scope, Assumptions, and 3 Key Issues.
  RAN impacts and dependencies
  None
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 18/06/2024 | 0% | SP-231197 | 20% | Study in progress

## Slide 4: FS_MPS4msg Status after SA2#160
  Other WG dependencies
  None
  Contentious issues
  None
  Plans for upcoming meetings (2.25 TUs remaining)
  SA2#160-E-AH: Start solution discussion
  SA2#161: Continue solution discussion, last meeting for new solution proposals
  SA2#162: Last meeting for solution updates, start discussion on evaluation and conclusion
  SA2#163: Complete solution evaluation and study conclusion

## Slide 5: FS_MPS4msg Work Plan
Total 6 TUs
  3 TUs for Study Phase
  3 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 0 | 0 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 0.75 | 0.75 | Continue discussion on Key Issues, start solution discussion
SA2#160-E-AH | Jan 2024 | 0.5 |  | Continue solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1 |  | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 0.25 |  | Last meeting for solution updates, start discussion on evaluation and conclusion
SA2#163 | May 2024 | 0.5 |  | Complete evaluations and conclusions
 | Total | 3 |  | 
Note: Planned TU allocation may change