## Slide 1: FS_EnergySys Status Report
Jungshin Park (Samsung),
Konstantinos Samdanis (Lenovo)

## Slide 2: FS_EnergySys Status at SA#103
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 15% | SP-231192 | 55% | Study in progress
  Progress since SA#102
  TR 23.700-66 v.0.4.0 has been produced
  Architectural Assumption, Scope and Definitions have been updated by three accepted pCRs
  Total 32 new solutions have been accepted in the TR
  4.5 TUs have been used and 2 TUs are remaining for Study Phase
  Impacts and dependencies on other WGs:
  RAN impacts/dependencies are possible based on proposed solutions documented in TR.
  An LS to TSG RAN and related WGs has been sent on the topic of per-UE energy consumption assessment in RAN
  SA5 dependencies are possible based on proposed solutions documented in TR
  Contentious issues
  None
  Next Steps
  Discuss on solutions updates and unhandled new solution proposals (if not covered by the existing solutions)
  Complete evaluation and conclusion
  Submit TR 23.700-66 to SA#104 for approval

## Slide 3: FS_EnergySys Status after SA2#161
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 40% | SP-231192 | 55% | Study in progress
  General
  Total 81 TDocs are submitted, 18 pCRs and 2 LSs have been agreed
  Discussion focused on new solution proposals
  Solutions updates will be discussed in the SA2#162 meeting
  Progress since SA2#160AH-e
  1 pCR for updating Definition has been accepted
  Total 17 new solutions have been accepted in the meeting
    5 new solutions have been accepted for KI#1
    8 new solutions have been accepted for KI#2
    4 new solutions have been accepted for KI#3

## Slide 4: FS_EnergySys Status after SA2#161
  RAN impacts and dependencies
  RAN impacts/dependencies are possible based on proposed solutions documented in TR
  An LS to TSG RAN and related WGs has been sent on the topic of per-UE energy consumption assessment in RAN
  Other WG dependencies
  SA5 dependencies are possible based on proposed solutions documented in TR
  Contentious issues
  None
  Plans for upcoming meetings (2 TUs remaining)
  SA2#162: Focus on solution updates, only unhandled new solution proposals from #161 (if not covered by the existing solutions), start discussion on evaluation and conclusion
  SA2#163: Critical solution updates only, Complete solution evaluation and study conclusion

## Slide 5: FS_EnergySys Status after SA2#160AH-e
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 15% | SP-231192 | 40% | Study in progress
  General
  Total 83 TDocs are submitted, and 30 TDocs (for 1TU) + 2 LSs are handled in the meeting
  Solution discussions started from this meeting
  Two LS proposals have been postponed to the next meeting
  Progress since SA#102
  Architectural Assumption, Scope and Definitions have been updated and agreed 3 pCRs
  Total 15 new solutions out of 23 proposals have been accepted in the meeting
    6 new solutions have been accepted for KI#1
    5 new solutions have been accepted for KI#2
    4 new solutions have been accepted for KI#3
  RAN impacts and dependencies
  None

## Slide 6: FS_EnergySys Status after SA2#160AH-e
  Other WG dependencies
  None
  Contentious issues
  None
  Plans for upcoming meetings (3.5 TUs remaining)
  SA2#161: Continue solution discussion, last meeting for new solution proposals
  SA2#162: last meeting for solution updates, start discussion on evaluation and conclusion
  SA2#163: Complete solution evaluation and study conclusion

## Slide 7: FS_EnergySys Work Plan
Total 13 TUs
  6.5 TUs for Study Phase
  6.5 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 1 | 1 | Continue discussion on Key Issues, start solution discussion
SA2#160AH-e | Jan 2024 | 1 | 1 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1.5 | 1.5 | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 1 |  | Focus on solution updates, only unhandled new solution proposals from #161(if not covered by the existing solutions), start discussion on evaluation and conclusion
SA2#163 | May 2024 | 1 |  | Critical solution updates only, Complete evaluations and conclusions
 | Total | 6.5 |  |