## Slide 1: FS_AmbientIoT Status Report
Runze Zhou (Huawei), Fei Lu (OPPO)
(Rapporteurs)

## Slide 2: FS_AmbientIoT Status after SA2#162
  Overall progress in SA2#162
  In total 16 papers are agreed, including:
    12 new solutions
    3 solution update
    1 new abbreviation “RFID”
  TR 23.700-13 v0.3.0 is available, including 24 solutions
  Impacts and dependencies on other WGs
  Several solutions have EN/note, need coordination with RAN, SA3 and SA5
Next steps
  Continue solution discussions( last time for new solution proposal) in SA2#163 meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 25% -> 45% | Dec 2024 | SP-231803 1020071

## Slide 3
In total 11.5 TUs for Study Phase
Check in TSG#106 (Dec’24) for further Ambient IoT work taking into account RAN Ambient IoT progress
FS_AmbientIoT Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 E-AH | Jan 2024 | 0.5 | 0.5 | TR skeleton, scope, architectural assumptions/requirements Start and complete key issue (only for information)Solutions
SA2#161 | Feb 2024 | 2 | 2 | Start solutions discussions key issue update to address the ENs can be considered NOTE: no new key issue proposal will be considered
SA2#162 | Apr 2024 | 2 | 2 | Continue solutions discussions
SA2#163 | May 2024 | 2 |  | Continue solutions discussions
SA2#164 | Aug 2024 | 2 |  | Continue and complete solutions discussions (preferably last time for solution update) Start evaluation/conclusion NOTE: need for new solutions will be checked after May meeting.
SA2#165 | Oct 2024 | 1.5 |  | Evaluation/conclusions
SA2#166 | Nov 2024 | 1.5 |  | Evaluation/conclusions
 | Total | 11.5 |  | 

## Slide 4: BACKUP

## Slide 5: FS_AmbientIoT Status after SA2#160AH-e
  Progress since SA2#160AH-e
  Study started with SA2#160AH-e.
  TR 23.700-13 v0.1.0 is available.
  40 TDocs were submitted and 22 Tdocs could not be handled due to TU budget/quota.
    The contents of the not handled Tdocs for new key issues were also considered in the discussion of the e-meeting.
  8 pCRs for TR skeleton, Scope, Terms, Architecture Assumptions/Requirements, 3 Key Issues to cover the WTs in the SID have been agreed.
  Key issue discussion has been finalized with two ENs(reference of the RAN TR to be updated, term name of “inventory” and “command” to be given). For future meetings, key issue update to address the ENs can be considered, but no new key issue proposal will be considered.
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Start solution discussions for agreed Key Issues in next meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 0% -> 13% | Dec 2024 | 1020071

## Slide 6: FS_AmbientIoT Status after SA2#161
  Progress since SA#102
  TR skeleton, Scope, Terms, Architecture Assumptions and Requirements are agreed
  3 key issues are agreed and no new key issue will be considered
  12 solutions are agreed and documented in the TR
  TR 23.700-13 v0.2.0 is available
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Continue solution discussions in SA2#162 meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 13% -> 25% | Dec 2024 | SP-231803 1020071

## Slide 7: FS_AmbientIoT Status at SA#103
  Progress since SA#102
  TR skeleton, Scope, Terms, Architecture Assumptions and Requirements are agreed
  3 key issues are agreed and no new key issue will be considered
  12 solutions are agreed and documented in the TR
  TR 23.700-13 v0.2.0 is available
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Continue solution discussions
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 13% -> 25% | Dec 2024 | SP-231803 1020071