## Slide 1: FS_UIA_ARC pre-Meeting Conference Call
Mike Starsinic (Rapporteur)
InterDigital

## Slide 2: Agenda
  Review of the work plan
  Key Issue #4 Solutions
    (LGE) LGE_S2-240xxxx_UIA_New Sol for KI#4.docx
    (InterDigital) S2-2402996_FS_UIA_ARC_Key_Issue_4_Solution1.docx
    (Ericsson) Ericsson_S2-2404xxx_devices-behind-5GRG-UE - ConferenceCall.docx
    (CableLabs) S2-2402944 - UE ID behind RG.docx
    (OPPO) OPPO_S2-240xxxx New Sol KI#4 devices behind 5G-RG_Pre-SA2#162_CC.docx
    (interDigital) S2-2403002_FS_UIA_ARC_Key_Issue_4_Solution2.docx
  Review the Informal Feedback from Companies on Key Issues 1 – 3.
    Company Input
      (OPPO) S2-24xxxxxr00_FS_UIA_ARC_Arch_Adding principles for solution evaluation.docx
    For each key issue review the rapporteur summary and proposal.
      (Rapporteur Summary) S2-240xxxx-FS_UIA_ARC_QA_rev_08_summary_v2.docx

## Slide 3
FS_UIA_ARC Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR, Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 1.5 | 1.5 | Key Issue Updates (e.g. KI#4 editor’s note), Solutions
SA2#162 | Apr 2024 | 1.75 |  | Solution Updates, New Solutions, Partial Evaluations Solutions that apply to a KI with no/few existing solutions in the TR (i.e. FS_UIA_ARC Key Issue #4), New solutions significantly different to existing one and proposed in a previous meeting but not handled, Time needs also to be given to papers that propose conclusions/solution principles.
SA2#163 | May 2024 | 1.5 |  | Evaluations, Solution Updates (Preferably only KI#4), Conclusions
 | Total | 5.25 | 2.0 | 
Total 9.5 TUs
  5.25 TUs for Study Phase
  4.25 TUs for Normative Work

## Slide 4: Backup

## Slide 5: FS_UIA_ARC Status after SA2#161
  Progress since SA2 #160AH-e
  Focus was on New Solutions and resolving the EN in KI#4.
  TR 23.700-32 v0.2.0 is available.
  48 TDocs were submitted to SA2 #161: 6 Key Issue Updates and 42 New Solutions
  2 Key Issue #4 Updates were agreed.
  16 New Solutions were agreed (for Key Issues #1, #2, and #3).
  27 papers were not handled.
    8 KI#1 Solutions were not handled.
    3 KI#2 Solutions were not handled.
    3 KI#3 Solutions were not handled.
    13 KI#4 Solutions were not handled.
  Impacts and Dependencies on other WGs
  Key Issue #2 has some SA3 dependency; e.g., authentication aspects.
  Key Issue #3 has some SA3 dependency; e.g., privacy/exposure aspects.
  Key Issue #3 may have some SA6 dependency; e.g., exposure aspects.
  No RAN dependency
Contentious issues
  None
Next steps
  In the next meeting: Solution Updates, New Solutions, Partial Evaluations
WI Code | Work Item Title | WP | Target Date | WID#
FS_UIA_ARC | Study on User Identities and Authentication Architecture | 15% -> 35% | June 2024 | 1020063

## Slide 6: FS_UIA_ARC Status at SA#103
  Progress since SA #102
  TR skeleton, Scope, Terms, and Architectural Assumptions/Requirements, are agreed.
  4 key issues to cover all 3 work tasks are agreed.
  16 New Solutions were agreed and document in the TR (for Key Issues #1, #2, and #3).
  No solutions for Key Issue #4 were handled.
  TR 23.700-32 v0.2.0 is available.
  Impacts and Dependencies on other WGs
  Key Issue #2 has some SA3 dependency; e.g., authentication aspects.
  Key Issue #3 has some SA3 dependency; e.g., privacy/exposure aspects.
  Key Issue #3 may have some SA6 dependency; e.g., exposure aspects.
  No RAN dependency
Contentious issues
  None
Next steps
  In the next meeting: Solution Updates, New Solutions, Partial Evaluations
WI Code | Work Item Title | WP | Target Date | WID#
FS_UIA_ARC | Study on User Identities and Authentication Architecture | 0% -> 35% | June 2024 | 1020063