## Slide 1: Status report for Study on Energy Efficiency and Energy Saving (FS_EnergySys)
Jungshin Park (Samsung),
Konstantinos Samdanis (Lenovo)

## Slide 2: FS_EnergySys Status after SA2#162
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 65% | SP-231192 | 75% | Study in progress
  General
  Total 86 TDocs were submitted, and 18 Tdocs were handled during 1 TU session
  10 pCRs have been agreed, and 1 LS has been postponed
  Unhandled new solution proposals and interim conclusions were prioritized, based on leadership guidance
  Solutions updates could not allocate time, and had to defer the discussion to next meetings
  TR 23.700-66 v0.5.0 is available
  Progress since SA2#161
  Total 7 new solutions have been accepted in the meeting
    2 new solutions have been added for KI#2
    5 new solutions have been added for KI#3
  Interim conclusions have been formed to facilitate further discussion before/at May meeting
  1 LS from TSG RAN on ‘per-UE energy consumption in RAN’ has been postponed

## Slide 3: FS_EnergySys Status after SA2#162
  RAN impacts and dependencies
  RAN impacts/dependencies are possible based on proposed solutions documented in TR
  Other WG dependencies
  SA5 dependencies are possible based on proposed solutions documented in TR
  Contentious issues
  None
  Plans for upcoming meetings (1 TU remaining)
  SA2#163: Critical solution updates only, Complete study conclusion, Prepare a WID proposal
  for normative work based on conclusion

## Slide 4: FS_EnergySys Work Plan
Total 13 TUs
  6.5 TUs for Study Phase
  6.5 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 1 | 1 | Continue discussion on Key Issues, start solution discussion
SA2#160AH-e | Jan 2024 | 1 | 1 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1.5 | 1.5 | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 1 | 1 | Focus on solution updates, only unhandled new solution proposals from #161, start discussion on evaluation and conclusion
SA2#163 | May 2024 | 1 |  | Critical solution updates only, Complete study conclusion, Prepare a WID proposal for normative work based on conclusion
 | Total | 6.5 |  |