## Slide 1: FS_5GSAT_Ph3 _ARCH Status Report Study on Integration of satellite components in the 5G architecture Phase 3
Jean-Yves Fine - Thales (Rapporteur)
Hucheng Wang – Catt (Co-rapporteur)

## Slide 2
General
  TR 23.700-29 v0.5.0 available
  Before the meeting, 42 solutions are listed in the TR
  Meeting outputs:
  1 LS response to SA3 on security of IP transport over satellite transport links
  3 additional new solutions (inherited from SA2#161) (2 for KI2; 1 for KI3) are agreed during the meeting, bringing the total to 45.
  9 existing solutions for KI#2 are updated.
  KI#1: LS to RAN3 (S2-2405600) agreed.
  List of principles for evaluation agreed for KI#2
  RAN impacts and dependencies
  Yes, on WT#1, WT#2
Contentious issues
  KI#1: IWK/Proxy, new RAT type, hard feeder link switchover
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSAT_Ph3_ARCH | Study on Integration of satellite components in the 5G architecture Phase 3 | 55 -> 75% | June, 2024 | SP-231199
FS_5GSAT_Ph3 _ARCH status after SA2#162 (1/3)

## Slide 3
Status on conclusion
  KI#1: to be concluded according RAN3 feedback on candidate mechanisms and assumptions (RAN3#123bi15/19May) and NWM outcomes in SA2#163 or latter (as alignment to RAN3)
  KI#2: List of principles for evaluation agreed.
  KI#2: to be concluded in SA2#163
  KI#3: List of principles for evaluation bootstrapped, to be completed on 3GPP discussion list.
  KI#3: to be concluded in SA2#163
Plan for how to complete the conclusions by end of the May meeting
On the basis of interim conclusions and principles for evaluations, rapporteur to use NWM to draft proposed solution principles and conclusions for input to the May meeting
Next steps
  @SA#163
    Conclude on KI#2 solution principles according NWM outcomes
    Conclude on KI#3 solution principles according NWM outcomes
    Conclude on KI#1 if RAN3 response to LS received and according NWM outcomes
FS_5GSAT_Ph3 _ARCH status after SA2#162 (2/3)

## Slide 4
Overall Plan
FS_5GSAT_Ph3 _ARCH work plan (3/3)
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, definition, assumption, scenario
SA2#160 | Nov 2023 | 1 | 1 | Key Issues, assumptions
SA2 E-AH | Jan 2024 | 1.5 | 1,5 | last meeting for Key Issues update (no new KI), start solution discussions
SA2#161 | Feb 2024 | 1 |  | Planned: Provide/update solutions. Start solutions evaluation Done: Provide solutions
SA2#162 | Apr 2024 | 1.5 |  | New solutions: only possible to resubmit new solution prio1 not open docs in Athens (max 6 docs). Make a short list of solution to be updated (max 10). Start evaluation on KI#1
SA2#163 | May 2024 | 1 |  | Complete evaluations and conclusions
 | Total | 7 |  |