## Slide 1: Release 19 FS_MPS4msg Status Report
Robert Streijl
Peraton Labs (Rapporteur)

## Slide 2: FS_MPS4msg Status after SA2#163
  General
  Evaluation and conclusion papers were submitted and agreed
  Study complete
  TR sent for approval to SA #104
  Normative WID revised based on the TR conclusions and sent to SA#104 for approval
  RAN impacts and dependencies
  None
  Other WG dependencies
  None
  Contentious issues
  None
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 18/06/2024 | 70% | SP-231672 | 100% | 

## Slide 3: FS_MPS4msg Work Plan
Total 6 TUs
  3 TUs for Study Phase – used 2.25
  3 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 0 | 0 | 
SA2#160 | Nov 2023 | 0.75 | 0.75 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160-AH-e | Jan 2024 | 0.5 | 0.5 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 0.5 | 0.5 | Complete solutions
SA2#162 | Apr 2024 | 0 | 0 | 
SA2#163 | May 2024 | 1.25 | 0.5 | Resolve open issues and ENs. Evaluations and conclusions.
 | Total | 3 | 2.25 | 

## Slide 4: FS_MPS4msg Status at SA#104
Progress since SA#103
  Completed evaluations and conclusions
  Study complete
  TR 23.700-75v0.4.0
RAN impacts and dependencies
  None
Contentious issues
  None
Next steps
  Start normative phase
WI Code | Work Item Title | WP | Target Date | WID#
FS_MPS4msg | Study on MPS for IMS Messaging and SMS services | 70% -> 100% | June 2024 | SP-231672
 | Aug, 24 | Oct, 24 | Nov, 24 | 
WID | #164 | #165 | #166 | Total TUs
MPS4msg | 1 | 1 | 1 | 3