## Slide 1: Rel-18 Status 5GMS_Pro_Ph2 and Potential Impact for Rel-19
Thomas Stockhammer (Rapporteur), Richard Bradbury (Editor)
Qualcomm Technologies, BBC
Document is identical to S4aI230201 which was agreed in MBS SWG
tsto@qti.qualcomm.com
3GPP TSG SA WG4 Meeting #127 S4-240113
Sophia Antipolis, France 29 January – 2 February 2024 rev of S4aI230201

## Slide 2: Relevant Documents and Timelines
SP-230976 WID 5G Media Streaming Protocols Phase 2
S4-231683 Updated Work Plan, Qualcomm Incorporated,
S4-232002 TS 26.510 V0.4.0 editor's draft, BBC,
S4-232008 Permanent Document v0.2.0, Qualcomm Incorporated (Rapporteur)
S4-232009 5GMS Functions are general Media Functions, Qualcomm Incorporated, BBC, Tencent (endorsed)
S4-232010 RTC Functions are general Media Functions, Qualcomm Incorporated (endorsed)
SA4#127 (29 January - 2 February 2024, Sophia Antipolis, FR) | Agree CRs to 26.512 5G Media Streaming Protocols Phase 2 Agree CRs to 26.247 DASH extensions for 5G Media Streaming Phase 2 Agree CR to 26.517 Extensions to MBS User Services to support 5GMS Agree CR to 26.532 Extensions to Event Exposure to support Network Assistance Agree TS 26.510 v2.0.0 to be sent to SA plenary for approval. Complete the permanent document on handling commonalities and inconsistencies across stage-2 specifications of TS26.501 and TS26.506. Communicate with other 3GPP working groups and external organizations, in particular 5G-MAG, on need basis Endorse work item summary
Supporting IM name
Qualcomm Incorporated
Tencent
BBC
Sony Europe B.V.
Orange
Dolby Laboratories Inc.
AT&T
Ericsson
HuaWei Technologies Co., Ltd
Samsung Electronics, CO., LTD
NTT

## Slide 3: Work Item Objectives
# | Objective | Supporters and Efforts
1 | Stage 3 support for uplink streaming as defined in TS 26.501 and based on the conclusions in clause 6.5 of TR 26.804. | explicit supporters Tencent, BBC; expected efforts medium
2 | Stage 3 support for end-to-end low latency live streaming as defined in TS 26.501 and based on the conclusions in clause 6.11 of TR 26.804. | explicit supporters Qualcomm, Tencent, BBC; expected efforts medium
3 | Stage 3 support for 5GMS over MBS and 5GMS hybrid services as defined in TS 26.501 and based on the conclusions in TR 26.804 and TR 26.802 | explicit supporters Qualcomm, BBC; expected efforts medium
4 | Stage 3 support for multiple media service entry points as defined in TS 26.501 and based on the conclusions in TR 26.804. | explicit supporters Qualcomm, Tencent, BBC; expected efforts medium
5 | Extensions to 5GMS protocols to support traffic identification based on the conclusions in TR 26.804, clause 6.3. | explicit supporters Ericsson, Qualcomm, Huawei, BBC; expected efforts low
6 | Addition of HTTP/3 to the 5GMS protocols as an optional alternative based on the conclusions in clause 6.4 of TR 26.804. | explicit supporters Tencent, BBC; expected efforts low
7 | Addition of necessary parameter extensions to the M1, M5, and M6 reference points to provide access to Background Data Transfer based on the conclusions in clause 6.6 of TR 26.804. | explicit supporters Qualcomm, BBC; expected efforts medium
8 | Specification of the usage of Oauth 2.0 (according to the SA3 guidelines) for 5GMS protocols based on the conclusions in clause 6.9 of TR 26.804. | explicit supporters Ericsson, BBC, Qualcomm; expected efforts medium
9 | Specifications for the 3GPP Service Handler and URL including the necessary functions on UE and device to support automatic launch of 5G System services in the context of 5G Media Streaming based on the conclusions in clause 6.13 of TR 26.804. | Qualcomm, BBC, Dolby, Tencent; expected efforts medium
10 | Additional minor enhancements based on feedback from 5G-MAG Reference tool developments. | BBC, Qualcomm, Dolby; expected efforts low
11 | Specification of a RESTful API at reference point M3 for the configuration of 5GMS AS instances by 5GMS AF based on the conclusions in TR 26.804. | BBC, Qualcomm, Tencent; expected efforts low
12 | Specification of data types for data reporting of ANBR-based Network Assistance invocations and (in liaison with CT3) specification of data types for exposure of events relating to invocation of AF-based and ANBR-based Network Assistance. | Sony, BBC; expected efforts medium
13 | Develop a new specification for Generalized media delivery to document interactions and APIs for provisioning and media session handling consolidating the stage-3 specification for reference points M1/RTC-1, M5/RTC-5 and M6/RTC-6 and port general functionalities from TS 26.512 to this new specification. | BBC, Qualcomm, Tencent, Samsung, NTT Expected efforts: high

## Slide 4: 1) Uplink streaming
Documents
  S4-231834 26.510 pCR: Uplink streaming improvements on draft 0.1.0, Tencent Cloud (agreed)
    BBC revision agreed and Content Publishing procedures incorporated into TS 26.510 V1.0.0.
  S4-231652 26.512 CR0038: Uplink Streaming: content publishing and egest, Tencent, BBC (endorsed)
    Procedures already moved to separate TS 26.510 pCR and incorporated into V1.0.0 (see above).
    Egest content protocols (clause 8) merged by Richard into S4aI230175 26.512 CR0047 (see Work Item objective 2).
Impacted Specifications: TS 26.510, TS 26.512
Candidate for TS 26.510: Yes
Status
  75% complete
Outstanding Issues
    Content Publishing Provisioning API clause in TS 26.512 CR0038 still needs to be converted into a pCR targeting TS26.510.
      Corresponding OpenAPI YAML also needed.
Expect completion at SA4#127
1 | Stage 3 support for uplink streaming as defined in TS 26.501 and based on the conclusions in clause 6.5 of TR 26.804. | explicit supporters Tencent, BBC; expected efforts medium | 

## Slide 5: 2) Low Latency and Dynamic Policies
Documents
  S4-231972 26.512 CR0047 Low-Latency Streaming and Dynamic Policies, Qualcomm, Ericsson (endorsed)
Impacted Specification: TS 26.512
Candidate for TS 26.510: No
Status
  80% complete
Outstanding Issues
  See endorsed CRs
  Richard merged in all other media plane CRs. Latest version in S4aI230175 back with Thomas for completion.
Expect completion at SA4#127
2 | Stage 3 support for end-to-end low latency live streaming as defined in TS 26.501 and based on the conclusions in clause 6.11 of TR 26.804. | explicit supporters Qualcomm, Tencent, BBC; expected efforts medium | 80% yes

## Slide 6: 3) 5GMS over MBS
Documents
  S4-231973 26.512 CR0048 5GMS over MBS and 5GMS hybrid services, Qualcomm (endorsed)
Impacted Specification: TS 26.512
Candidate for TS 26.510: No
Status
  80% complete
Outstanding issues
  See endorsed CRs
Expect completion at SA4#127
3 | Stage 3 support for 5GMS over MBS and 5GMS hybrid services as defined in TS 26.501 and based on the conclusions in TR 26.804 and TR 26.802 | explicit supporters Qualcomm, BBC; expected efforts medium | 

## Slide 7: 4) Multiple Media Service Entry Points
Documents
  S4-231471 26.512 CR0049 [5GMS_Pro_Ph2] Multiple media service entry points, Qualcomm (endorsed)
    Merged by Richard into S4aI230175 26.512 CR0047 (see Work Item objective 2).
  S4-231971 26.512 CR0051 Multiple Service Entry & Uplink streaming: media entry point, Tencent (endorsed)
    Merged by Richard into S4aI230175 26.512 CR0047 (see Work Item objective 2).
Impacted Specification: TS 26.512
Candidate for TS 26.510: possibly
Status
  95% complete
Outstanding Issues
  See endorsed CRs
  Richard merged in all other media plane CRs. Latest version in S4aI230175 back with Thomas for completion.
Expect completion at SA4#127
4 | Stage 3 support for multiple media service entry points as defined in TS 26.501 and based on the conclusions in TR 26.804. | explicit supporters Qualcomm, Tencent, BBC; expected efforts medium | 

## Slide 8: 5) Traffic Identification
Documents
  S4-231754 26.512 CR0052 Traffic Identification, Ericsson LM (endorsed)
Impacted Specifications: TS 26.512
Candidate for TS 26.510: recommended
Status
  80% complete
Outstanding Issues
  See endorsed CR
  Recommend conversion to TS 26 510 pCR
Expect completion at SA4#127
5 | Extensions to 5GMS protocols to support traffic identification based on the conclusions in TR 26.804, clause 6.3. | explicit supporters Ericsson, Qualcomm, Huawei, BBC; expected efforts low | 

## Slide 9: 6) HTTP/3
Documents
  S4-231854 26.512 CR0050 [5GMS_Pro_Ph2] Add HTTP-3 as allowed protocol in 26.512, Tencent (noted)
    Media plane aspects (5MGS AS at M2/M4) merged by Richard into S4aI230175 26.512 CR0047 (see Work Item objective 2).
Impacted Specifications: TS 26.512
Candidate for TS 26.510: no
Status
  Decision at SA4#125 (Gothenburg) not to add HTTP/3 to the 5GMS AF at M1/M5.
  95% complete
Expect completion at SA4#127
6 | Addition of HTTP/3 to the 5GMS protocols as an optional alternative based on the conclusions in clause 6.4 of TR 26.804. | explicit supporters Tencent, BBC; expected efforts low | 

## Slide 10: 7) Background Data Transfer
Stage-2 approval
  S4-232004 26.501 CR0077 [5GMS_Ph2] Addition of Background Data Transfer feature, BBC, Qualcomm
  S4-232003 26.501 CR0081 [5GMS_Ph2] Addition the dynamic policies invocation for uplink streaming (incl. BDT)
    Both approved at SA#102 and already published in TS 26.501 V18.4.0.
Documents
  S4-231194 26.512 CR0045 Background Data Transfer in 5GMS, Qualcomm (endorsed)
  S4-231653 26.512 CR0058 [5GMS_Pro_Ph2] Improvements on Background Data Transfer in 5GMS, Tencent (noted)
  S4-231791 26.512 CR0061 MQTT notification channel, Qualcomm Germany (noted)
Candidate for TS 26.510: yes
Status: 50% complete
Outstanding Issues
  Recommend merging CR0058 into CR0045 before submitting as a TS 26.510 pCR.
  Corresponding OpenAPI YAML also needed.
Possible completion at SA4#127
7 | Addition of necessary parameter extensions to the M1, M5, and M6 reference points to provide access to Background Data Transfer based on the conclusions in clause 6.6 of TR 26.804. | explicit supporters Qualcomm, BBC; expected efforts medium | 

## Slide 11: 8) OAuth2.0
Documents
  S4-231753 TS 26.512 CR0059 Extending 5GMS with Oauth 2.0 support, Ericsson LM
Candidate for TS 26.510: Yes
Status
  75% complete (OpenAPI YAML already prototyped)
Discussion from SA4#126:
  Richard: Is the idea to obtain an authorization code, and use it subsequently in M5
  Thorsten: Yes
  Richard: Do we need this kind of security (oauth) at M5? Understand for M1. We got a security network right. What are you protecting against
  Thorsten: For example, you could have applications using policy templates of other applications that it is not intended to use
  Imed: Just to follow up, this is calls invoked my MSH, not by application. Maybe we need to dig deeper. Where will the MSH get it
  Thorsten: In 26804, we have done some scenarios. People should start looking
Outstanding Issues
  Thorsten to produce a pCR to TS 26.510 clause 7.1.4 providing descriptive text about API security token.
Potential completion at SA4#127
8 | Specification of the usage of Oauth 2.0 (according to the SA3 guidelines) for 5GMS protocols based on the conclusions in clause 6.9 of TR 26.804. | explicit supporters Ericsson, BBC, Qualcomm; expected efforts medium | 

## Slide 12: 9) Service URL Handler
Documents
  S4-231464 TS 26.512 CR0046 [5GMS_Pro_Ph2] Service URL Handling
    Main description of generic 3GPP Service URL needs to be redirected to TS 26.510 clause 6 pCR.
    Instantiation for 5G Media Streaming remains in this TS 26.512 CR.
  S4-231636 TS 26.512 CR0036 Rel-18 API changes to support 3GPP Service URL, BBC
    Change to M5 Service Access Information API so that the external service identifier is used as the query rather than Provisioning Session ID.
Candidate for TS 26.510: possibly
Outstanding Issues
  See endorsed CRs
  CR0046 to be split into two contributions, the second one a pCR to TS 26.510.
  CR0036 to be converted into a pCR to TS 26.510, including OpenAPI YAML changes.
Status
  60% complete
Unlikely completion at SA4#127
9 | Specifications for the 3GPP Service Handler and URL including the necessary functions on UE and device to support automatic launch of 5G System services in the context of 5G Media Streaming based on the conclusions in clause 6.13 of TR 26.804. | Qualcomm, BBC, Dolby, Tencent; expected efforts medium | 

## Slide 13: 10) 5G-MAG Feedback
Documents
  none
Candidate for TS 26.510: no
Status
  100% complete
Outstanding Issues
  None
Expect completion at SA4#127
10 | Additional minor enhancements based on feedback from 5G-MAG Reference tool developments. | BBC, Qualcomm, Dolby; expected efforts low | 

## Slide 14: 11) M3
Documents
  S4-231985 TS 26.512 CR0055 5GMS AS configuration procedures and APIs at M3, BBC (endorsed)
Candidate for TS 26.510: no
Outstanding Issues
  See endorsed CR
Status
  70% complete
Expect completion at SA4#127
11 | Specification of a RESTful API at reference point M3 for the configuration of 5GMS AS instances by 5GMS AF based on the conclusions in TR 26.804. | BBC, Qualcomm, Tencent; expected efforts low | 

## Slide 15: 12) ABNR-based Network Assistance
Documents
  S4-231843 26.532 CR0004 ANBR-based network assistance data reporting, Sony, BBC (approved)
  SP-231347 26.512 CR0040 ANBR-based network assistance data reporting, Sony, BBC (approved)
  SP-231229 26.512 CR0041 Event exposure APIs, BBC (approved)
  S4-231889 LS to CT3 (reply to C3-233582) Reply LS on event exposure APIs for 5G Media Streaming
Candidate for TS 26.510
  No
Outstanding Issues
  None
Status
  100% complete
Completed at SA#102
12 | Specification of data types for data reporting of ANBR-based Network Assistance invocations and (in liaison with CT3) specification of data types for exposure of events relating to invocation of AF-based and ANBR-based Network Assistance. | Sony, BBC; expected efforts medium | 

## Slide 16: 13) TS 26.510
Documents
  S4aI230185 [5GMS_Pro_Ph2] Further discussion on OpenAPI design, BBC (ad hoc agreed)
  S4aI230188 [5GMS_Pro_Ph2] TS 26.510 V1.0.1 editor's draft, BBC
  S4aI230192 TS 26.512 CR0057 Remove M1, M5 and M6 procedures and APIs, BBC
Candidate for TS 26.510: yes
Status
  60% complete
Outstanding issues
  Network interface specification clauses ported from TS 26 512 V17.7.0, modified according to WG agreements and indicating applicability to 5G Media Streaming and/or Real-time Media Communication.
  Agree pseudo Change Requests adding procedures and/or 3GPP merge requests and/or client APIs in the scope of the 5GMS_Pro_Ph2 and iRTCW SA4 Work Items.
  OpenAPI definitions will then be adjusted based on the agreed network interface specifications.
Expect completion to 75% at SA4#127  more work needed
13 | Develop a new specification for Generalized media delivery to document interactions and APIs for provisioning and media session handling consolidating the stage-3 specification for reference points M1/RTC-1, M5/RTC-5 and M6/RTC-6 and port general functionalities from TS 26.512 to this new specification. | BBC, Qualcomm, Tencent, Samsung, NTT Expected efforts: high | 

## Slide 17: Work Item Objectives Status
# | Objective | Supporters and Efforts | Status
1 | Stage 3 support for uplink streaming as defined in TS 26.501 and based on the conclusions in clause 6.5 of TR 26.804. | explicit supporters Tencent, BBC; expected efforts medium | 75%, yes
2 | Stage 3 support for end-to-end low latency live streaming as defined in TS 26.501 and based on the conclusions in clause 6.11 of TR 26.804. | explicit supporters Qualcomm, Tencent, BBC; expected efforts medium | 80%, yes
3 | Stage 3 support for 5GMS over MBS and 5GMS hybrid services as defined in TS 26.501 and based on the conclusions in TR 26.804 and TR 26.802 | explicit supporters Qualcomm, BBC; expected efforts medium | 80%, yes
4 | Stage 3 support for multiple media service entry points as defined in TS 26.501 and based on the conclusions in TR 26.804. | explicit supporters Qualcomm, Tencent, BBC; expected efforts medium | 95% yes
5 | Extensions to 5GMS protocols to support traffic identification based on the conclusions in TR 26.804, clause 6.3. | explicit supporters Ericsson, Qualcomm, Huawei, BBC; expected efforts low | 80%, yes
6 | Addition of HTTP/3 to the 5GMS protocols as an optional alternative based on the conclusions in clause 6.4 of TR 26.804. | explicit supporters Tencent, BBC; expected efforts low | 95%, yes
7 | Addition of necessary parameter extensions to the M1, M5, and M6 reference points to provide access to Background Data Transfer based on the conclusions in clause 6.6 of TR 26.804. | explicit supporters Qualcomm, BBC; expected efforts medium | 50%, possibly
8 | Specification of the usage of Oauth 2.0 (according to the SA3 guidelines) for 5GMS protocols based on the conclusions in clause 6.9 of TR 26.804. | explicit supporters Ericsson, BBC, Qualcomm; expected efforts medium | 75%, possibly
9 | Specifications for the 3GPP Service Handler and URL including the necessary functions on UE and device to support automatic launch of 5G System services in the context of 5G Media Streaming based on the conclusions in clause 6.13 of TR 26.804. | Qualcomm, BBC, Dolby, Tencent; expected efforts medium | 60%, no
10 | Additional minor enhancements based on feedback from 5G-MAG Reference tool developments. | BBC, Qualcomm, Dolby; expected efforts low | 100%, yes
11 | Specification of a RESTful API at reference point M3 for the configuration of 5GMS AS instances by 5GMS AF based on the conclusions in TR 26.804. | BBC, Qualcomm, Tencent; expected efforts low | 70%, yes
12 | Specification of data types for data reporting of ANBR-based Network Assistance invocations and (in liaison with CT3) specification of data types for exposure of events relating to invocation of AF-based and ANBR-based Network Assistance. | Sony, BBC; expected efforts medium | 100%, yes
13 | Develop a new specification for Generalized media delivery to document interactions and APIs for provisioning and media session handling consolidating the stage-3 specification for reference points M1/RTC-1, M5/RTC-5 and M6/RTC-6 and port general functionalities from TS 26.512 to this new specification. | BBC, Qualcomm, Tencent, Samsung, NTT Expected efforts: high | 60%, no

## Slide 18: Conclusions

## Slide 19: Status Check and Proposal
Of the 13 Work Topics, at least 9, up to 11, are expected to be completed at SA4#127
However, it is expected that not all topics can be completed
  Background Data Traffic required stage-2 updates
  Service URL requires some detailed checks across the specification
  TS 26.510/512 split requires final thoughts
  OpenAPI needs to be completed for TS 26.510 and TS 26.512
Three options:
  Complete work item at SA4#127 and add all features with a CR to the specfications and do feature corrections
  Complete work item at SA4#127 and defer non-completed features to the Rel-19
  Ask for an exception with a very clear set of actions to complete the remaining topics based on this slide deck.
    Two meeting cycles will allow OpenAPI to be integrated before sending TS 26.510 V2.0.0 to SA Plenary.
Rapporteur and Editor of TS 26.512 prefer Option 3  prepare exception for SA4#127
The completion of the work item should not stop the agreement of a new study related to advanced media delivery topics as long as the priority for SA4#127-bis-e and SA4#128 is on the completion of the work item
Preliminary considerations

## Slide 20: Learn lessons from TR 26.804
Generally the approach in TR 26.804 working on key issue worked well.
More detailed instructions on the exact normative work can accelerate normative work further
how well we did planning from TR 26.804 towards normative work – what worked well and what can we do better!