3GPP TSG-SA WG4 Meeting #131						S4-250148

Geneva, Switzerland, 17 – 21 Feburuary 2025

Source:	Panasonic Holdings Corporation

Title:	Consideration about the DaCAS time plan

Agenda item:	7.6

Document for:	DISCUSSION

- Introduction

The new WID on diverse audio capturing system for UEs has been approved [1].  The source has attempted to derive a possible time plan based on the scheduled 3GPP meetings and the necessary agreements and activities required to complete the Work Item.

- Discussion on the time plan

The expected output and timeline presented in the WID are as follows [1].

| Type | TS/TR number | Title | For info at TSG# | For approval at TSG# |
| --- | --- | --- | --- | --- |
| TS | 26.533 | Diverse audio Capturing System for UEs | SA#108 ( June. 2025) | SA#109 (Sep,2025) |

This indicates that SA4 will agree on a draft specification at its May meeting in Fukuoka and complete its work at its July e-meeting. Prior to the May meeting, SA4 will hold two meetings: one in February in Geneva and an e-meeting in April.

On the other hand, the WID explains that TS 26.533 consists of two parts, which require the specification of the items summarized below.

Part 1:

- Definition of a set of target devices / target device types:

  - Number of microphones

  - Overall microphone configuration model (e.g. placement and relative distances of microphones)

- Definition of minimum performance requirement / objective criteria of raw microphone signal performance and characteristics:

  - Directional response / SNR / Frequency response etc.

- Definition of requirements for signals

- Collection of a common database of raw/compensated microphone signals for the development of example solutions for converting raw/compensated microphone signals into at least one IVAS encoder input format.

Part 2:

- immersive audio capture example solutions for converting raw/compensated microphone signals into at least one IVAS encoder input format, considering acoustic processing for immersive signals:

  - Development

  - Evaluation (based on relevant sending side terminal audio quality test methods defined in TS 26.260)

  - Verification and potential revision of the minimum performance requirement/objective criteria for raw microphone signal performance and characteristics

  - Specification

  - Potential alignment with TS 26.260 and 26.261

By mapping each item to be completed onto each scheduled meeting, the source has derived the following time plan.

The source assumes the following:

- Evaluation methodologies and criteria to be evaluated should be agreed upon more than one month before the meeting that reviews the evaluation results.

- The verification phase should be allocated before the July SA4 meeting

- The collected database may have copyright issues that need to be resolved before the final evaluation of the candidate proposals for the example solutions.

- The target devices and the performance criteria to be evaluated should focus on the most relevant areas to make the schedule realistic.

- Interim ad-hoc meetings may be helpful; However, the intervals between the SA4 meetings are one or two months, which may not provide sufficient time for scheduling ad-hoc meetings.

| Date | Meeting | Activity |
| --- | --- | --- |
| 2025-02 | SA4#131 (2025/02/17-21) | - Agreement on definition of target devices - Agreement on definition of performance requirements / objective criteria and performance evaluation methodologies - Agreement on definition of requirements for signals - Start of collecting common database. Legal framework is established if necessary for resolving possible copyright issues. - Potential proponents of the example solutions are invited for starting performance evaluation according to the agreed methodologies. |
| 2025-04 | SA4#131-bis-e (2025/04/11-17) | - Revision of the performance evaluation methodologies if needed - Agreement on minimum performance requirements / objective criteria - Common database available for evaluation - Copyright issues must be cleared. Legal framework must be finished before the SA4#131-bis-e if necessary. - Agreement on deliverables of potential proponents of the example solutions for the SA#132 meeting. |
| 2025-05 | SA4#132 (2025/05/19-23) | - Review of deliverables of the proponents and their results of evaluation of example solutions. - Selection of the example solutions if necessary. - Draft TS 26.533. - Organization of verification tests. Agreement on sending draft TS 26.533 to SA for information Verification tests are initiated |
| 2025-06 | SA#180 (2025/06/10-13) | TSG-SA preview of draft TS 26.533 Verification test phase Preparation of final draft TS 26.533 |
| 2025-07 | SA4#133-e (2025/07/21-25) | - Review results of verification of (selected) example solutions. - Potential revision of the minimum performance requirements/objective criteria and characteristics. - Final draft TS 26.533. Agreement on sending final draft TS 26.533 to SA. |
| 2025-09 | SA#109 (2025/09/16-19) | TSG-SA approval of TS 26.533 |

- Concluding summary

This contribution document discussed a possible time plan of DaCAS.  A tentative time plan has been drafted.  The document also suggests allocating sufficient time for evaluation and verification.  Additionally, it recommends focusing on the most relative areas for defining target devices and the performance criteria to be evaluated.

- Reference

- SA WG4, “WID on Diverse audio Capturing System for UEs,” SP-241962, 3GPP TSG Meeting #106, Madrid, Spain, 10th – 13th December 2024.