## Slide 1: Release-17 Time Plan Proposal for OAM SA5#135e, 25 January – 3 February, 2021
Zou Lan, SA5 Vice-Chair, HUAWEI

## Slide 2: Background
Rel-17 release schedule was discussed in SA and RAN plenary in Dec. 2020 , Rel-17 release schedule were updated in SA#90E (Dec.2020).
We need to align the SA5 work plan with the overall 3GPP release schedule.
This tdoc uses the following references:
  SA#90e: 3GPP Work Plan review at Plenary #90e (SP-201146)
  SA#86 3GPP Newcomer Orientation.pdf
Comments to the time plan proposal are welcome before SA5#136e.

## Slide 3
Ref: SA#86 3GPP Newcomer Orientation.pdf

## Slide 4: Detailed view of SA5 OAM dependency with other groups
SA1
Requirements
SA2
Architecture
SA3
Security
SA4
Media
SA5 OAM
Stage 3
SA6
Apps/MC
RAN
Radio Access
CT – Protocols & Coding
Stage 1
Stage 2
Stage 3
time
SA5 OAM
Stage 1
SA5 OAM
Stage 2
O-RAN
ONAP
GSMA GST
ETSI ZSM
1
2
1. SA1 Management requirements refer to SA5 specifications.
2. Take GSMA GST deliverables as input
3. Align the MnS with ZSM
4. ONAP reuses SA5 MnS
5. Collaboration with SA2 on architecture and CN management
6. Collaboration with SA4 on QoE
7. O-RAN reuse SA5 MnS
8. Provide inputs to CT
9. Collaboration with RAN on RAN management
3
4
5
6
7
8
9

## Slide 5: Latest timelines from SA#90e
Ref: SA#90e SP-201146

## Slide 6: Latest timelines from SA#90e

## Slide 7: Consideration on SA5 OAM time management
1. Strictly follow the SA/CT release time plan (especially guarantee to align the stage 3 freeze time).
2. For the CT related feature, need to provide inputs to CT as early as possible.
3. Avoid exception as much as possible, narrow down the scope of the work in case the work can’t be finalized within the release planned time period.

## Slide 8: SA5 Leaders recommendation for Release plan (OAM) (1)
SA5 OAM Rel-17 plan
  Closure of WI/SI proposal: no new Rel-17 WI/SI is recommended after SA5 #136e.
  Stage 1 freeze: Jun.2021 (6 months later than SA/CT Rel-17 plan)
  Stage 2 freeze: Dec.2021 (6 months later than SA/CT Rel-17 plan)
  Stage 3(CT related): Mar.2022
  Stage 3(others): Jun.2022
SA5 Rel-18 plan
  Start of WI/SI proposal: new Rel-18 WI/SI is recommended from SA5 #139e.
  Stage 1 freeze: Jun.2022
SA/CT Rel-17 plan:
Stage 1 and content definition (already completed for a while)
Rel-17 stage 2 freeze (relevant for SA/CT) – June 2021 (TSGs#92)
Rel-17 stage 3 freeze – March 2022 (TSGs#95)
Rel-17 protocol coding freeze (ASN.1, OpenAPI, …) – June 2022 (TSGs#96)
RAN Rel-17 plan:
  RAN1 freeze: Dec.2021
  Stage 3 freeze:
  Sep.2021->Mar.2022
  ASN.1 freeze:
  Dec.2021->Jun.2022

## Slide 9: SA5 Leaders recommendation for Release plan (OAM) (2)
#135e
#136e
#137e
#139
SA5 OAM time plan
SA5 OAM Rel-17 plan:
Closure of WI/SI proposal: no new Rel-17 WI/SI is recommended after SA5 #136e.
Stage 1 freeze: Jun.2021
Stage 2 freeze: Dec.2021
Stage 3(CT related): Mar.2022
Stage 3(others): Jun.2022
SA5 Rel-18 plan：
Start of WI/SI proposal: new Rel-18 WI/SI is recommended from SA5 #139e.
Stage 1 freeze: Jun.2022
#140
#138
#141
#142
No new R17 WI/SI
Rel-17
Schedule
Rel-18
Schedule
(preliminary)
#143
R17 stage 1
R17 stage 2
R17 stage 3 (CT related)
R18 stage 1
R17 stage 3 (others)
Start new R18 WI/SI

## Slide 10: Thank you!

## Slide 11: Change History
SA5 #129e | S5-201349 SA5 Rel-17 time plan proposal for OAM
SA5# 131e | S5-203021 Rel-17 time plan proposal for OAM
SA5# 135e | S5-211081 Rel-17 time plan proposal for OAM