## Slide 1: Release-18/19 Time Plan Proposal for OAM SA5#146, 14 – 18 Nov, 2022
Zou Lan, SA5 Vice-Chair, HUAWEI
Thomas Tovinger, 3GPP SA5 Chair (Ericsson)

## Slide 2: Background
Rel-18 release schedule was discussed in SA and RAN plenary in Dec. 2021.
We need to align the SA5 work plan with the overall 3GPP release schedule.
This tdoc uses the following references:
  SA#94e: 3GPP Work Plan review at Plenary #94e (SP-211555)
  SA#86 3GPP Newcomer Orientation.pdf
Rel-19 work plan started discussion in SA from July 2022, an NWM document collecting comments from SA leaders and SA company representatives: https://nwm-trial.etsi.org/#/documents/7896
Rel-19 release planning was discussed in SA#97 plenary in Sep.2022, a discussion paper (SP-220994) is noted. Further off-line discussion until the next TSG SA meeting, based on this, was encouraged.
Update of SA5#141e endorsed tdoc S5-221173 in blue

## Slide 3
Ref: SA#86 3GPP Newcomer Orientation.pdf

## Slide 4: Detailed view of SA5 OAM relation with other groups
SA1
Requirements
SA2
Architecture
SA3
Security
SA4
Media
SA5 OAM
Stage 3
SA6
Apps/MC
RAN
Radio Access
CT – Protocols & Coding
Stage 1
Stage 2
Stage 3
time
SA5 OAM
Stage 1
SA5 OAM
Stage 2
O-RAN
ONAP
GSMA GST
ETSI ZSM
1
2
1. SA1 Management requirements refer to SA5 specifications.
2. Take GSMA GST deliverables as input
3. Align the MnS with ZSM
4. ONAP reuses SA5 MnS
5. Collaboration with SA2 on architecture and CN management
6. Collaboration with SA4 on QoE
7. O-RAN reuse SA5 MnS
8. Provide inputs to CT
9. Collaboration with RAN on RAN management
10. Collaboration with SA6 on exposure and edge computing
11. Collaboration with SA3 on security aspects
3
4
5
6
7
8
9
Note: To be updated with working progress in Rel-18
10
11
Ref: SA5#141e S5-221173

## Slide 5: Background information from latest 3GPP Work Plan review at Plenary #97 (1/2)
Ref: RP-221900 _CP-222012_SP-220972
So far SA5 Rel-18 time plan is not specifically shown in the latest 3GPP work plan

## Slide 6: Background information from latest 3GPP Work Plan review at Plenary #97 (2/2)
Ref: RP-221900 _CP-222012_SP-220972

## Slide 7: Current progress of 3GPP SA5 R18 (1/4)
Ref: SA5#145e S5-225006
There are 3 work items with no progress from SA5#143e.

## Slide 8: Current progress of R18 (2/4)
There are 8 studies, 5 studies with progress less than 50%, need to check whether the studies are planned to be finalized on time.
Ref: SA5#145e S5-225006

## Slide 9: Current progress of R18 (3/4)
There are 8 studies, 5 studies with progress less than 50%, need to check whether the studies are planned to be finalized on time.
Ref: SA5#145e S5-225006

## Slide 10: Current progress of R18 (4/4)
There are 7 studies, 5 studies with progress less than 50%, need to check whether the studies are planned to be finalized on time.
Ref: SA5#145e S5-225006

## Slide 11: Consideration on SA5 OAM R18&R19 time planning(1/2)
General considerations as agreed in S5-221173:
1. We should strictly follow the 3GPP release timelines (especially to align the stage 3 freeze date).
2. For the CT related features, we need to provide inputs to CT as early as possible.
3. Management aspects which have no CN/RAN dependency or which needs to influence CN/RAN should be addressed as early as possible.
4. Avoid exception requests as much as possible, in case the work could not be completed according to the time plan, either narrow down the scope of the work, or postpone the work to next release.
Concrete time planning consideration:
Rel-18 studies:
  For the topics which target to start corresponding work items in Rel-18, the studies need to be closed and corresponding work items be initiated no later than Mar, 2023. This is to leave enough time to produce high quality standardization specification within Rel-18 timeframe. For the leftover work which could not be finalized in the study, it could be considered for potential Rel-19 work.
  It’s also allowed to use the full Rel-18 time for the approved study items if there is no plan for standardization in Rel-18.
Rel-18 work items: all the work items are to be finished strictly following the 3GPP overall time schedule. Rapporteurs are requested to consider reasonable Rel-18 scope and coordinate the work with best utilizing the time.
Rel-19 studies/work items: closely following the SA Rel-19 discussion and provide SA5 relevant inputs if they are available.
Update of SA5#141e endorsed tdoc S5-221173 in blue

## Slide 12: Consideration on SA5 OAM R18&R19 time planning(2/2)
Dec.2022&Mar.2023
(check point-1 for SA R19 preparation activities)
Dec.2023
(check point-2)
Now
A. Rel-18 approved SIs
A-1: Keep study only in Rel-18
A-2: Close study and Initiate Rel-18 corresponding WI
A-2: Rel-18 corresponding WI starts
A-3: Close study with no Rel-18 corresponding WI
B. Rel-18 approved WIs
B-1. Objectives which reached consensus, produce Rel-18 specifications, Rel-18 closed
C. Potential Rel-19 topics
B-2.Objectives which need more time for discussion
C. New ideas for Rel-19
potential R19 topics and join the SA R19 workplan
①
②
③

## Slide 13
Release 18 timeline– figure with SA5 OAM
TSG#93-e
SA1 Stage 1100%
RAN4perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
RAN Content def.
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
*
2024
Now
Studies (SA5 OAM)
Stage 1 (SA5 OAM)
Stage 2 Functional and stage 3 work (OAM/CN related),
provide inputs to CT
Stage 2 Functional and stage 3 work (RAN related)
SA5 OAM Rel-18 Timeline
Ref: update of RP-221900 _CP-222012_SP-220972

## Slide 14: Release 18 timelines – with SA5 OAM text
Release 18 Freezes and other milestones, sorted by dates :
  Sept 2021 (TSG#93): Stage 1: 80% normative work; SA Workshop; joint SA/RAN/CT meeting
  Dec 2021 (TSG#94):
    Stage 1: 100% normative work
    RAN/SA/CT joint meeting on Rel-18 content
    SA2 Work Items prioritization
    RAN Content Definition
  Mar 2022 (TSG#95): RAN4-lead WIDs specified
  June 2022 (#96), Sept 2022 (#97) and Dec 2022 (#98): no specific deadline defined yet
  Mar 2023 (TSG#99): Stage 2 Functional work Freeze
  June 2023 (TSG#100): no specific deadline defined yet
  Sep 2023 (TSG#101): RAN1 Freeze
  Dec 2023 (TSG#102): Freeze of:
    Stage 3 (CT&SA)
    RAN2, RAN3, RAN4 Core
  Mar 2024 (TSG#103): “coding freeze”. Freeze of:
    ASN-1; Open APIs
  June 2024 (TSG#104): RAN4 Freeze
SA5 OAM Release 18 Freezes and other milestones, sorted by dates :
  Mar 2022 (TSG#95): SA5 SIDs/WIDs specified
  Sept 2022 (#97) and Dec 2022 (#98): SA5 SID concluded and Rel-18 WID started if needed
  Mar 2023 (TSG#99): Stage 1 work freeze
  Sep 2023 (TSG#101): Stage 2 Functional work Freeze and stage 3(OAM/CN related), provide inputs to CT
  Dec 2023 (TSG#102): Stage 2 Functional work Freeze and stage 3 (RAN related)
Start of R18
Support of SA2, provide inputs to CT
Support of RAN
Dec 2022 (SA#98) and Mar 2023(SA#99): SA5 SID concluded and Rel-18 WID started if needed
Jun 2023 (TSG#100): Stage 1 work freeze
updated to:
Update of SA5#141e endorsed tdoc S5-221173 in blue
Now

## Slide 15
Release 19 timeline– figure with SA5 OAM
TSG#93-e
Note: All starting dates are indicative
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
*
2024
Now
Release 19
SA1 Stage 1 80%
100%
RAN4
content def.
RAN Content def.
*
Rel-19 planning
SA5 OAM Rel-19 Timeline

## Slide 16: Leaders’ recommendation for SA5 OAM time planning for endorsement
SA5 OAM Release 18 planning：
Mar 2022 (TSG#95): SA5 SIDs/WIDs specified
Dec 2022 (#98) and Mar 2023(#99): SA5 SID concluded and Rel-18 WID started if needed
Jun 2023 (TSG#100): Stage 1 work freeze (Majority topics)
Sep 2023 (TSG#101): Stage 1 leftover and Stage 2 Functional work Freeze and stage 3(OAM/CN related), provide inputs to CT
Dec 2023 (TSG#102): Stage 2 Functional work Freeze and stage 3 (RAN related)
SA5 OAM Release 19 planning：
Dec 2022: closely follow SA Rel-19 discussion and provide SA5 relevant Rel-19 inputs/planning if they are available
Dec 2023 (TSG#102): Start of Rel-19 following 3GPP release timelines
Note:
We should strictly follow the 3GPP release timelines (especially to align the stage 3 freeze date).
For the CT related features, we need to provide inputs to CT as early as possible.
Management aspects which have no CN/RAN dependency or which needs to influence CN/RAN should be addressed as early as possible.
Avoid exception requests as much as possible, in case the work could not be completed according to the time plan, either narrow down the scope of the work, or postpone the work to next release.
Update of SA5#141e endorsed tdoc S5-221173 in blue

## Slide 17: Thank you!

## Slide 18: Change History
SA5 #141e | S5-221173 SA5 Rel-18 time plan proposal for OAM
SA5 #146 | S5-226377 Rel-18&Rel-19 Time Plan Proposal for OAM