## Slide 1: SA6#46-e Work Plan Review
Suresh Chitturi
SA6 Chair
SAMSUNG

## Slide 2: Overview: Rel-17 Work Items – 1/2
Work Item | WI Code | WID Approved | SA#93-e | SA6#45-BIS-e | SA6#46-e | Target Completion | Remarks
Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 | eMONASTERY2 | SA#84 (06/2019) | 100% | 100% | 100% | SA#89 (09/2020) | 
MC services support on IOPS mode of operation | MCIOPS | SA#84 (06/2019) | 100% | 100% | 100% | SA#89 (09/2020) | 
Enhanced Mission Critical Push-to-talk architecture phase 3 | enh3MCPTT | SA#87 (03/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 
Enhancements for functional architecture and information flows for Mission Critical Data | eMCData3 | SA#86 (12/2019) | 100% | 100% | 100% | SA#92 (06/2021) | 
Architecture for enabling Edge Applications | EDGEAPP | SA#86 (12/2019) | 99% | 99% | 100% | SA#90 (12/2020) | 

## Slide 3: Overview: Rel-17 Work Items – 2/2
Work Item | WI Code | WID Approved | SA#93-e | SA6#45-BIS-e | SA6#46-e | Target Completion | Remarks
Enhanced application layer support for V2X services | eV2XAPP | SA#89 (09/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 
Application Architecture for MSGin5G Service | 5GMARCH | SA#89 (09/2020) | 90% | 95% | 100% | SA#92 (06/2021) | 
Mission Critical Services over 5GS | MCOver5GS | SA#89 (09/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 
Enhanced Service Enabler Architecture Layer for Verticals | eSEAL | SA#90 (12/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 
Application layer support for Uncrewed Aerial System (UAS) | UASAPP | SA#90 (12/2020) | 100% | 100% | 100% | SA#92 (06/2021) | 

## Slide 4: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#93-e | SA6#45-BIS-e | SA6#46-e | Target Completion | Remarks
Study on Mission Critical Services support over 5G System | FS_MCOver5GS | SA#80 (06/2018) | 87% | 89% | 91% | SA#96 (06/2022) | 
Study of Interconnection and Migration Aspects for Railways | FS_IRail | SA#88 (06/2020) | 60% | 70% | 85% | SA#94 (12/2021) | TR for approval at SA#95-e
Study on Network Slice Capability Exposure for Application Layer Enablement | FS_NSCALE | SA#91 (03/2021) | 25% | 30% | 55% | SA#96 (06/2022) | Revised SID at SA6#46-e (target date – Jun 2022)
Study on application enablement aspects for subscriber-aware NB API access | FS_SNAAPP | SA#92 (06/2021) | 20% | 40% | 65% | SA#95 (03/2022) | TR for information at SA#94-e Target completion to be shifted to SA#96.
Study on Application Capability Exposure for IoT Platforms | FS_ACE_IOT | SA#92 (06/2021) | 15% | 25% | 40% | SA#95 (03/2022) | 

## Slide 5: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#93-e | SA6#45-BIS-e | SA6#46-e | Target Completion | Remarks
Study on enhanced Application Architecture for enabling Edge Applications | FS_eEDGEAPP | SA#92 (06/2021) | 10% | 30% | 45% | SA#96 (06/2022) | Revised SID at SA6#45-BIS-e (target date – Jun 2022)
Study on 5G-enabled fused location service capability exposure | FS_5GFLS | SA#92 (06/2021) | 20% | 25% | 40% | SA#96 (06/2022) | Revised SID at SA6#46-e (target date – Jun 2022)
Study on enhanced architecture for UAS Applications | FS_eUASAPP | SA#93 (09/2021) | 0% | 5% | 10% | SA#97 (09/2022) | Revised SID at SA6#45-BIS-e (target date – Sep 2022)
Study on SEAL data delivery enabler for vertical applications | FS_SEALDD | SA#93 (09/2021) | 0% | 15% | 30% | SA#96 (06/2022) | 
Study on enhancements to application layer support for V2X services; Phase 2 | FS_eV2XAPP2 | SA#93 (09/2021) | 0% | 10% | 30% | SA#96 (06/2022) | 

## Slide 6: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#93-e | SA6#45-BIS-e | SA6#46-e | Target Completion | Remarks
Study on Application Data Analytics Enablement Service | FS_ADAES | New SID |  |  |  | SA#97 (09/2022) | Agreed at SA6#45-BIS-e
Study on Application layer support for Personal IoT and Residential Networks | FS_PIRatesAPP | New SID |  |  |  | SA#97 (09/2022) | Agreed at SA6#46-e
Study on sharing of administrative configuration between interconnected MC service systems | FS_MCShAC | New SID |  |  |  | SA#99 (03/2023) | Agreed at SA6#46-e
Study on Mission Critical Aad hoc gGroup Communications Support for Mission Critical Services | FS_MCAHGC | New SID |  |  |  | SA#97 (09/2022) | Agreed at SA6#46-e

## Slide 7: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#93-e | SA6#45-BIS-e | SA6#46-e | Target Completion | Remarks
Mission Critical Services over 5MBS | MCOver5MBS | SA#93 (09/2021) | 0% | 10% | 30% | SA#95 (03/2022) | 
Gateway UE function for Mission Critical Communication | MCGWUE | SA#93 (09/2021) | 0% | 20% | 50% | SA#96 (06/2022) | 
Application layer support for Factories of the Future (FF) | FFAPP | SA#93 (09/2021) | 0% | 5% | 15% | SA#98 (12/2022) | 
Enhanced Service Enabler Architecture Layer for Verticals Phase 2 | eSEAL2 | New WID |  |  |  | SA#98 (12/2022) | Agreed at SA6#45-BIS-e
Enhanced Mission Critical Push-to-talk architecture phase 4 | enh4MCPTT | New WID |  |  |  | SA#99 (03/2023) | Agreed at SA6#45-BIS-e
Mission Critical Services over 5GProSe | MCOver5GProSe | New WID |  |  |  | SA#99 (03/2023) | Agreed at SA6#45-BIS-e

## Slide 8: Rel-18 Content and Timeline (Endorsed in S6-212437 & S6-212840)
Proposal #1: Formal prioritization exercise will not be undertaken for SA6 in Rel-18, however, “content freeze” shall be established at SA6#46-e i.e. further new WID/SIDs, with the exception of “follow-up” WIDs based on ongoing study-items, may be accepted after SA6#46-e meeting only with consideration to factors such as availability of TUs, impact to workload and urgency to pursue the item.
Proposal #2: The studies for Rel-18 must be concluded latest by June 2022 or Sep 2022, to allow sufficient time (i.e. at least 9 months, maximum of 6 meetings) for normative work, failing which it can result in a risk of completion of the Rel-18 normative work by March 2023 or may be subject to down-scoping.
Proposal #3: All approved Rel-18 WID/SIDs will be on the agenda during e-meetings. Additionally, time allocations for specific agenda items may be limited and time allocated to present/discuss each document may also be limited. Other strategies e.g. “alternating” agenda items, may be considered when F2F meetings resume.
Proposal #4: Rel-18 workload feasibility assessment to be prepared with inputs from Rapporteurs, based on the WID/SID objectives and the available TUs in Rel-18

## Slide 9: Conference calls and other items
Pre-SA6#47-e conference calls
  eEDGEAPP – 2 (date TBD)
  NSCALE – 1 (date TBD)
  MC – 1 (date TBD)
  New items (structure/skeleton/scope) – 1 (date TBD)
Q2/2022 SA6 meeting dates -> to be converted to e-meetings
Rapporteurs to make the draft TRs/TSs available within one week!
All pre-agreed/approved revisions MUST be in the inbox folder!
Rapporteurs to provide inputs to Rel-17 WI summaries (TR 21.917)
Current
Proposed
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC
SA6#48-e | 04 – 12 April 2022 | Online
SA6#49-e | 16 – 24 May 2022 | Online

## Slide 10: SA6 Chair Election
Elections to SA6 Chair position to be held in SA6#47-e meeting
  Mr. Suresh Chitturi completes two terms as SA6 Chair in Feb 2022
  Announcement will be made on the SA6 list with the details

## Slide 11: Thank You!