## Slide 1: FS_XRApp: Status and Work plan
Feb, 2024
Shaowen Zheng (CMCC)

## Slide 2: Outline
SID status and remarks
TU planning status
Summary

## Slide 3: SID status and remarks
TR 23.700-23 structure | Till SA6 #58 (10%) | Remarks | SA6 #59 (Ideally 35%)
Scope / Intro / Definitions | Scope, introduction added |  | 
Key Issues | Key issue #1: KPI measurement and exposure Key issue #2: E2E Multi-Modal Communication Flows | It is recommended to have finalized KI by SA6#60 | most KI(s) proposed agreed (more than 4?)
Application enablement architecture requirements | - | It is recommended to have architecture requirements per service. | General Application enablement architecture requirements agreed
Application enablement architecture for XR services | - | It is recommended to have finalized application enablement architecture by SA6#60 | General application enablement architecture for XR services agreed
Solutions | - | It is recommended to be finalized by SA6#61 | more than 1? solutions agreed
Business Relationships | - | - | Business Relationships agreed
Evaluation | - | It is recommended to be finalized by SA6#61 | 
Conclusions | - | It is recommended to be finalized by SA6#62 | 

## Slide 4: FS_XRApp(SID) TU planning
Meeting | TUs Planned |  | Work Planned | Completion rate | TUs Consumed | Work Completed
 | SID | WID |  |  |  | 
SA6#57 (Oct-23) | - | - | SID Approval |  | - | SID Approval completed
SA6#58 (Nov-23) | 0.5 TU | - | Skeleton, introduction, scope and Key Issues | SID: 10% | 0.5 (SID) | Skeleton, introduction, scope, and 2 Key issues agreed
SA6#59 (Feb-24) | 1.0 TUs | - | Key Issues, Architecture Requirements, Architecture , Business Models, Solutions | SID:35%? | 1.0 TU? | 
SA6#60 (Apr-24) | 1.0 TUs | - | Key Issues and Architecture (Freeze), Architecture Requirements, Solutions, Solution evaluation | SID:60%? |  | 
SA6#61 (May-24) | 1.0 TUs | - | Solutions, Solution evaluation and Conclusions. Send for Information. WID Approval | SID:85%? |  | 
SA6#62-Adhoc-e (Jul-24) | 0.5 TUs | 1.0 TUs | Finish Solution Conclusions, Send for Approval Begin Normative work (Architecture and Solutions, Business Relationships) | SID:100%? WID:10%? |  | 
SA6#62 (Aug-24) | - | 1.0 TUs | Architecture and Solutions | WID:40%? |  | 
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions | WID:70%? |  | 
SA6#64 (Nov24) | - | 1.0 TUs | Complete unfinished work, Send for Approval. | WID:100%? |  | 
Total | 4 TUs | 4 TUs |  |  | 0.5 TUs | 

## Slide 5: Summary
  More Key Issues and solutions are welcomed.
Suggested Work Plan
  SA6#59 (target: 35% completed)
    Ideally to reach the common understanding about the Business Relationships and the application enablement architecture for XR services.
    As many KIs approved as possible.
  SA6#60 (target: 60% complete)
    Get application enablement architecture and Key Issues freezed.
    As many solutions approved as possible.