## Slide 1: Rel-19 Status and Plan
Rel-19 Rapporteurs

## Slide 2: FS_eLSAPP (SID/WID) Status until SA6#61 (Rapporteur: Liping Wu)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#55 (May-23) | - | - | SID Approval | - | SID Approval completed
SA6#56 (Aug-23) | 0.5TU | - | Skeleton, Scope, Key Issues | 15% | Finish Skeleton, Scope and 2 key issues
SA6#57 (Oct-23) | 1.0 TU | - | Key Issues, Architecture Requirements, Solutions | 20% | Finish Architecture Requirements, 2 KI, 3 Solutions
SA6#58 (Nov-23) | 1.0 TU | - | Key Issues, Solutions | 30% | Finish 1 Solutions, update 3 solutions
SA6#59 (Feb-24) | 1.0 TU |  | Key Issues, Solutions | 40% | Finish 2 Solutions, update 2 solution
SA6#60 (Apr-24) | 1.0 TU | - | Key Issues(Freeze), Solutions, Start Solution Conclusions. Send for information, WID proposal | 60% | Finish KI updates, 1 new KI, 3 solutions updates
SA6#61 (May-24) | 0.5 TU | - | Solutions(Freeze), Finish Solution Conclusions. Send for Approval, WID Approval | 90%？ | Finish Arch requirements, Overall Evaluation and Conclusions, 3 new solutions
SA6#62-Adhoc-e (Jul-24) (TBC) |  | 0.5 TUs | Begin Normative work | Remaining work for SID/WID: Remaining ENs / Overall Evaluation and Conclusions for new solutions Normative work | 
SA6#62 (Aug-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#64 (Nov24) | - | 0.5 TUs | Complete unfinished work, Send for Approval. |  | 
Total | 5 TUs | 3 TUs |  |  | 

## Slide 3: eMMTelAPP (SID/WID) Status untill SA6#61 (Rapporteur: Yue Liu)
Meeting | TUs Planned |  | Work Planned | Completion rate | Work Completed
 | SID | WID |  |  | 
SA6#57 (Oct-23) | - | - | SID Approval |  | SID Approval completed
SA6#58 (Nov-23) | 0.5 TU | - | Skeleton, introduction, scope and Key Issues | SID: 10% | Skeleton, introduction, scope, and 2 Key issues agreed
SA6#59 (Feb-24) | 1.0 TUs | - | Key Issues, Architecture Requirements, Architecture , Business Models, Solutions | SID:20% | Key Issues, Architecture Requirements, Architecture , Business Models
SA6#60 (Apr-24) | 1.0 TUs | - | Key Issues (Freeze), Architecture, Architecture Requirements, Solutions, Solution evaluation | SID:45% | 2 Architecture Requirements, 5 new KIs, 8 new Solutions,
SA6#61 (May-24) | 1.0 TUs | - | Solutions, Solution evaluation and Conclusions. Send for Information. WID proposal | SID:70%? | Ongoing discussion: 7 solution updates, 7 new solutions, 2 conclusion, Coversheet, WID
SA6#62-Adhoc-e (Jul-24)(TBC) | 0.5 TUs | 1.0 TUs | Finish Solution Conclusions, Send for Approval Begin Normative work (Architecture and Solutions, Business Relationships) | Remaining work for SID/WID: Architecture requirements Architecture Solution evaluations Overall evaluation and Conclusion Normative work | 
SA6#62 (Aug-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#64 (Nov24) | - | 1.0 TUs | Complete unfinished work, Send for Approval. |  | 
Total | 4 TUs | 4 TUs |  |  | 
Meeting | TUs Planned |  | Work Planned | Completion rate | Work Completed
 | SID | WID |  |  | 
SA6#55 (May-23) | - | - | SID Approval | - | SID Approval completed
SA6#56 (Aug-23) | 1.0 TU | - | Skeleton, Scope, Key Issues | SID: 15% | Skeleton, scope, Analysis of gaps, Architectural Assumptions and Principles, and 2 Key issues agreed
SA6#57 (Oct-23) | 1.0 TU | - | Key Issues, Architecture Requirements | SID: 25% | 2 new KIs agreed
SA6#58 (Nov-23) | 1.0 TU | - | Key Issues, Architecture Requirements, Solutions | SID: 25% | No important progress, only some update of existing text
SA6#59 (Feb-24) | 1.0 TU | - | Key Issues, Architecture Requirements, Solutions | SID: 35% | Architecture and 3 other solutions
SA6#60 (Apr-24) | 1.0 TU |  | Key Issues (Freeze), Solutions, Start Solution Conclusions. Send for Information. WID Approval | SID: 45% | 5 new Key Issues, 2 new solutions and 2 updated solutions
SA6#61 (May-24) | 1.0 TU |  | Finish Solution Conclusions, Send for Approval WID Approval | SID: 70%? | 3 new solutions, 4 conclusions, Coversheet, WID proposal
SA6#62-Adhoc-e (Jul-24) (TBC) | - | 1.0 TU | Begin Normative work (architecture impacts) | Remaining work for SID/WID: Architecture requirements Architecture Solution for 2 Key Issuess Solution evaluations Overall evaluation and Conclusion Normative work | 
SA6#62 (Aug-24) | - | 1.0 TU | Architecture and Solutions, Deployment models |  | 
SA6#63 (Oct-24) |  | 1.0 TU | Architecture and Solutions, Deployment models |  | 
SA6#64 (Nov24) |  | 1.0 TU | Complete unfinished work, Send for Approval. |  | 
Total | 6 TUs | 4 TUs |  |  | 

## Slide 4: FS_AIMLAPP (SID/WID) Status until SA6#61 (Rapporteur: Manos)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#56 (Aug-23) | - | - | SID Approval |  | SID Approval completed
SA6#57 (Oct-09) | 2.0 TU |  | Skeleton, Scope, Key Issues, Solutions | 15% | Skeleton, Scope, 3 Key Issues Approved, 3 Solutions Approved
SA6#58 (Nov-13) | 1.0 TU |  | Key Issues, Architecture Requirements, Solutions, Background Analysis | 35% | Generic Requirements, Definitions, Background Analysis, 4 Key Issues Approved, 7 Solutions Approved
SA6#59 (Feb-24) | 1.0 TU |  | Key Issues (Freeze), Solutions and solution updates | 55% | KI updates, 9 solutions, background analysis
SA6#60 (Apr-24) | 1.0 TU |  | Stable Architecture, Solutions (Freeze), Solution Updates and Evaluations, Deployment/ Business Models | 80% | KI updates, 11 new solutions and sol updates, deployment scenarios, Architecture
SA6#61 (May-24) | 1.0 TU |  | Overall Evaluation and Conclusions. SID send for Approval. WID Approval | 95%? | Ongoing discussion: Business model, Arch requirements, Arch enhancements, Overall Eval and Conclusions, 3 new solutions, Coversheet, WID
SA6#62-Adhoc-e (Jul-24) (TBC) | - | 1.0 TU | Architecture, Deployments and Features (procedures and flows) | Remaining work for SID/WID: Remaining ENs / Overall Evaluation and Conclusions of new solution Normative work | 
SA6#62 (Aug-24) | - | 1.0 TU | Features (procedures and flows) and APIs |  | 
SA6#63 (Oct-24) | - | 1.0 TU | Features (procedures and flows) and APIs |  | 
SA6#64 (Nov24) | - | 1.0 TU | Complete unfinished work, Send for Approval. |  | 
Total | 6 TUs | 4 TUs |  |  | 

## Slide 5: FS_Metaverse_App (SID/WID) Status untill SA6#61 (Rapporteur: Sapan)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#57 (Oct-23) | - | - | SID Approval | - | SID Approval completed
SA6#58 (Nov-23) | 2.0 TUs | - | Skeleton, Scope, Key Issues |  | Skeleton, scope and 2 Key issues agreed
SA6#59 (Feb-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions |  | 1 Architecture option, 3 new KIs, 2 Solutions
SA6#60 (Apr-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions | 50% | Definitions, 2 new KIs, 5 Sol Update, 6 new solutions, 2 KI updates, 1 architecture option
SA6#61 (May-24) | 2.0 TUs | - | Key Issues (Freeze), Solutions, Start Solution Conclusions. Send for Information. WID Approval | 70%? | Ongoing discussion: Architecture req., Definition, 7 new solutions, 6 Sol Update, 3 Sol evaluation, 1 Overall evaluation and conclusion, 1 KI update, 1 new KI, 2 solution updates, Coversheet, WID
SA6#62-Adhoc-e (Jul-24) (10 – 18 July 2024 - TBD) | 2.0 TUs | 1.0 TUs | Finish Solution Conclusions, Send TR for Approval Begin Normative work (architecture impacts) | Remaining work for SID: Continue Architecture requirements Deployment models Business relationships Continue Solution evaluations Continue Overall evaluation and Conclusion | 
SA6#62 (Aug-24) | - | 2.0 TUs | Architecture and Solutions, Business Relationships |  | 
SA6#63 (Oct-24) | - | 3.0 TUs | Architecture and Solutions, Deployment models |  | 
SA6#64 (Nov24) | - | 3.0 TUs | Complete unfinished work, WID complete / Send for Approval. |  | 
Total | 10 TUs | 9 TUs |  |  | 

## Slide 6: FS_XRApp (SID/WID) Status untill SA6#61 (Rapporteur: Shaowen Zheng)
Meeting | TUs Planned |  | Work Planned | Completion rate | Work Completed
 | SID | WID |  |  | 
SA6#57 (Oct-23) | - | - | SID Approval |  | SID Approval completed
SA6#58 (Nov-23) | 0.5 TU | - | Skeleton, introduction, scope and Key Issues | SID: 10% | Skeleton, introduction, scope, and 2 Key issues agreed
SA6#59 (Feb-24) | 1.0 TUs | - | Key Issues, Architecture Requirements, Architecture , Business Models, Solutions | SID:20% | Key Issues, Architecture Requirements, Architecture , Business Models
SA6#60 (Apr-24) | 1.0 TUs | - | Key Issues (Freeze), Architecture, Architecture Requirements, Solutions, Solution evaluation | SID:45% | 2 Architecture Requirements, 5 new KIs, 8 new Solutions,
SA6#61 (May-24) | 1.0 TUs | - | Solutions, Solution evaluation and Conclusions. Send for Information. WID proposal | SID:70%? | Ongoing discussion: 7 solution updates, 7 new solutions, 2 conclusion, Coversheet, WID
SA6#62-Adhoc-e (Jul-24)(TBC) | 0.5 TUs | 1.0 TUs | Finish Solution Conclusions, Send for Approval Begin Normative work (Architecture and Solutions, Business Relationships) | Remaining work for SID/WID: Architecture requirements Architecture Solution evaluations Overall evaluation and Conclusion Normative work | 
SA6#62 (Aug-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#64 (Nov24) | - | 1.0 TUs | Complete unfinished work, Send for Approval. |  | 
Total | 4 TUs | 4 TUs |  |  | 

## Slide 7: FS_5GSAT_Ph3_App (SID/WID) Status untill SA6#61 (Rapporteur: Basu)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#57 (Oct-23) | - | - | SID Approval |  | SID Approval completed
SA6#58 (Nov-23) | 1.0 TU | - | Skeleton, Scope, Key Issues |  | Skeleton, scope and 2 Key issues agreed
SA6#59 (Feb-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions |  | 1 KI updated, 3 new KIs, 1 solution
SA6#60 (Apr-24) | 2.0 TUs | - | Key Issues, Architecture Requirements, Solutions | 40% | 1 KI updated, 2 new KIs, 1 solution updated, 2 new solutions
SA6#61 (May-24) | 2.0 TUs | - | Key Issues (Freeze), Solutions, Start Solution Conclusions. Send for Information. WID Approval | 60%? | Ongoing discussion: 1 KI update, 2 new KIs, 2 solution updates, 6 new solutions, Coversheet, WID
SA6#62-Adhoc-e (Jul-24) (TBC) | 2.0 TUs | 2.0 TUs | Finish Solution Conclusions, Send for Approval Begin Normative work (architecture impacts) | Remaining work for SID/WID: Architecture requirements Deployment models Architecture Business relationships Solution evaluations Overall evaluation and Conclusion Normative work | 
SA6#62 (Aug-24) | - | 2.0 TUs | Architecture and Solutions, Business Relationships |  | 
SA6#63 (Oct-24) | - | 2.5 TUs | Architecture and Solutions, Deployment models |  | 
SA6#64 (Nov24) | - | 2.5 TUs | Complete unfinished work, Send for Approval. |  | 
Total | 9 TUs | 9 TUs |  |  | 

## Slide 8: FS_CAPIF_Ph3 (SID/WID) Status until SA6#61 (Rapporteur: Diego Preciado Rojas)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA#102 (Dec-23) | - | - | SID Approval | - | SID (presented as company contribution to SA) Approval completed
SA6#59 (Feb-24) | 0.5 TUs | - | Skeleton, Scope, Key Issues | 20% | Skeleton, scope and 7 Key issues Approved
SA6#60 (Apr-24) | 0.5 TUs | - | Key Issues, Architecture Requirements, Solutions | 40% | 5 Solutions Approved. 1 Key Issue Updated.
SA6#61 (May-24) | 0.5 Tus | - | Key Issues, Architecture Requirements, Solutions | 55% | Ongoing discussion: 11 solutions, 1 KI
SA6#62-Adhoc-e (Jul-24) (TBC) | 0.5 TUs |  | Key Issues (Freeze), Solutions, Solution evaluations/Overall evaluation. WID agreement | Remaining work for SID/WID: New KIs (consideration from external WGs/SDOs) Architecture aspects Solutions for KI#2, #6 Solution evaluations Overall evaluation and Conclusion Normative work | 
SA6#62 (Aug-24) | 1.0 TUs- | 1.0 TUs | Conclusions, Send for Approval, Begin Normative work (based on agreed WID) |  | 
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#64 (Nov24) | - | 1.0 TUs | Architecture and Solutions (remaining) |  | 
Total | 3 TUs | 3 TUs |  |  | 

## Slide 9: enhMC(WID) Status untill SA6#61 (Rapporteur: Harish Negalaguli)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#55 (Oct-23) | - | - | WID Approval |  | enhMC WID was agreed
SA6#56 (Nov-23) | - | - | Enhancements/corrections to MC Specs |  | Broadband Call out feature introduction
SA6#57 (Oct-23) | - | 1.0 TU | Solutions/Enhancements |  | Priority & Resource Management, Group-Regroup corrections
SA6#58 (Nov-23) | - | 1.0 TU | Solutions/Enhancements |  | Emergency Alert corrections, New feature discussions on MCGWUE
SA6#59 (Feb-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures) | 40% | Logging disc, Enh to Location, Multi-logon and corrections to existing MCX
SA6#60 (Apr-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures) |  | Minor corrections/enhancements to MCX
SA6#61 (May-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures) | 60% | UE-UE Relay, Location CRs and Logging disc
SA6#62-Adhoc-e (Jul-24) (TBC) | - | 0 | Solutions & Architecture(flows, Procedures) | Remaining work for SID/WID: MCX enhancements according to the remaining objectives, especially: Discreet listening and logging for mission critical services; Temporary MCX User with Limited Service mode; Expand the message storage coverage to also MCPTT and MCVideo services; Enhancements to the existing procedures or specify new procedures for all MC services to cover the gaps if any identified | 
SA6#62 (Aug-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures) |  | 
SA6#63 (Oct-24) | - | 1.0 TU | Solutions & Architecture(flows, Procedures) |  | 
SA6#64 (Nov24) | - | 1.0 TU | Complete unfinished work, Send for Approval. |  | 
Total | - | 8 TUs |  |  | 

## Slide 10: MCShAC (WID) Status until SA6#61 (Rapporteur: Andreas Flander)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#55 (May-23) | - | - | WID Approval | - | WID Approval completed
SA6#56 (Aug-09) | - | 0.6 TUs | Begin normative work | 10% | New chapter for MCShAC introduced to TS 23.280
SA6#57 (Oct-13) | - | 0.6 TUs | Architecture and Functional | 20% | Functional entities of ACM and ACM user profile
SA6#58 (Nov-23) | - | 0.6 TUs | Architecture and Solutions | 40% | Common ACM procedure, Updating group members of interconnected MC service group
SA6#59 (Feb-24) | - | 0.6 TUs | Architecture and Solutions | 90% | 5 CRs about solutions of MCShAC (4) and correction (1) – all objectives of WID MCShAC have been met
SA6#60 (Apr-24) | - | 0.6 TUs | Architecture and Solutions | 90% | No contributions (as of SA6#59 status for MCShAC)
SA6#61 (May-24) | - | 0.6 TUs | Architecture and Solutions | 90% | No contributions (as of SA6#59 status for MCShAC)
SA6#62-Adhoc-e (Jul-24) (TBC) | - | 0.6 TUs | None as of this meeting is about Rel-19 studies only | Remaining work for WID: 10% left over for corrections, miscellaneous and closing: E.g. specifying ACM client profile authorization enties in clause A.9 of TS 23.280 Miscellaneous | 
SA6#62 (Aug-24) | - | 0.6 TUs | Corrections, miscellaneous |  | 
SA6#63 (Oct-24) | - | 0.6 TUs | Corrections, miscellaneous |  | 
SA6#64 (Nov24) | - | 0.6 TUs | Closing. |  | 
Total | - | 6 TUs |  |  | 

## Slide 11: FRMCS_Ph5(SID/WID) Status untill SA6#61 (Rapporteur: Martin Oettl)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#56 (Aug) | - | - | WID Approval | - | WID approved
SA6#57 (Oct-09) | - | 1.0 TU | Solutions | - | Enhancements on ad hoc group communications, other minor changes
SA6#58 (Nov-13) | - | 1.0 TU | Solutions | - | Enhancements on ad hoc group communications, other minor changes
SA6#59 (Feb-24) | - | 1.0 TU | Solutions | - | Enhancements on ad hoc group communications Migration for Railways, other minor changes
SA6#60 (Apr-24) | - | 1.0 TU | Solutions | 45% | Migration for Railways, multi-talker control, other minor changes
SA6#61 (May-24) | - | 1.0 TU | Solutions | 55% | Client initiated connection establishment, corrections
SA6#62-Adhoc-e (Jul-24) (TBC) | - |  | - | Remaining work for SID/WID: Continue work on solutions as described in the objectives of the WID | 
SA6#62 (Aug-24) | - | 1.0 TU | Solutions |  | 
SA6#63 (Oct-24) | - | 1.0 TU | Solutions |  | 
SA6#64 (Nov24) | - | 1.0 TU | Complete unfinished work, |  | 
Total |  | 8TUs |  |  | 

## Slide 12: 5GMARCH_Ph3 (WID) Status untill SA6#61 (Rapporteur: Yue Liu)
Meeting | TUs Planned |  | Work Planned | Completion rate | Work Completed
 | SID | WID |  |  | 
SA6#55 (May-23) | - | - | WID Approval | - | WID Approval completed
SA6#56 (Aug-23) |  | 0 TU | No contribution | WID: 0% | 
SA6#57 (Oct-23) |  | 1.0 TU | solutions | WID: 10% | 1 Cat B CR
SA6#58 (Nov-23) |  | 0 TU | No contribution | WID: 10% | 
SA6#59 (Feb-24) |  | 1.0 TU | solutions | WID: 35% | 2 Cat C and 3C at F CRs
SA6#60 (Apr-24) |  | 1.0 TU | solutions | WID: 45% | 2 Cat B, 1 Cat C and 2 Cat F CRs
SA6#61 (May-24) |  | 1.0 TU | solutions | WID: 45% | 1 Cat F CR
SA6#62-Adhoc-e (Jul-24) (TBC) |  | - |  |  | 
SA6#62 (Aug-24) |  | 1.0 TU | solutions, Complete unfinished work, Send for Approval. |  | 
Total | 0 TUs | 5 TUs |  |  | 

## Slide 13: EDGEAPP_Ph3 (WID) Status untill SA6#61 (Rapporteur: Hyesung)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#57 (Oct-23) | - | 2 | Normative work for new or enhanced feature |  | Common EAS discovery/selection from federated partners Service continuity for common EAS Service continuity in ENS via leading ECSP Service continuity for ENS scenarios
SA6#58 (Nov-23) | - | 1.5 | Normative work for new or enhanced feature |  | 
SA6#59 (Feb-24) | - | 1.5 | Normative work for new or enhanced feature |  | 
SA6#60 (Apr-24) | - | 2.5 | Normative work for new or enhanced feature | 55% | 
SA6#61 (May-24) | - | 1.5? | Normative work for new or enhanced feature | 80%? | General enhancement of common EAS selection / Common EAS bundle discovery and selection
SA6#62-Adhoc-e (Jul-24) (TBC) | - | ? | Only LS related issue? | Remaining work for SID/WID: Service continuity of common EAS bundle EEL operation to support Dynamic EAS instantiation by ECSP management system in ENS scenarios Resolve Editor’s Note Address details and inconsistencies for all the objectives in the WID | 
SA6#62 (Aug-24) | - | ? | Addressing the remaining issues/inconsistency |  | 
SA6#63 (Oct-24) | - | ? | Addressing the remaining issues/inconsistency |  | 
SA6#64 (Nov24) | - | ? | Focus on the remaining issues/inconsistency |  | 
Total | 0 TUs | 9 TUs |  |  | 

## Slide 14: SEALDD_Ph2(SID/WID) Status untill SA6#61 (Rapporteur: Cuili Ge)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#56 (Aug) | - | - | WID Approval | - | SID Approval completed
SA6#57 (Oct-09) | - | 1.0 TU | Solutions | - | SEALDD enhancement based on network L4S capabilities, BAT; SEALDD Policy enhancement
SA6#58 (Nov-13) | - | 1.0 TU | Solutions | - | SEALDD enhancement based on network L4S capabilities
SA6#59 (Feb-24) | - | 1.0 TU | Solutions | - | SEALDD enhancements to support Background data transfer and the seamless SEALDD relocation enhancement with downlink data breakpoint information
SA6#60 (Apr-24) | - | 1.0 TU | Solutions | 55% | Connection and flow clarification, corrections.
SA6#61 (May-24) | - | 1.0 TU | Solutions | 70% | Client initiated connection establishment, corrections
SA6#62-Adhoc-e (Jul-24) (TBC) | - |  | Solutions | Remaining work for SID/WID: Further enhancement to the new features/procedures introduced in R19; | 
SA6#62 (Aug-24) | - | 1.0 TU | Solutions |  | 
SA6#63 (Oct-24) | - | 1.0 TU | Solutions |  | 
SA6#64 (Nov24) | - | 1.0 TU | Complete unfinished work, Send for Approval. |  | 
Total |  | 8TUs |  |  | 

## Slide 15: CAPIF_EXT(WID) Status untill SA6#61 (Rapporteur: Junpei Uoshima)
Meeting | TUs Planned |  | Work Planned | % Completion | Work Completed
 | SID | WID |  |  | 
SA6#56 (Aug-30) | - | - | WID Approval |  | WID Approval completed
SA6#57 (Oct-23) | - | 0.5 TU | Skeleton, Scope | 5% | Skeleton, Scope
SA6#58 (Nov-23) | - | 0.5 TU | References, Definitions, Overview of CAPIF | 20% | References, Definitions, Overview of CAPIF
SA6#59 (Feb-24) | - | 0.5 TU | Role of Stakeholders for API Exposure, Exemplary Use Cases and Adoption, Summary | 55% | Role of Stakeholders for API Exposure, 4 Exemplary Use Cases and Adoption, Summary
SA6#60 (Apr-24) | - | 0.5 TU | Exemplary Use Cases and Adoption | 65% | 2 Exemplary Use Cases and Adoption
SA6#61 (May-24) | - | 0.2TU | Exemplary Use Cases and Adoption | 80%? | Ongoing discussion: 4 Exemplary Use Cases and Adoption
SA6#62-Adhoc-e (Jul-24) (TBC) | - | 0.3 TU | Exemplary Use Cases and Adoption | Remaining work for SID/WID: Exemplary Use Cases and Adoption | 
SA6#62 (Aug-24) | - | 0.5 TU | Complete unfinished work, Send for Approval. |  | 
SA6#63 (Oct-24) | - | - |  |  | 
Total | - | 3 TUs |  |  |