## Slide 1: SA WG3 Status report for ‘FS_Metaverse_Sec’
Rohini Rajendran (Samsung), Lihui Xiong (OPPO)

## Slide 2
TUs planned
In SA3#115 Adhoc e-meeting:
  2 KIs agreed
In SA3#116 meeting:
  1 solution agreed
In SA3#117 meeting:
  Finalize all KIs (expect no more KI in further meeting)
  Expects companies to submit solutions as well
In SA3#118 meeting:
  Solution evaluation, conclusion
In SA3#119 meeting:
  Normative work
Overall plan
‘FS_Metaverse_Sec’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative)
WT1 | 1.5 | 0.5
WT2 | 1.5 | 0.5
WT3 | 1 | 1

## Slide 3
General
  Currently the SID includes only 2 KI, in SA3#117 it is expected to have new KI and solutions. Conclusions of these KI*s might take another meeting cycle.
Dependencies:
  SA3 progress depends on the LS response from SA1 and SA6
  Conclusion of each KI depends on SA6 work progress
Contentious Issue:
  None
Risks:
  Completing the normative work within timeline
‘‘FS_Metaverse_Sec’ status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030039 | Study on security aspects of 5G mobile metaverse services | ‘FS_Metaverse_Sec | Rel-19 | S3 | Mar-2024 | 0% | 20% | -

## Slide 4
Pending issues
  Issue#1: Authentication and authorization of digital asset
  Issue#2: Digital Asset management security
  Solutions to existing KIs
Dependencies:
  SA3 progress depends on the LS response from SA1 and SA6
  Conclusion of each KI depends on SA6 work progress
TUs consumed
  SA3#115 Adhoc-e - 0.5 TU
  SA3#116 - 0.25 TU
TUs remaining
  SA3#117 - 1 TU
  SA3#118 - 1 TU
  SA3#119 - 1 TU
Plan for completion
  SA3#119
‘‘FS_Metaverse_Sec’ pending work and plan for completion