## R5#104
3GPP TSG RAN WG5 (RAN5) Meeting #104 | [9 empty] | R5-244044(Draft v4)
Maastricht, Netherlands, 19 - 23 August 2024
WI Progress and Target Completion Date Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | Rel-16 | R5-244491 | 2024-12-01 | 52% | 53% | 2024-12-01 |  | CMCC
880069 | UE Conformance Test Aspects - 5G V2X with NR sidelink | Rel-16 | R5-244656 | 2024-12-01 | 68% | 73% | 2024-12-01 |  | Huawei | CR No.
900056 | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | Rel-17 | R5-244887 | 2024-12-01 | 11% | 11% | 2024-12-01 |  | Huawei
911003 | UE Conformance Test Aspects - NR-based access to unlicensed spectrum | Rel-16 | R5-245287 | 2024-12-01 | 79% | 85% | 2024-12-01 |  | Qualcomm | RAN#105
930051 | UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) | Rel-17 | R5-244757 | 2024-09-01 | 6% | 100% | 2024-09-01 |  | Ericsson | A.I.
950062 | UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 | Rel-17 | R5-244883 | 2024-12-01 | 49% | 51% | 2024-12-01 |  | Huawei
960072 | UE Conformance - NR small data transmissions in INACTIVE state | Rel-17 | R5-244199 | 2024-12-01 | 98% | 98% | 2024-12-01 |  | Qualcomm
960074 | UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) | Rel-17 | R5-245289 | 2024-12-01 | 78% | 82% | 2024-12-01 |  | Qualcomm | RAN#105
960075 | UE Conformance - Further enhancement on NR demodulation performance | Rel-17 | R5-244138 | 2024-09-01 | 93% | 100% | 2024-09-01 |  | China Telecom
960076 | UE Conformance - Enhancement of Private Network Support for NG-RAN including CT aspects | Rel-17 | R5-245090 | 2024-09-01 | 96% | 100% | 2024-09-01 |  | China Telecom
960079 | UE Conformance - Further enhancements on MIMO for NR | Rel-17 | R5-245130 | 2024-12-01 | 92% | 99% | 2024-12-01 |  | Samsung
960080 | UE Conformance - NR support for high speed train scenario in frequency range 2 | Rel-17 | R5-245136 | 2024-12-01 | 60% | 67% | 2024-12-01 |  | Samsung | +6month
960083 | UE Conformance - NR Sidelink Relay | Rel-17 | R5-244994 | 2024-09-01 | 30% | 40% | 2024-12-01 | +3 | CATT
960084 | UE Conformance - NR Sidelink enhancement | Rel-17 | R5-244992 | 2024-09-01 | 5% | 35% | 2025-03-01 | +6 | CATT
960089 | UE Conformance Test Aspects - NR RRM enhancement | Rel-16 | R5-245424 | 2024-12-01 | 70% | 75% | 2024-12-01 |  | Apple
970072 | UE Conformance - NR QoE management and optimizations for diverse services | Rel-17 | R5-244122 | 2024-09-01 | 20% | 100% | 2024-09-01 |  | Ericsson | AI
970075 | UE Conformance - NR Positioning Enhancements | Rel-17 | R5-244357 | 2024-12-01 | 56% | 70% | 2024-12-01 |  | CATT
970077 | Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) | Rel-16 | R5-244946 | 2024-09-01 | 82% | 100% | 2024-09-01 |  | NIST
1000050 | UE Conformance - Additional NR bands for UL-MIMO in Rel-18 | Rel-18 | R5-244750 | 2024-12-01 | 49% | 52% | 2024-12-01 |  | China Unicom | Meeting No
1000051 | UE Conformance - High power UE (power class 2) for NR FR1 FDD single band | Rel-18 | R5-244755 | 2024-12-01 | 12% | 15% | 2024-12-01 |  | China Unicom
1000054 | UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-245093 | 2025-06-01 | 55% | 65% | 2025-06-01 |  | China Telecom
1000056 | UE Conformance - UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL | Rel-17 | R5-244885 | 2025-06-01 | 9% | 9% | 2025-06-01 |  | Huawei
1000057 | UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations | Rel-18 |  | 2025-06-01 | 5% | 100% | 2025-06-01 | -9 | Huawei
1000058 | UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands | Rel-18 | R5-244889 | 2025-06-01 | 12% | 27% | 2025-06-01 |  | Huawei
1000059 | UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 | Rel-18 | R5-244399 | 2024-12-01 | 26% | 75% | 2024-12-01 |  | Nokia
1010051 | UE Conformance - Rel-17 LTE CA Configurations | Rel-17 | R5-245095 | 2024-12-01 | 50% | 70% | 2024-12-01 |  | China Telecom
1020087 | UE Conformance - Air-to-ground network for NR | Rel-18 | R5-244475 | 2025-06-01 | 50% | 57% | 2025-06-01 |  | CMCC
1020088 | UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | Rel-18 | R5-245166 | 2025-06-01 | 26% | 45% | 2025-06-01 |  | Huawei
1030060 | UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 | Rel-18 | R5-245712 | 2025-12-01 | 22% | 43% | 2025-12-01 |  | Nokia
1030061 | UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | Rel-18 | R5-244458 | 2025-06-01 | 5% | 14% | 2025-06-01 |  | China Telecom | RAN#105
1030062 | UE Conformance - Enhanced support of reduced capability NR devices plus CT1 | Rel-18 | R5-244787 | 2025-12-01 | 5% | 28% | 2025-12-01 |  | China Unicom
1030063 | UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects | Rel-18 | R5-245055 | 2025-12-01 | 5% | 40% | 2025-12-01 |  | Nokia
1030064 | UE Conformance - Introduction of 900 MHz LTE band in the US | Rel-18 | R5-244396 | 2025-03-01 | 85% | 85% | 2025-03-01 |  | Nokia
1030065 | UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | Rel-18 | R5-245443 | 2025-03-01 | 5% | 15% | 2025-03-01 |  | Apple | A.I.
1030066 | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 | Rel-18 | R5-244891 | 2025-06-01 | 5% | 12% | 2025-06-01 |  | Huawei
1030067 | UE Conformance - Network energy savings for NR | Rel-18 | R5-245185 | 2025-12-01 | 5% | 24% | 2025-12-01 |  | Huawei
1030068 | UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | Rel-18 | R5-245022 | 2025-06-01 | 58% | 76% | 2025-06-01 |  | Huawei | +71%
1030069 | UE Conformance - Further NR coverage enhancements | Rel-18 | R5-244692 | 2025-12-01 | 5% | 28% | 2025-12-01 |  | China Telecom
1030070 | UE Conformance - Multi-carrier enhancements for NR | Rel-18 | R5-245116 | 2025-12-01 | 18% | 80% | 2025-12-01 |  | China Telecom | +66%
1030071 | UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | Rel-18 | R5-245194 | 2025-12-01 | 5% | 36% | 2025-12-01 |  | Samsung | RAN#105
1030072 | UE Conformance - NR MIMO evolution for downlink and uplink | Rel-18 | R5-245192 | 2025-12-01 | 5% | 19% | 2025-12-01 |  | Samsung | RAN#105
1030073 | UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects | Rel-18 | R5-244470 | 2025-12-01 | 16% | 27% | 2025-12-01 |  | CMCC
1040102 | UE Conformance 4Rx for NR bands for FWA UEs (up to 2.6GHz) and handheld UEs (1GHz to 2.6GHz) | Rel-18 | R5-245468 | 2025-06-01 |  | 13% | 2025-06-01 |  | ZTE
1040103 | UE Conformance - Mobile Terminated-Small Data Transmission (MT-SDT) for NR | Rel-18 | R5-244201 | 2025-12-01 |  | 10% | 2025-12-01 |  | Qualcomm
1040104 | UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC | Rel-18 | R5-244513 | 2026-06-01 |  | 5% | 2026-06-01 |  | CMCC
1040105 | UE Conformance - NR demodulation performance evolution | Rel-18 | R5-244140 | 2025-12-01 |  | 8% | 2025-12-01 |  | China Telecom
1040106 | UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects | Rel-18 | R5-245097 | 2026-06-01 |  | 5% | 2026-06-01 |  | China Telecom
1040107 | UE Conformance - Expanded and improved NR positioning | Rel-18 | R5-244359 | 2026-06-01 |  | 5% | 2026-06-01 |  | CATT
1040108 | UE Conformance - Further NR mobility enhancements | Rel-18 | R5-244213 | 2025-12-01 |  | 20% | 2025-12-01 |  | MediaTek
1040109 | UE Conformance -Introduction of FDD LTE band (L+S band) for IoT NTN operation | Rel-18 | R5-244215 | 2025-03-01 |  | 95% | 2025-03-01 |  | MediaTek
1040110 | UE Conformance - Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | Rel-18 | R5-244217 | 2025-06-01 |  | 5% | 2025-06-01 |  | MediaTek
1040111 | UE Conformance - Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies | Rel-18 | R5-245445 | 2025-06-01 |  | 5% | 2025-06-01 |  | Apple | A.I.
1040112 | UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR Ues | Rel-18 | R5-245342 | 2025-06-01 |  | 40% | 2025-06-01 |  | Apple | +5% CR No.
1040113 | UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | Rel-18 | R5-245284 | 2025-12-01 |  | 5% | 2025-12-01 |  | Qualcomm | RAN#105