## Slide 1: Discussion of SA2 TU planning for Rel-20
Andy Bennett
SA WG2 Chair

## Slide 2: SA2 Rel-20 TU planning discussion
The main milestones for Rel-20 have mostly been decided
  Rel-20 content defined: June 2025
  5G-Advanced Stage 2 80%: June 2026
  5G-Advanced Stage 2 100%: September 2026
  6G Study 100%: December 2026 or March 2027 (TBD)
The focus of SA2 TU planning should be on the period March 2025 – September 2026
  This covers the time from the earliest possible existence of SA-approved Rel-20 Study or Work Items until the Stage 2 100% complete deadline
A possible timeline for 5G-Advanced topics is shown on the next slide
  It includes an interim deadline for completion of Rel-20 5G Advanced studies in February 2026

## Slide 3: Potential 5G Advanced timeline in Rel-20
It is important to note that any 5G Advanced study items approved by SA in June would have just 4 meetings until the suggested SA2 study completion target of February 2026
  It is important then that larger study + normative items will need to be approved by SA in March
The study completion target is required to ensure sufficient number of meetings to complete the normative work (and even so, only gives 3 meetings for this)
Stage 2 100% completion is intended to mean that there are no exceptions
  This is likely to be a challenge for anything more than a small/medium sized study + work item
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 | SA2 ad hoc | SA2#167 | SA#107 | SA2#168 | SA2#169 | SA#108 |  | SA2#170 | SA#109 | SA2#171 | SA2#172 | SA#110 | TBD | SA2#173 | SA#111 | SA2#174 | SA2#175 | SA#112 |  | SA2#176 | SA#113 | SA2#177 | SA2#178 | SA#114
Rel-19 Milestones | Stage 2 100% |  |  |  |  |  |  |  |  | Stage 3 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rel-20 milestones and events | 5GA WS |  |  | 6G WS Some SA2 5GA content |  |  | 5GA Stage 1 100% Rel-20 Content defined |  |  |  |  |  |  |  | Rel-20 5GA study 100% | 6G FS Stage 1 100% |  |  | 5GA Stage 2 80% |  |  | 5GA Stage 2 100% |  |  | 6G Study 100% (TBC)
5GA timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation Phase |  |  | #1 |  | #2 | #3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Study Phase |  |  |  |  | #1 | #2 |  |  | #3 |  | #4 | #5 |  |  | #6 |  |  |  |  |  |  |  |  |  | 
Normative phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | #1 | #2 |  |  | #3 |  |  |  | 
Maintenance phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | #1 | #2 | 

## Slide 4: Potential 6G timeline in Rel-20
This shows the meetings available for the 6G study work
The timeline extends beyond when the 5G-Advanced work needs to be completed
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 | SA2 ad hoc | SA2#167 | SA#107 | SA2#168 | SA2#169 | SA#108 |  | SA2#170 | SA#109 | SA2#171 | SA2#172 | SA#110 | TBD | SA2#173 | SA#111 | SA2#174 | SA2#175 | SA#112 |  | SA2#176 | SA#113 | SA2#177 | SA2#178 | SA#114
Rel-19 Milestones | Stage 2 100% |  |  |  |  |  |  |  |  | Stage 3 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rel-20 milestones and events | 5GA WS |  |  | 6G WS Some SA2 5GA content |  |  | 5GA Stage 1 100% Rel-20 Content defined |  |  |  |  |  |  |  | Rel-20 5GA study 100% | 6G FS Stage 1 100% |  |  | 5GA Stage 2 80% |  |  | 5GA Stage 2 100% |  |  | 6G Study 100% (TBC)
6G study timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation Phase |  |  |  |  | #1 | #2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Study Phase |  |  |  |  |  |  |  |  | #1 |  | #2 | #3 |  |  | #4 |  | #5 | #6 |  |  | #7 |  | #8 | #9 | 

## Slide 5: SA2 Rel-20 planning in more detail
The Rel-19 planning was based on a total number of TU’s per meeting of 36, or which 6 were buffer TU’s
The 6 buffer TU’s were for TEI19, Rel-18 alignment, overflow, 5G deployment issues, etc
We’ve seen that typically there are many drafting sessions in addition to the regular sessions, and these occupy Q0, lunch breaks and some Q5 time, this comprised an additional ~30% on top of the planned TU’s
Clashes between topics have meant not all parallel sessions can be used
In particular, it is difficult to schedule topics in parallel with large items that wide interest
  Should limit the TU’s per meeting per item allocation to 2
For these reasons the TU budget provided in SP-241670 has an additional 3 buffer TU’s per meeting built in (see the next slide)

## Slide 6: Summary of TU plan
SA2 | #167 | #168 | #169 | #170 | #171 | #172 | #173 | #174 | #175 | #176 | #177 | #178
Date | Feb-25 | Apr-25 | May-25 | Aug-25 | Oct-25 | Nov-25 | Feb-26 | Apr-26 | May-26 | Aug-26 | Oct-26 | Nov-26
Milestones and deadlines |  | Start some 5GA |  | Start all 5GA and 6G |  | Complete some 5GA studies | Complete all 5GA studies |  | 5GA Stage 2 80% | 5GA Stage 2 100% |  | 
Pre-Rel-19 maint | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Rel-19 maint | 15 | 11 | 11 | 9 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 2
Rel-19 exceptions | 8 |  |  |  |  |  |  |  |  |  |  | 
Rel-20 | 3 | 12 | 12 | 15 | 18 | 18 | 20 | 20 | 20 | 22 | 15 | 15
Rel-20 maint |  |  |  |  |  |  |  |  |  |  | 7 | 7
Total | 31 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
 |  | Duration of 5GA work in Rel-20 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Duration of 6G study work in Rel-20 (tbc) |  |  |  |  |  |  |  | 
 |  | Total TU's for Rel-20 March 25 - September 26 |  |  |  |  | 157 |  |  |  |  | 
 |  | Additional TU's for 6G after September 26 |  |  |  |  | 30 |  |  |  |  | 

## Slide 7: Some comments on the previous slide
The Rel-20 TU’s include “preparation” time, in other words time required to discuss the draft SIDs and WIDs
6 TU’s expected for this Rel-20 preparation in April and May 2025
So the TU budget that can be allocated to Rel-20 SIDs and WIDs is 157 – 6 = 151 TU’s
It can be expected that during the 6G study at least the first 6 months will be as a single stream, potentially splitting into parallel streams later
  This means that the TU estimate for the 6G study does not translate 1:1 into the number of sessions (a single stream = 2 or 3 TU’s, depending on whether running in parallel with 5G Advanced topics)
For 5G Advanced TU planning the TU budget for the normative WID should be the same as for the study
  Our experience in Rel-19 again indicates that this should be the approach taken

## Slide 8: Different time split scenarios
There has been discussion of how the TU budget in Rel-20 should be divided between 5G Advanced and 6G
The analysis here looks only at the period from March 2025 to September 2026
Some planning assumptions
  9 ordinary meetings in this period
  151 TU’s available for SI/WI TU budgets (excludes TU’s for SID/WID discussion)
  5G Advanced studies complete latest by March 2026 (gives 3 meetings for normative work)
  Maximum 2 TU’s per meeting per item for 5G Advanced items
  Study TU’s = Normative TU’s for 5G Advanced items
  Maximum TU’s for a 5G Advanced item = 12 (6 study + 6 normative)
  The mean total TU budget per Rel-19 item (excluding Ambient IoT) was 119.5/14 = 8.5 TU’s

## Slide 9: Different time split scenarios
Given these assumptions here is an illustration of the possible numbers of 5G Advanced Study + Work Item topics
Observations on the 6G budget
  Additional TU’s available after the Stage 2 freeze
5G Advanced |  | 6G |  | 5G Advanced items *
70% | 105 TU | 30% | 45 TU | 9 – 12
60% | 90 TU | 40% | 60 TU | 8 – 11
50% | 75 TU | 50% | 75 TU | 6 – 9
40% | 60 TU | 60% | 90 TU | 5 – 7
30% | 45 TU | 70% | 105 TU | 4 – 5
* Smaller number based on 12 TU’s per item, larger number based on 8.5 TU’s per item